## CMS PBI RPT View Details (hidden)
Business Value (Rank) | Reports | DB Developers | PBI Developers | Schema | Snowflake DEV View | QA View Staus | UAT View Staus | PROD View Staus | Reporting Sprint Goal | Report Number
1 | RPT_02_CO Flue Warning Tag Control | Rupa | Navya |  | gdm_rpt.vw_CO_Flue_Warning_Tag_Control |  |  |  |  | 28
2 | RPT_02_Warning Tag HEFPA | Sree | Shraddha | GDM_RPT | VW_WARNING_TAG_HEFPA |  |  |  |  | 29
3 | RPT_02_Warning tag Printout | Sree | Navya | [6 empty] | 30
4 | RPT_02_Corrosion | Siva | Sarath | [6 empty] | 31
5 | RPT_02_House Pipe Test Comment Control | Geeta | Shraddha | GDM_RPT | GDM_RPT.VW_CMS_HOUSE_PIPE_TEST_COMMENT |  |  |  |  | 32
6 | RPT_02 _Required Regulator Inspection Performed Control | Siddu | Navya | GDM_RPT | GDM_RPT.VW_REQUIRED_REGULATOR_INSPECTIONS_PERFORMED_CONTROL |  |  |  |  | 33
7 | RPT_02_Service Regulator Inspections | Sree | Sarath | GDM_RPT | GDM_RPT.VW_SERVICE_REGULATOR_INSPECTIONS |  |  |  |  | 34
8 | RPT_02_Service Regulator Inspection Printout | Sree | Sarath | GDM_RPT | GDM_RPT.VW_SERVICE_REGULATOR_INSPECTION_PRINTOUT |  |  |  |  | 35
9 | RPT_02_20 Year Regulator Inspection | Siddu | Navya | [6 empty] | 36
10 | RPT_02_Fixed Factor | Nick | Shraddha | [6 empty] | 37
11 | RPT_02_Fixed Factor Printout | Nick | Shraddha | [6 empty] | 38
12 | RPT_02_Fixed Factor Mismatch | Rupa | Sarath | [6 empty] | 39
13 | RPT_02_Work Order Completion Printout | Rupa | Sarath | [6 empty] | 40
14 | RPT_02_GRO Control | Siva | Navya | [6 empty] | 41
15 | RPT_02_GRO Monitor |  | Navya | [6 empty] | 42

## Report Migration Status (hidden)
April Delivery | [5 empty] | Release Date Schedule | [8 empty] | Total
Leak Reports | In Progress | DEV | PBI | In QA | In UAT | In Production | 2026-04-30 | 2026-05-07 | 2026-05-24 | 2026-05-28 | 2026-06-04 | 2026-06-11 | 2026-06-18 | 2026-06-25
8 | [6 empty] | 2026-04-30: 7; 2026-05-07: 1; 2026-05-24: 0
8
May Delivery | [5 empty] | Release Date Schedule
Leak Reports | In progress | DEV | PBI | In QA | In UAT | In Production | 2026-04-30 | 2026-05-07 | 2026-05-24 | 2026-05-28 | 2026-06-04 | 2026-06-11 | 2026-06-18 | 2026-06-25
10 | [6 empty] | 0 |  | 0 | 4 | 2 | 2 | 2 |  | Total
10
JuneDelivery | [5 empty] | Release Date Schedule
Leak Reports | In progress | DEV | PBI | In QA | In UAT | In Production | 2026-04-30 | 2026-05-07 | 2026-05-24 | 2026-05-28 | 2026-06-04 | 2026-06-11 | 2026-06-18 | 2026-06-25
9 |  | 3 | 1 |  | 2 |  | 0 |  | 0 |  |  | 1 | 1 | 1 | Total
3

## Leaks PBI RPT View Details (hidden)
Business Value (Rank) | Report Name | DB Developers | PBI Developers | Schema | Snowflake DEV View | QA View Staus | UAT View Staus | PROD View Staus | Reporting Sprint Goal | Report Number
1 | RPT_04_Active Leaks | Fetwi | Sarath | GDM_RPT | DEV_GDM_DEV_DB.GDM_RPT.VW_ACTIVE_LEAKS | Ready |  |  | Sprint 1 | 1
2 | RPT_04_Count of Active Leaks On Hand | Fetwi | Sarath | GDM_RPT | DEV_GDM_DEV_DB.GDM_RPT.VW_ACTIVE_LEAKS | Ready |  |  | Sprint 1 | 2
4 | RPT_04_Leak Scheduling | Sreevarsha | Sarath | GDM_RPT | DEV_GDM_DEV.GDM_RPT.VW_GAS_LEAK_SCHEDULING |  |  |  |  | NA
5 | RPT_04_Leak Days Remaining | Siva | Navya | GDM_RPT | DEV_GDM_DEV_DB.GDM_RPT.VW_LEAK_DAYS_REMAINING | Ready |  |  | Sprint 1 | 3
3 | RPT_04_Cleared Leaks | Sreevarsha | Sarath | GDM_RPT | DEV_GDM_DEV_DB.GDM_RPT.VW_CLEARED_LEAKS | Ready |  |  | Sprint 2 | 4
6 | RPT_04_Leaks Repaired Detail | Rupa | Shraddha | GDM_RPT | GDM_RPT.VW_LEAKS_REPAIRED_DETAIL | Ready |  |  | Sprint 2 | 5
7 | RPT_04_Leaks Aging | Sreevarsha | Navya | GDM_RPT | GDM_RPT.VW_LEAKS_AGING | Ready |  |  | Sprint 2 | 6
9 | RPT_04_Prior Leak Readings | Siddhu | Navya | GDM_RPT | DEV_GDM_DEV_DB.GDM_RPT.VW_PRIOR_LEAK_READINGS | Ready |  |  | Sprint 2 | 7
8 | RSS_04_Leak Grade Change History | Siva | Navya | GDM_RPT | DEV_GDM_DEV.GDM_RPT.VW_LEAK_GRADE_CHANGE_HISTORY |  |  |  |  | 8
14 | RPT_04_Rechecks Completed less than 14 days | Rupa | Shraddha | GDM_RPT | gdm_rpt.vw_Rechecks_Completed_less_than_14days |  |  |  | Sprint 3 | 9
15 | RPT_04_SEI Leak Activity | Siva | Shraddha | GDM_RPT | DEV_GDM_DEV_DB.GDM_RPT.VW_SEI_LEAK_ACTIVITY_LEAK_EXTENT |  |  |  | Sprint 3 | 10
|  |  |  | GDM_RPT | DEV_GDM_DEV_DB.GDM_RPT.VW_SEI_LEAK_ACTIVITY_LEAKS_LOC
13 | RPT_04_PSC Quarterly Leak | Geetha | Sarath | GDM_RPT | DEV_GDM_DEV_DB.GDM_RPT.VW_PSC_QUARTERLY_LEAKS |  |  |  | Sprint 3 | 11
10 | RPT_04_Surveillances With Zero Readings | Sreevarsha | Navya | GDM_RPT | GDM_RPT.VW_SURVEILLANCES_WITH_ZERO_READINGS |  |  |  | Sprint 3 | 12
11 | RPT_04 High Emitter leaks | Sreevarsha | Navya | GDM_RPT | GDM_RPT.VW_HIGH_EMITTER_LEAKS |  |  |  | Sprint 3 | 13
12 | RPT_04_School Zone Leaks Without Repair | Sreevarsha | Sarath | GDM_RPT | GDM_RPT.VW_SCHOOL_ZONE_LEAKS_REPORT |  |  |  |  | 14
16 | RPT_04_CMS Leak Productivity | Siddu | Navya | GDM_RPT | VW_CMS_LEAK_PRODUCTIVITY |  |  |  |  | 15
17 | RPT_04_Main Break Corrosion and Leak Cluster | Siddu | Sarath | GDM_RPT | VW_Leak_Cluster and VW_Main_Break |  |  |  |  | 16
18 | RPT_04_Leak Summary Status | Fetwi | Navya | GDM_RPT | DEV_GDM_DEV_DB.GDM_RPT.VW_LEAK_SUMMARY_STATUS |  |  |  |  | 17
19 | RPT_04_PSC Leak Printout | Fetwi | Shraddha | GDM_RPT | DEV_GDM_DEV_DB.GDM_RPT.VW_PSC_LEAK_PRINTOUT |  |  |  |  | 18
20 | RPT_04_Leak Increase Reads | Fetwi | Navya | GDM_RPT | DEV_GDM_DEV_DB.GDM_RPT.VW_LEAK_INCREASE_READS |  |  |  |  | 19
21 | RPT_04_Leak Control Report | Geetha | Navya | GDM_RPT | VW_LEAK_CONTROL, |  |  |  |  | 20
|  |  |  | GDM_RPT | VW_LEAK_CONTROL_COMPLETE, |  |  |  |  | 20
|  |  |  | GDM_RPT | VW_LEAK_CONTROL_REPAIR, |  |  |  |  | 20
|  |  |  | GDM_RPT | VW_LEAK_CONTROL_BACKLOG. |  |  |  |  | 20
22 | RPT_04_Leak Life Cycle | Geetha | Shraddha | GDM_RPT | VW_LEAK_LIFE_CYCLE_REPORT_LEAK_INVENTORY VW_Leak_Life_Cycle_Report_LeakInventoryWOSummary VW_LEAK_LIFE_CYCLE_REPORT_LEAKRECHECKSURVEY VW_LEAK_LIFE_CYCLE_REPORT_LEAK_READING VW_Leak_Life_Cycle_Report_LeakRepair VW_LEAK_LIFE_CYCLE_REPORT_LEAKREPAIRRESURVEY |  |  |  |  | 21
23 | RPT_04_Leak Life Cycle Legacy LMS LI |  | Navya |  | VW_DH_LEAK_LIFE_CYCLE_REPORT_LEAK_READING_LMS VW_DH_LEAK_LIFE_CYCLE_REPORT_LEAKINVENTORY_LMS VW_DH_LEAK_LIFE_CYCLE_REPORT_LEAKINVENTORYWOSUMMARY_LMS VW_DH_LEAK_LIFE_CYCLE_REPORT_LEAKRECHECKSURVEY_LMS VW_DH_LEAK_LIFE_CYCLE_REPORT_LEAKREPAIR_LMS VW_DH_LEAK_LIFE_CYCLE_REPORT_LEAKREPAIRRESURVEY_LMS |  |  |  |  | 22
24 | Leak 360 Dashboard | Siva | Sarath | GDM_RPT | VW_LEAKS360_DASHBOARD |  |  |  |  | 23
[5 empty] | VW_LEAKS360_DASHBOARD_LEAKSWORKORDER |  |  |  |  | 23
25 | RPT_04_Leak Recheck Control | Siva | Shraddha | GDM_RPT | GDM_RPT.VW_LEAK_RECHECK_CONTROL_FAILED_LEAKS_R30 |  |  |  |  | 24
|  |  |  | GDM_RPT | GDM_RPT.VW_LEAK_RECHECK_CONTROL_FMEXCEPTION
|  |  |  | GDM_RPT | GDM_RPT.VW_LEAK_RECHECK_CONTROL_LEAK_EXCEPTION
|  |  |  | GDM_RPT | GDM_RPT.VW_LEAK_RECHECK_CONTROL_LEAK_GRADE_CHANGE_SAME_DAY
GDM_RPT
|  |  |  | GDM_RPT | GDM_RPT.VW_LEAK_RECHECK_CONTROL_LEAK_RECHECK_ANALYSIS
26 | RPT_04_Main_Replacement Report | Sreevarsha | Navya |  | vw_Main_Replacement_Report |  |  |  |  | 25
27 | RPT_04_ Leak Repair Exception | Geetha | Shraddha |  | GDM_RPT.VW_LEAK_REPAIR_EXCEPTIONS |  |  |  |  | 26
28 | New Report called Leak_Sample_Point_Mismatch | Siddu | Shraddha | GDM_RPT | DEV_GDM_DEV_DB.GDM_RPT.VW_Leak_Sample_Point_Mismatch; |  |  |  |  | 27
* for QA/UAT/PROD provide status for availabilty

## Fact Table
Domain | Status | Status Start Date | Expected Release Date | Actual Release Date | Report Name | DB Developers | PBI Developers | Schema | PO
Leaks | In Production |  | 2026-04-30 | 2026-04-30 | RPT_04_Active Leaks | Fetwi | Sarath | GDM_RPT | PO3
Leaks | In Production |  | 2026-06-30 | 2026-06-30 | RPT_04_Count of Active Leaks On Hand |  |  |  | PO2
Leaks | In Production |  | 2026-06-30 | 2026-06-30 | RPT_04_Leak Days Remaining |  |  |  | PO3
Leaks | In Production |  | 2026-06-30 | 2026-06-30 | RPT_04_Cleared Leaks |  |  |  | PO1
Leaks | In Production |  | 2026-06-30 | 2026-06-30 | RPT_04_Leaks Repaired Detail |  |  |  | PO1
Leaks | In Production |  | 2026-06-30 | 2026-06-30 | RPT_04_Leaks Aging |  |  |  | PO1
Leaks | In Production |  | 2026-06-30 | 2026-06-30 | RPT_04_Prior Leak Readings |  |  |  | PO3
Leaks | In Production |  | 2026-06-30 | 2026-06-30 | RSS_04_Leak Grade Change History |  |  |  | PO3
Leaks | In Production |  | 2026-06-30 | 2026-06-30 | RPT_04_Surveillances With Zero Readings |  |  |  | PO2
Leaks | In Production |  | 2026-06-30 | 2026-06-30 | RPT_04 High Emitter leaks |  |  |  | PO1
Leaks | In Production |  | 2026-06-30 | 2026-06-30 | RPT_04_School Zone Leaks Without Repair |  |  |  | PO1
Leaks | In Production |  | 2026-06-30 | 2026-06-30 | RPT_04_PSC Quarterly Leak |  |  |  | PO1
Leaks | In Production |  | 2026-06-30 | 2026-06-30 | RPT_04_Rechecks Completed less than 14 days |  |  |  | PO2
Leaks | In Production |  | 2026-06-30 | 2026-06-30 | RPT_04_SEI Leak Activity |  |  |  | PO1
Leaks | In Production |  | 2026-06-30 | 2026-06-30 | RPT_04_CMS Leak Productivity |  |  |  | PO3
Leaks | In Production |  | 2026-06-30 | 2026-06-30 | RPT_04_Main Break Corrosion and Leak Cluster |  |  |  | PO3
Leaks | In Production |  | 2026-06-30 | 2026-06-30 | RPT_04_Leak Summary Status |  |  |  | PO1
Leaks | In Production |  | 2026-06-30 | 2026-06-30 | RPT_04_PSC Leak Printout |  |  |  | PO3
Leaks | In Production |  | 2026-06-30 | 2026-06-30 | RPT_04_Leak Increase Reads |  |  |  | PO3
Leaks | In Production |  | 2026-06-30 | 2026-06-30 | New Report: Leak Repair Exception |  |  |  | PO2
Leaks | In Production |  | 2026-06-30 | 2026-06-30 | RPT_04_Leak Control Report |  |  |  | PO1
Leaks | In Production |  | 2026-06-30 | 2026-06-30 | RPT_04_Leak Life Cycle |  |  |  | PO2
Leaks | In Production |  | 2026-06-30 | 2026-07-16 | RPT_04_Leak Life Cycle Legacy LMS LI | Fetwi | Navya |  | PO3
Leaks | QA |  | 2026-06-30 | 2026-07-16 | Leak 360 Dashboard | Siva | Sarath |  | PO3
Leaks | In Production |  | 2026-06-30 | 2026-06-30 | RPT_04_Leak Recheck Control |  |  |  | PO2
Leaks | In Production |  | 2026-06-30 | 2026-06-30 | Leak reading sample point mismatch |  |  |  | PO1
CMS | Dev |  | 2026-07-31 |  | RPT_02_CO Flue Warning Tag Control |  |  |  | PO1
CMS | Dev |  | 2026-07-31 |  | RPT_02_Warning Tag HEFPA |  |  |  | PO3
CMS | Dev |  | 2026-07-31 |  | RPT_02_Warning tag Printout |  |  |  | PO1
CMS | Dev |  | 2026-07-31 |  | RPT_02_Corrosion |  |  |  | PO2
CMS | Dev |  | 2026-07-31 |  | RPT_02_House Pipe Test Comment Control |  |  |  | PO2
CMS | Dev |  | 2026-07-31 |  | RPT_02 _Required Regulator Inspection Performed Control |  |  |  | PO1
CMS | Dev |  | 2026-07-31 |  | RPT_02_Service Regulator Inspections |  |  |  | PO1
CMS | Dev |  | 2026-07-31 |  | RPT_02_Service Regulator Inspection Printout |  |  |  | PO2
CMS | Dev |  | 2026-07-31 |  | RPT_02_20 Year Regulator Inspection |  |  |  | PO3
CMS | Dev |  | 2026-07-31 |  | RPT_02_Fixed Factor |  |  |  | PO3
CMS | Dev |  | 2026-07-31 |  | RPT_02_Fixed Factor Printout |  |  |  | PO2
CMS | Dev |  | 2026-07-31 |  | RPT_02_Work Order Completion Printout |  |  |  | PO2
CMS | Dev |  | 2026-07-31 |  | RPT_02_GRO Control |  |  |  | PO3
CMS | Dev |  | 2026-08-30 |  | RPT_02_GRO Monitor |  |  |  | PO2
CMS | Dev |  | 2026-08-30 |  | RPT_02_Public Buildings Inspection | Geetha |  |  | PO3
CMS | Dev |  | 2026-08-30 |  | RPT_02_Investigate Wall Check and Service Check | Sree |  |  | PO3
CMS | Dev |  | 2026-08-30 |  | RPT_02_Cut Out Orders | Fetwi |  |  | PO1
CMS | Dev |  | 2026-08-30 |  | RPT_02_Gas Trouble | Siddu |  |  | PO1
CMS | Not Started |  | 2026-08-30 |  | RPT_02_Wall Check Control |  |  |  | PO3
CMS | Not Started |  | 2026-08-30 |  | RPT_02_High Pressure Steel Inside Inspection |  |  |  | PO2
CMS | Not Started |  | 2026-08-30 |  | RPT_02_Large Gas Outage |  |  |  | PO3
CMS | Not Started |  | 2026-08-30 |  | RPT_02_Fitting Work |  |  |  | PO2
CMS | Not Started |  | 2026-08-30 |  | RPT_02_Field Collector Report |  |  |  | PO1
CMS | Not Started |  | 2026-08-30 |  | RPT_02_Turn On for Non-Payment |  |  |  | PO2
CMS | Not Started |  | 2026-08-30 |  | RPT_02_Collector Payment Recap |  |  |  | PO2
CMS | Not Started |  | 2026-08-30 |  | RPT_02_Incentive Management |  |  |  | PO2
CMS | Not Started |  | 2026-09-30 |  | RPT_02_UTC Report |  |  |  | PO1
CMS | Not Started |  | 2026-09-30 |  | RPT_02_Adjacent Property Checks |  |  |  | PO3
CMS | Not Started |  | 2026-09-30 |  | RPT_02_High Bill Investigations |  |  |  | PO2
CMS | Not Started |  | 2026-09-30 |  | RPT_02_Emergency Order Type |  |  |  | PO3
CMS | Not Started |  | 2026-09-30 |  | RPT_02_Cut Out Curb Box |  |  |  | PO3
CMS | Not Started |  | 2026-09-30 |  | RPT_02_New York Incident |  |  |  | PO1
CMS | Not Started |  | 2026-09-30 |  | RPT_02_Outside Repeat Leaks |  |  |  | PO2
CMS | Not Started |  | 2026-09-30 |  | RPT_02_Meter Change |  |  |  | PO3
CMS | Not Started |  | 2026-09-30 |  | RPT_02_Field Order Value |  |  |  | PO2
CMS | Not Started |  | 2026-09-30 |  | RPT_02_Same Day Reconnect |  |  |  | PO2
CMS | Not Started |  | 2026-09-30 |  | RPT_02_Site Specific Analysis |  |  |  | PO2
CMS | Not Started |  | 2026-09-30 |  | RPT_02_PSC Wire Down Response Time |  |  |  | PO3
CMS | Not Started |  | 2026-09-30 |  | RPT_02_Hazardous Above Ground Leak |  |  |  | PO1
CMS | Not Started |  | 2026-09-30 |  | RPT_02_AMI Contractor Completion Report |  |  |  | PO2
CMS | Not Started |  | 2026-09-30 |  | RPT_02_Collection Statistic |  |  |  | PO1
CMS | Not Started |  | 2026-09-30 |  | RPT_02_First and Last Job |  |  |  | PO2
CMS | Not Started |  | 2026-09-30 |  | RPT_02_Rate Class |  |  |  | PO1
CMS | Not Started |  | 2026-09-30 |  | RPT_04_Leak Recheck Times |  |  |  | PO2

## Dim Table
Domain | Expected Report Count | Expected Release Date
Leaks | 8 | 2026-04-30
Leaks | 10 | 2026-05-30
Leaks | 9 | 2026-06-30
CMS | 15 | 2026-07-30
CMS | 15 | 2026-08-30
CMS | 17 | 2026-09-30
CMS | 20 | 2026-10-30
CMS | 20 | 2026-11-30
Maintenance and Construction | 18 | 2026-12-30
Maintenance and Construction | 18 | 2027-01-30
Maintenance and Construction | 19 | 2027-02-28
Meter Management | 9 | 2027-03-30
Assets and Engineering | 8 | 2027-03-30

## Sheet3 (hidden)
In Progress
DEV
PBI
In QA
In UAT
In Production

## Timeline Chart
Reports Migration & Data Product Timelines
Data Product | Count | Apr-26 | May-26 | Jun-26 | Jul-26 | Aug-26 | Sep-26 | Oct-26 | Nov-26 | Dec-26 | Jan-27 | Feb-27 | Mar-27
Leaks (RPT) | 27 | 8 | 10 | 9
CMS (includes Dispatch) (RPT) | 87 |  |  |  | 15 | 15 | 17 | 20 | 20
Maintenance and Construction (RPT) | 55 | [8 empty] | 18 | 18 | 19
Meter Management (RPT) | 9 | [11 empty] | 9
Assets and Engineering (RPT) | 8 | [11 empty] | 8
Total | 186

## Sheet1
Not Started
DEV
QA
DPO Approval
In Production