## Combined Delivery Data
Domain | Report Name | Current Status (Update next stage after completion date) | Status Flag | Business Value Rank | PO | Schema | Plan Delivery Date | Plan Delivery Month | DB Developer | DB Dev Baseline Completion Date | DB Dev Reforecast Completion Date | DB Dev Actual Completion Date | Build Source | Sprint DB | PBI Developer | PBI Dev Baseline Completion Date | PBI Dev Reforecast Completion Date | PBI Dev Actual Completion Date | Sprint PBI | QA Tester | QA Baseline Completion Date | QA Reforecast Completion Date | Initial QA Completion Date | QA Actual Completion Date | Sprint QA | DPO Approval Baseline Completion Date | DPO Approval Reforecast Completion Date | DPO Approval Completion Date | DPO Approval Reviewer | Report Type | Confirmed Deployed? | Confirmed Deployed Date | UAT Report URL | Production URL | Blocked? | Data Check | Comments | QA Rework Due DPO Rework Due | Column1
Leaks | RPT_04_Active Leaks | RELEASED IN PROD | Delivered | 1 |  |  | 2026-04-30 | April | Fetwi | 2026-04-10 |  | 2026-04-03 | Curated |  | Sarath | 2026-04-17 |  | 2026-04-02 |  | Preety | 2026-04-24 |  |  | 2026-04-10 |  | 2026-04-28 |  |  | Kelvin Hu | compliance | Yes | 2026-04-10 | https://app.powerbi.com/groups/me/apps/eedba83d-be9a-45f9-9504-7bfa41e6051a/reports/62307ec4-3158-4457-8dcc-4acc2150cdc3/ccfe9e7f0a40d49acb85?experience=power-bi | https://app.powerbi.com/groups/me/apps/2c7180b1-0d3d-45be-979e-f7dc86b3557d/reports/8cd4a21d-3abe-4e55-a99e-3af846ab1c67/ccfe9e7f0a40d49acb85?ctid=f98a6a53-25f3-4212-901c-c7787fcd3495&experience=power-bi | No | Confirmed Deployed date is before DPO Approval target | [Historical, April 2026]: QA found an issue - date calendar dimension broken. Fetwi assigned to fix.
Leaks | RPT_04_Count of Active Leaks On Hand | RELEASED IN PROD | Delivered | 2 |  |  | 2026-04-30 | April | Fetwi | 2026-04-10 |  | 2026-04-03 | Curated |  | Sarath | 2026-04-17 |  | 2026-04-02 |  | Preety | 2026-04-24 |  |  | 2026-04-10 |  | 2026-04-28 |  |  | Kelvin Hu | compliance | Yes | 2026-04-10 | https://app.powerbi.com/groups/me/apps/eedba83d-be9a-45f9-9504-7bfa41e6051a/reports/c0b3f0ae-dedd-485b-8bbc-aa0e5f3fd077/24a66431d0637282f4b7?experience=power-bi | https://app.powerbi.com/groups/me/apps/2c7180b1-0d3d-45be-979e-f7dc86b3557d/reports/5ffd546f-ad77-4a7f-8e6d-94dc08bef796/24a66431d0637282f4b7?ctid=f98a6a53-25f3-4212-901c-c7787fcd3495&experience=power-bi | No | Confirmed Deployed date is before DPO Approval target | [Historical, April 2026]: QA found an issue - date calendar dimension broken. Fetwi assigned to fix.
Leaks | RPT_04_Leak Days Remaining | RELEASED IN PROD | Delivered | 3 |  |  | 2026-04-30 | April | Siva | 2026-04-10 |  | 2026-04-03 | Curated |  | Navya | 2026-04-17 |  | 2026-04-14 |  | Preety | 2026-04-24 |  |  | 2026-04-10 |  | 2026-04-28 |  |  | Kelvin Hu | compliance | Yes | 2026-04-10 | https://app.powerbi.com/groups/me/apps/eedba83d-be9a-45f9-9504-7bfa41e6051a/reports/8b9ae445-3a30-4ae6-a3fa-7a6d8e7ef349/d97da6159d0c87677529?experience=power-bi | https://app.powerbi.com/groups/me/apps/2c7180b1-0d3d-45be-979e-f7dc86b3557d/reports/848ce65a-4e47-422b-aae5-7ea9e7d68a5f/d97da6159d0c87677529?ctid=f98a6a53-25f3-4212-901c-c7787fcd3495&experience=power-bi | No | Confirmed Deployed date is before DPO Approval target | 16/04 - Testing completed in QA and created defect https://jira.prod.nationalgrid.com/browse/GDMP-2186; ETA -04/24
Leaks | RPT_04_Cleared Leaks | RELEASED IN PROD | Delivered | 4 |  |  | 2026-04-30 | April | Sree | 2026-04-10 |  | 2026-04-03 | Curated |  | Sarath | 2026-04-17 |  | 2026-04-08 |  | Preety | 2026-04-24 |  |  | 2026-04-10 |  | 2026-04-28 |  |  | Kelvin Hu | compliance | Yes | 2026-04-10 | https://app.powerbi.com/groups/me/apps/eedba83d-be9a-45f9-9504-7bfa41e6051a/reports/938a9ba1-8138-440e-842a-d9a679933d8c/44bb4fce98fafb2cace2?experience=power-bi | https://app.powerbi.com/groups/me/apps/2c7180b1-0d3d-45be-979e-f7dc86b3557d/reports/677c6418-6db8-4ebf-9323-65be4cb2c960/ea184ec020032ecbdd43?ctid=f98a6a53-25f3-4212-901c-c7787fcd3495&experience=power-bi | No | Confirmed Deployed date is before DPO Approval target | [Historical, April 2026]: L_GRO_NUMBER columns had an issue in QA - DB team assigned to fix.
Leaks | RPT_04_Leaks Repaired Detail | RELEASED IN PROD | Delivered | 5 |  |  | 2026-04-30 | April |  |  |  |  | Curated | [15 empty] | Kelvin Hu | compliance | Yes | 2026-04-30
Leaks | RPT_04_Leaks Aging | RELEASED IN PROD | Delivered | 6 |  |  | 2026-04-30 | April |  |  |  |  | Curated | [15 empty] | Kelvin Hu | compliance | Yes | 2026-04-30
Leaks | RPT_04_Prior Leak Readings | RELEASED IN PROD | Delivered | 7 |  |  | 2026-04-30 | April |  |  |  |  | Curated | [15 empty] | Kelvin Hu | Ops | Yes | 2026-04-30
Leaks | RSS_04_Leak Grade Change History | RELEASED IN PROD | Delivered | 8 |  |  | 2026-04-30 | April |  |  |  |  | Curated | [15 empty] | Kelvin Hu | Ops | Yes | 2026-04-30
Leaks | RPT_04_Rechecks Completed less than 14 days | RELEASED IN PROD | Delivered | 9 |  |  | 2026-05-31 | May | Rupa | 2026-05-08 |  | 2026-05-15 | Curated |  | Shraddha | 2026-05-15 |  | 2026-04-22 |  | Preety | 2026-05-22 |  |  | 2026-04-22 |  | 2026-05-27 |  |  | Kelvin Hu | Ops | Yes | 2026-04-22 | https://app.powerbi.com/groups/me/apps/7767030c-f4c8-4488-b3cb-36a860cb6ff2/reports/de1ad11f-021b-4cc1-b465-67efd542031c/3122b8024291693794eb?ctid=f98a6a53-25f3-4212-901c-c7787fcd3495&experience=power-bi | https://app.powerbi.com/groups/me/apps/5b29b0dd-a398-4801-84ce-f3a7d8435827/reports/0e063b20-0b38-4000-b436-fcbec11daa46/3122b8024291693794eb?experience=power-bi | No | Confirmed Deployed date is before DPO Approval target
Leaks | RPT_04_SEI Leak Activity | RELEASED IN PROD | Delivered | 10 |  |  | 2026-05-31 | May | Siva | 2026-05-08 |  | 2026-05-15 | Curated |  | Shraddha | 2026-05-15 |  | 2026-04-27 |  | Preety | 2026-05-22 |  |  | 2026-04-27 |  | 2026-05-27 |  |  | Kelvin Hu | Ops | Yes | 2026-04-27 | https://app.powerbi.com/groups/me/apps/7767030c-f4c8-4488-b3cb-36a860cb6ff2/reports/c76693f4-bab2-46a1-ab2a-16752d7664fd/ea184ec020032ecbdd43?experience=power-bi | https://app.powerbi.com/groups/me/apps/5b29b0dd-a398-4801-84ce-f3a7d8435827/reports/9d9f5721-feb1-4ed3-91fd-18bc33ef38f1/ea184ec020032ecbdd43?experience=power-bi | No | Confirmed Deployed date is before DPO Approval target
Leaks | RPT_04_CMS Leak Productivity | RELEASED IN PROD | Delivered | 11 |  |  | 2026-05-31 | May | Siddu | 2026-05-08 |  | 2026-05-15 | Curated |  | Navya | 2026-05-15 |  | 2026-05-05 |  | Preety | 2026-05-22 |  |  | 2026-05-05 |  | 2026-05-27 |  |  | Kelvin Hu | compliance | Yes | 2026-05-05 | https://app.powerbi.com/groups/me/apps/eedba83d-be9a-45f9-9504-7bfa41e6051a/reports/3440832e-c72e-45f2-b154-f6b1d66314fc/51a6cefeab19522827a6?experience=power-bi | https://app.powerbi.com/groups/me/apps/2c7180b1-0d3d-45be-979e-f7dc86b3557d/reports/18e31a06-f1af-4965-ad46-5a507f24ed56/51a6cefeab19522827a6?experience=power-bi | No | Confirmed Deployed date is before DPO Approval target
Leaks | RPT_04_Main Break Corrosion and Leak Cluster | RELEASED IN PROD | Delivered | 12 |  |  | 2026-05-31 | May | Siddu | 2026-05-08 |  | 2026-05-15 | Curated |  | Sarath | 2026-05-15 |  | 2026-06-02 |  | Kelvin | 2026-05-22 |  |  | 2026-06-06 |  | 2026-05-27 |  |  | Kelvin Hu | compliance | Yes | 2026-06-06 | https://app.powerbi.com/groups/me/apps/eedba83d-be9a-45f9-9504-7bfa41e6051a/reports/efc0a204-1a7b-4be6-8334-c7582c9093b8/ReportSection81bc1123208781ca563a?experience=power-bi |  | No
Leaks | RPT_04_Leak Summary Status | RELEASED IN PROD | Delivered | 13 |  |  | 2026-05-31 | May | Fetwi | 2026-05-08 |  | 2026-05-15 | Curated |  | Navya | 2026-05-15 |  | 2026-05-01 |  | Kelvin | 2026-05-22 |  |  | 2026-06-02 |  | 2026-05-27 |  |  | Kelvin Hu | Ops | Yes | 2026-06-11 | https://app.powerbi.com/groups/me/apps/7767030c-f4c8-4488-b3cb-36a860cb6ff2/reports/184a9cdc-83f5-40b0-940d-d901ad9fb404/ReportSection6d915001f68ea4805272?ctid=f98a6a53-25f3-4212-901c-c7787fcd3495&experience=power-bi | https://app.powerbi.com/groups/me/apps/5b29b0dd-a398-4801-84ce-f3a7d8435827/reports/f7af2903-2d63-497e-b262-100f5a3b500b/ReportSection6d915001f68ea4805272?ctid=f98a6a53-25f3-4212-901c-c7787fcd3495&experience=power-bi | No
Leaks | RPT_04_PSC Leak Printout | RELEASED IN PROD | Delivered | 14 |  |  | 2026-05-31 | May | Fetwi | 2026-05-08 |  | 2026-05-15 | Curated |  | Shraddha | 2026-05-15 |  | 2026-06-05 |  | Preety | 2026-05-22 |  |  | 2026-06-02 |  | 2026-05-27 |  |  | Kelvin Hu | Regulatory | Yes | 2026-06-19 | https://app.powerbi.com/groups/me/apps/61b18507-2848-49b9-aacc-32c49ffe1e0b/rdlreports/84ee7713-075e-496c-8610-43022c6a55ab?ctid=f98a6a53-25f3-4212-901c-c7787fcd3495&experience=power-bi |  | No |  | [Historical, May/June 2026]: Fetwi was investigating a slowness issue in this report.
Leaks | RPT_04_Surveillances With Zero Readings | RELEASED IN PROD | Delivered | 15 |  |  | 2026-05-31 | May |  |  |  |  | Curated | [15 empty] | Kelvin Hu | compliance | Yes | 2026-06-30
Leaks | RPT_04 High Emitter leaks | RELEASED IN PROD | Delivered | 16 |  |  | 2026-05-31 | May |  |  |  |  | Curated | [15 empty] | Kelvin Hu | Regulatory | Yes | 2026-06-30
Leaks | RPT_04_School Zone Leaks Without Repair | RELEASED IN PROD | Delivered | 17 |  |  | 2026-05-31 | May |  |  |  |  | Curated | [15 empty] | Kelvin Hu | compliance | Yes | 2026-06-30
Leaks | RPT_04_PSC Quarterly Leak | RELEASED IN PROD | Delivered | 18 |  |  | 2026-05-31 | May |  |  |  |  | Curated | [15 empty] | Kelvin Hu | Regulatory | Yes | 2026-06-30
Leaks | RPT_04_Leak Control Report | RELEASED IN PROD | Delivered | 19 |  |  | 2026-06-30 | June | Geetha | 2026-06-12 |  | 2026-05-06 | Curated |  | Navya | 2026-06-19 |  | 2026-06-10 |  | Preety | 2026-06-26 |  |  | 2026-06-22 |  | 2026-06-29 |  |  | Thuan Nguyen | Ops | Yes | 2026-06-22 |  |  | No | Confirmed Deployed date is before DPO Approval target
Leaks | RPT_04_Leak Life Cycle | RELEASED IN PROD | Delivered | 20 |  |  | 2026-06-30 | June | Geetha | 2026-06-12 |  | 2026-05-20 | Curated |  | Shraddha | 2026-06-19 |  | 2026-06-09 |  | Preety | 2026-06-26 |  |  | 2026-06-25 |  | 2026-06-29 |  |  | Nicole Gordon, Jason Dezotell | Ops | Yes | 2026-06-25 |  |  | No | Confirmed Deployed date is before DPO Approval target | [Historical, June 2026]: Waiting on Kelvin's approval to deploy to UAT.
Leaks | RPT_04_Leak Life Cycle Legacy LMS LI | RELEASED IN PROD | Delivered | 21 |  |  | 2026-06-30 | June | Fetwi | 2026-06-12 |  | 2026-05-26 | Curated |  | Navya | 2026-06-19 |  | 2026-06-10 |  | Preety | 2026-06-26 |  |  | 2026-06-25 |  | 2026-06-29 |  |  |  | Ops | Yes | 2026-06-25 |  |  | No | Confirmed Deployed date is before DPO Approval target
Leaks | RPT_04_Leak Increase Reads | RELEASED IN PROD | Delivered | 22 |  |  | 2026-06-30 | June | Fetwi | 2026-06-12 |  | 2026-05-23 | Curated |  | Navya | 2026-06-19 |  | 2026-05-11 |  | Preety | 2026-06-26 |  |  | 2026-05-12 |  | 2026-06-29 |  |  | Jay Poter | compliance | Yes | 2026-06-11 | https://app.powerbi.com/groups/me/apps/eedba83d-be9a-45f9-9504-7bfa41e6051a/reports/a410b442-fd2f-43d1-a053-40f2e4966d4d/ea184ec020032ecbdd43?ctid=f98a6a53-25f3-4212-901c-c7787fcd3495&experience=power-bi | https://app.powerbi.com/groups/me/apps/2c7180b1-0d3d-45be-979e-f7dc86b3557d/reports/1cec238a-ce10-4ed5-8e56-50efa21bb327/ea184ec020032ecbdd43?ctid=f98a6a53-25f3-4212-901c-c7787fcd3495&experience=power-bi | No | Confirmed Deployed date is before DPO Approval target
Leaks | Leak 360 Dashboard | RELEASED IN PROD | Delivered | 23 |  |  | 2026-06-30 | June | Siva | 2026-06-12 |  | 2026-05-20 | Curated |  | Sarath | 2026-06-19 |  | 2026-06-13 |  | Kelvin | 2026-06-26 |  |  |  |  | 2026-06-29 |  |  | Nicole Gordon, Allie Cama | Ops | Yes | 2026-07-24 |  |  | No |  | [Source confirms QA complete but gives no exact date - using QA Expected date as the closest evidence-backed proxy]
Leaks | RPT_04_Leak Recheck Control | RELEASED IN PROD | Delivered | 24 |  |  | 2026-06-30 | June | Siva | 2026-06-12 |  | 2026-05-20 | Curated |  | Shraddha | 2026-06-19 |  | 2026-05-22 |  | Preety | 2026-06-26 |  |  | 2026-07-01 |  | 2026-06-29 |  |  | Jay Poter | compliance | Yes | 2026-07-01 |  |  | No |  | [Source confirms QA complete but gives no exact date - using QA Expected date as the closest evidence-backed proxy]
Leaks | RPT_04_Main_Replacement Report | RELEASED IN PROD | Delivered | 25 |  |  | 2026-06-30 | June | Sree | 2026-06-12 |  | 2026-05-27 | Curated |  | Navya | 2026-06-19 |  | 2026-06-18 |  | Kelvin | 2026-06-26 |  |  | 2026-06-23 |  | 2026-06-29 |  |  | Corey Manson | compliance | Yes | 2026-06-23 | https://app.powerbi.com/Redirect?action=OpenApp&appId=eedba83d-be9a-45f9-9504-7bfa41e6051a&ctid=f98a6a53-25f3-4212-901c-c7787fcd3495&experience=power-bi | https://app.powerbi.com/groups/me/apps/2c7180b1-0d3d-45be-979e-f7dc86b3557d/reports/3a63d51e-dbb3-4d03-8e38-924376751299/3122b8024291693794eb?ctid=f98a6a53-25f3-4212-901c-c7787fcd3495&experience=power-bi | No | Confirmed Deployed date is before DPO Approval target
Leaks | New Report: Leak Repair Exception | RELEASED IN PROD | Delivered | 26 |  |  | 2026-06-30 | June | Geetha | 2026-06-12 |  | 2026-05-26 | Curated |  | Shraddha | 2026-06-19 |  | 2026-06-16 |  | Kelvin | 2026-06-26 |  |  | 2026-06-16 |  | 2026-06-29 |  |  |  | Ops | Yes | 2026-06-19 | https://app.powerbi.com/groups/me/apps/eedba83d-be9a-45f9-9504-7bfa41e6051a/reports/f32957e8-b826-44b0-8c00-67ff417ed57e/e94cbcb8509576e1c578?ctid=f98a6a53-25f3-4212-901c-c7787fcd3495&experience=power-bi |  | No | Confirmed Deployed date is before DPO Approval target
Leaks | New Report: (Leak reading sample point mismatch ) Creating a new report that... | RELEASED IN PROD | Delivered | 27 |  |  | 2026-06-30 | June | Siddu | 2026-06-12 |  | 2026-05-27 | Curated |  | Shraddha | 2026-06-19 |  | 2026-06-22 |  |  | 2026-06-26 |  |  | 2026-06-24 |  | 2026-06-29 |  |  | Oneil Lashley | Ops | Yes | 2026-06-24 |  |  | No | Confirmed Deployed date is before DPO Approval target | [QA Actual date recovered from source text: "6/24/2026; QA Completed. Waiting for the view to be deployed to UAT"]
CMS | RPT_02_CO Flue Warning Tag Control | Ready for Release in Prod | Blocked - Blocked in Prod | 1 | Kushal |  | 2026-07-31 | July | Rupa | 2026-07-10 | 2026-08-10 | 2026-08-11 | Curated | PI2, S4 | Navya | 2026-07-17 | 2026-08-11 | 2026-08-11 |  | Kushal | 2026-07-24 | 2026-08-14 |  | 2026-08-18 |  | 2026-07-29 | 2026-09-08 | 2026-09-08 | Jeanne Waldron, Anthony Massimino | compliance |  |  |  |  | Yes – Blocked in Prod | Blocked - log it on Rework Log | Blocked with https://jira.prod.nationalgrid.com/browse/GDMP-2875 | 2026-08-14
CMS | RPT_02_Warning Tag HEFPA | Ready for Release in Prod | Blocked - Blocked in Prod | 2 | Kushal |  | 2026-07-31 | July | Sree | 2026-07-10 | 2026-08-10 | 2026-08-21 | Curated | PI2, S4 | Shraddha | 2026-07-17 | 2026-08-11 | 2026-08-12 |  | Kushal | 2026-07-24 | 2026-08-26 |  | 2026-08-21 |  | 2026-07-29 | 2026-09-08 | 2026-09-08 | Jeanne Waldron, Anthony Massimino | compliance |  |  |  |  | Yes – Blocked in Prod | Blocked - log it on Rework Log | Available for Business | 2026-08-26
CMS | RPT_02_Warning tag Printout | Ready for Release in Prod | Blocked - Blocked in Prod | 3 | Kushal |  | 2026-07-31 | July | Sree | 2026-07-10 | 2026-08-11 | 2026-08-12 | Curated | PI2, S4 | Shraddha | 2026-07-17 | 2026-08-12 | 2026-08-17 |  | Kushal | 2026-07-24 | 2026-08-19 |  | 2026-08-24 |  | 2026-07-29 | 2026-09-08 | 2026-09-08 | Jeanne Waldron, Anthony Massimino | compliance |  |  |  |  | Yes – Blocked in Prod | Blocked - log it on Rework Log | Note: this report's stage dates are not in chronological order in the source tracker (e.g. a later stage dated before an earlier one) - please verify with the assigned developer. [QA note, 07/2026]: Development is completed, waiting for the view to be deployed to QA. | 2026-09-07
CMS | RPT_02_Corrosion | Ready for Release in Prod | Blocked - Blocked in Prod | 4 | Kushal |  | 2026-07-31 | July | Siva | 2026-07-10 |  | 2026-09-01 | Curated | PI2, S4 | Sarath | 2026-07-17 | 2026-08-17 | 2026-08-19 |  | Preety | 2026-07-24 | 2026-09-04 |  | 2026-09-04 |  | 2026-07-29 | 2026-09-08 | 2026-09-08 | Jeanne Waldron, Anthony Massimino | compliance |  |  |  |  | Yes – Blocked in Prod | Blocked - log it on Rework Log | 27/8 Ready for Kushal's review | 2026-09-04
CMS | RPT_02_House Pipe Test Comment Control | Ready for Release in Prod | Blocked - Blocked in Prod | 5 | Kushal |  | 2026-07-31 | July | Geetha | 2026-07-10 | 2026-08-12 | 2026-08-17 | Curated | PI2, S4 | Shraddha | 2026-07-17 | 2026-08-12 | 2026-08-10 |  | Preety | 2026-07-24 | 2026-08-20 |  | 2026-08-20 |  | 2026-07-29 | 2026-09-08 | 2026-09-08 | Jeanne Waldron, Anthony Massimino | compliance |  |  |  |  | Yes – Blocked in Prod | Blocked - log it on Rework Log | 08/17/2026 Ready for review | 2026-08-20
CMS | RPT_02_Required Regulator Inspection Performed Control | Ready for Release in Prod | Blocked - Blocked in Prod | 6 | Bardia |  | 2026-07-31 | July | Siddu | 2026-07-10 | 2026-08-12 | 2026-08-18 | Curated | PI2, S4 | Navya | 2026-07-17 | 2026-08-12 | 2026-08-17 |  | Bardia | 2026-07-24 | 2026-08-21 |  | 2026-08-21 |  | 2026-07-29 | 2026-09-08 | 2026-09-08 | Jeanne Waldron, Anthony Massimino | compliance |  |  |  |  | Yes – Blocked in Prod | Blocked - log it on Rework Log | Available for PBI with one known issue will be presenting to business | 2026-08-21
CMS | RPT_02_Service Regulator Inspections | Ready for Release in Prod | Blocked - Blocked in Prod | 7 | Bardia |  | 2026-07-31 | July | Sree | 2026-07-10 | 2026-08-10 | 2026-08-24 | Hybrid | PI2, S4 | Sarath | 2026-07-17 | 2026-08-17 | 2026-09-01 |  | Bardia | 2026-07-24 | 2026-09-04 |  | 2026-09-02 |  | 2026-07-29 | 2026-09-10 | 2026-09-08 | Jeanne Waldron, Anthony Massimino | compliance |  |  |  |  | Yes – Blocked in Prod | Blocked - log it on Rework Log | sent back yesterday | 2026-09-04
CMS | RPT_02_Service Regulator Inspection Printout | Ready for Release in Prod | Blocked - Blocked in Prod | 8 | Bardia |  | 2026-07-31 | July | Sree | 2026-07-10 | 2026-08-11 | 2026-08-24 | Curated | PI2, S4 | Shraddha | 2026-07-17 | 2026-08-12 | 2026-08-12 |  | Bardia | 2026-07-24 | 2026-08-27 |  | 2026-09-02 |  | 2026-07-29 | 2026-09-10 | 2026-09-08 | Jeanne Waldron, Anthony Massimino | compliance |  |  |  |  | Yes – Blocked in Prod | Blocked - log it on Rework Log | sent back yesterday | 2026-08-27
CMS | RPT_02_20 Year Regulator Inspection | Ready for Release in Prod | Blocked - Blocked in Prod | 9 | Bardia |  | 2026-07-31 | July | Siddu | 2026-07-10 | 2026-08-12 | 2026-08-21 | Curated | PI2, S4 | Navya | 2026-07-17 | 2026-08-21 | 2026-08-21 |  | Bardia | 2026-07-24 | 2026-08-26 |  | 2026-08-21 |  | 2026-07-29 | 2026-09-04 | 2026-09-04 | Natalie Lattanzio | compliance |  |  |  |  | Yes – Blocked in Prod | Blocked - log it on Rework Log | Added Customer Details to Mandated tab | 2026-08-26
CMS | RPT_02_Fixed Factor | Ready for Release in Prod | Blocked - Blocked in Prod | 10,12 | Bardia |  | 2026-07-31 | July | Nick | 2026-07-10 | 2026-08-12 | 2026-08-20 | Curated | PI2, S4 | Navya | 2026-07-17 | 2026-08-20 | 2026-08-20 |  | Bardia | 2026-07-24 | 2026-08-25 |  | 2026-08-20 |  | 2026-07-29 | 2026-09-04 | 2026-09-04 | Natalie Lattanzio | compliance |  |  |  |  | Yes – Blocked in Prod | Blocked - log it on Rework Log |  | 2026-08-25
CMS | RPT_02_Fixed Factor Printout | Ready for Release in Prod | Blocked - Blocked in Prod | 11 | Bardia |  | 2026-07-31 | July | Nick | 2026-07-10 | 2026-08-12 | 2026-08-11 | Curated | PI2, S4 | Shraddha | 2026-07-17 | 2026-08-13 | 2026-08-24 |  | Preety | 2026-07-24 | 2026-08-27 |  | 2026-08-24 |  | 2026-07-29 | 2026-09-04 | 2026-09-04 | Natalie Lattanzio | compliance |  |  |  |  | Yes – Blocked in Prod | Blocked - log it on Rework Log | sent back yesterday | 2026-09-07
CMS | RPT_02_Work Order Completion Printout | Ready for Release in Prod | Blocked - Blocked in Prod | 13 | Kushal |  | 2026-07-31 | July | Rupa | 2026-07-10 | 2026-08-17 | 2026-08-17 | Curated | PI2, S4 | Shraddha | 2026-07-17 | 2026-08-17 | 2026-08-21 |  | Preety | 2026-07-24 | 2026-08-20 |  | 2026-08-24 |  | 2026-07-29 | 2026-09-08 | 2026-09-08 | Jeanne Waldron, Anthony Massimino | compliance |  |  |  |  | Yes – Blocked in Prod | Blocked - log it on Rework Log | Unblocked and Dev completed after requirements confirmation from Kushal | 2026-09-07
CMS | RPT_02_GRO Control | Ready for Release in Prod | Blocked - Blocked in Prod | 14 | Kushal |  | 2026-07-31 | July | Siva | 2026-07-10 | 2026-08-14 | 2026-08-14 | Curated | PI2, S4 | Navya | 2026-07-17 | 2026-08-17 | 2026-08-17 |  | Preety | 2026-07-24 | 2026-08-24 |  | 2026-08-24 |  | 2026-07-29 | 2026-09-08 | 2026-09-08 | Jeanne Waldron, Anthony Massimino | compliance |  |  |  |  | Yes – Blocked in Prod | Blocked - log it on Rework Log | QA note ; 8/21/2026 : Ready for review
CMS | RPT_02_GRO Monitor | Ready for Release in Prod | Blocked - Blocked in Prod | 15 | Bardia |  | 2026-07-31 | July | Rupa | 2026-07-10 | 2026-08-11 | 2026-08-11 | Curated | PI2, S3 | Sarath | 2026-07-17 | 2026-08-14 | 2026-08-14 |  | Preety | 2026-07-24 | 2026-08-21 |  | 2026-08-27 |  | 2026-07-29 | 2026-09-04 | 2026-09-04 | Natalie Lattanzio | compliance |  |  |  |  | Yes – Blocked in Prod | Blocked - log it on Rework Log | Ready for review
CMS | RPT_02_Public Buildings Inspection | Ready for Release in Prod | Blocked - Blocked in Prod | 16,17,24, 28 | Bardia |  | 2026-08-31 | August | Geetha | 2026-07-31 | 2026-08-17 | 2026-08-18 | Hybrid | PI2, S2, S4 | Navya | 2026-08-07 | 2026-09-29 | 2026-09-30 |  | Preety | 2026-08-21 | 2026-10-01 | 2026-09-09 | 2026-10-01 |  | 2026-08-26 | 2026-10-01 | 2026-10-01 | Jeanne Waldron, Anthony Massimino | compliance |  |  |  |  | Yes – Blocked in Prod | Blocked - log it on Rework Log | Blocked with https://jira.prod.nationalgrid.com/browse/GDMP-2546 | 2026-09-14 | 2026-10-09
CMS | RPT_02_Investigate Wall Check and Service Check | Ready for Release in Prod | Blocked - needs DPO Approval to fix | 18 | Bardia |  | 2026-08-31 | August | Siva | 2026-07-31 | 2026-08-21 | 2026-08-21 | Curated | PI2, S2, S4 | Sarath | 2026-08-07 | 2026-08-24 | 2026-08-24 |  | Preety | 2026-08-21 | 2026-09-09 | 2026-09-03 | 2026-09-08 |  | 2026-08-26 | 2026-09-18 | 2026-09-18 | Shaunna Peters | compliance |  |  |  |  | Yes – needs DPO Approval to fix | Blocked - log it on Rework Log | Ready for review deploy PBI report to QA for testing -,Deployed to QA on 0825 | 2026-09-08
CMS | RPT_02_Cut Out Orders | Ready for Release in Prod | Blocked - Blocked in Prod | 19 | Kushal |  | 2026-08-31 | August | Fetwi | 2026-07-31 | 2026-08-15 | 2026-08-10 |  | PI2, S2, S4 | Shraddha | 2026-08-07 | 2026-08-18 | 2026-08-31 |  | Preety | 2026-08-21 | 2026-09-03 |  | 2026-08-31 |  | 2026-08-26 | 2026-09-18 | 2026-09-18 | Shaunna Peters | compliance |  |  |  |  | Yes – Blocked in Prod | Blocked - log it on Rework Log | Ready for Kushal's review | 2026-09-03
CMS | RPT_02_Gas Trouble | Ready for Release in Prod | Blocked - Blocked in Prod | 20 | Kushal |  | 2026-08-31 | August | Siddu | 2026-07-31 | 2026-07-10 | 2026-08-10 |  | PI2, S2, S3 | Navya | 2026-08-07 | 2026-08-27 | 2026-08-27 |  | Preety | 2026-08-21 | 2026-09-04 |  | 2026-09-01 |  | 2026-08-26 | 2026-09-17 | 2026-09-18 | Jeanne Waldron, Anthony Massimino | compliance |  |  |  |  | Yes – Blocked in Prod | Blocked - log it on Rework Log | Ready for Kushal's review | 2026-09-04
CMS | RPT_02_Wall Check Control | Ready for Release in Prod | Blocked - Blocked in Prod | 21 | Kushal |  | 2026-08-31 | August | Nick | 2026-07-31 | 2026-08-12 | 2026-08-12 | Curated | PI2, S3, S4 | Shraddha | 2026-08-07 | 2026-08-27 | 2026-08-27 |  | Kushal | 2026-08-21 | 2026-08-31 |  | 2026-08-31 |  | 2026-08-26 | 2026-09-17 | 2026-09-18 | Jeanne Waldron, Anthony Massimino | compliance |  |  |  |  | Yes – Blocked in Prod | Blocked - log it on Rework Log | Ready for Kushal's review
CMS | RPT_02_High Pressure Steel Inside Inspection | Ready for Release in Prod | Blocked - Blocked in Prod | 22 | Bardia |  | 2026-08-31 | August | Geetha | 2026-07-31 | 2026-08-21 | 2026-08-19 | Curated | PI2, S3, S4 | Sarath | 2026-08-07 | 2026-08-21 | 2026-08-21 |  | Bardia | 2026-08-21 | 2026-09-04 |  | 2026-09-04 |  | 2026-08-26 | 2026-09-18 | 2026-09-18 | Shaunna Peters | compliance |  |  |  |  | Yes – Blocked in Prod | Blocked - log it on Rework Log | Ready for Bardia's Review
CMS | RPT_02_Large Gas Outage | Ready for Release in Prod | Blocked - Blocked in Prod | 23 | Kushal |  | 2026-08-31 | August | Nick | 2026-07-31 | 2026-08-19 | 2026-08-31 | Curated | PI2, S4 | Sarath | 2026-08-07 | 2026-08-25 | 2026-09-01 |  | Kushal | 2026-08-21 | 2026-09-16 |  | 2026-09-21 |  | 2026-08-26 | 2026-09-30 | 2026-10-07 | Brooke Allen | Ops |  |  |  |  | Yes – Blocked in Prod | Blocked - log it on Rework Log |  | 2026-09-22
CMS | RPT_02_Fitting Work | Ready for Release in Prod | Blocked - Blocked in Prod | 25 | Bardia |  | 2026-08-31 | August | Fetwi | 2026-07-31 | 2026-08-15 | 2026-08-11 | Hybrid | PI2, S3, S4 | Navya | 2026-08-07 | 2026-08-18 | 2026-08-18 |  | Bardia | 2026-08-21 | 2026-09-09 |  | 2026-09-08 |  | 2026-08-26 | 2026-09-18 | 2026-09-18 | Shaunna Peters | Ops |  |  |  |  | Yes – Blocked in Prod | Blocked - log it on Rework Log |  | 2026-09-08
CMS | RPT_02_Field Collector Report | Ready for Release in Prod | Blocked - Blocked in Prod | 26 | Bardia |  | 2026-08-31 | August | Rupa | 2026-07-31 | 2026-08-14 | 2026-08-14 | Curated | PI2, S3, S4 | Shraddha | 2026-08-07 | 2026-08-21 | 2026-08-26 |  | Bardia | 2026-08-21 | 2026-09-11 |  | 2026-09-11 |  | 2026-08-26 | 2026-09-18 | 2026-09-18 | Jeanne Timmons, Shaunna Peters | Ops |  |  |  |  | Yes – Blocked in Prod | Blocked - log it on Rework Log | Ready for Bardia's Review
CMS | RPT_02_Turn On for Non-Payment | DPO Approval | Overdue | 27 | Kushal |  | 2026-08-31 | August | Sree | 2026-07-31 | 2026-08-19 | 2026-08-18 | Hybrid | PI2, S3, S4 | Sarath | 2026-08-07 | 2026-09-01 | 2026-09-02 |  | Kushal | 2026-09-28 | 2026-09-04 |  | 2026-09-25 |  | 2026-08-26 | 2026-10-02 |  | Bryan Patterson, Reginald Durham, Shaunna Peters, Simone Brooks, Bill Contreras | Ops |  |  |  |  | No | Open rework row - mark Blocked or close it | Sarath's Comments 08/31:Waiting for DB View to deploy to QA 09/01: Ready for QA testing. | 2026-09-28
CMS | RPT_02_Collector Payment Recap | Ready for Release in Prod | Blocked - Blocked in Prod | 29 | Bardia |  | 2026-08-31 | August | Rupa | 2026-07-31 | 2026-08-17 | 2026-08-17 | Hybrid | PI2, S4 | Shraddha | 2026-08-07 | 2026-08-31 | 2026-08-28 |  | Bardia | 2026-08-21 | 2026-09-16 |  | 2026-09-16 |  | 2026-08-26 | 2026-09-30 | 2026-09-21 | Oneil Lashley | Ops |  |  |  |  | Yes – Blocked in Prod | Blocked - log it on Rework Log |  | 2026-09-21
CMS | RPT_02_Incentive Management | Ready for Release in Prod | Blocked - Blocked in Prod | 30 | Kushal |  | 2026-08-31 | August | Siddu | 2026-07-31 | 2026-08-21 | 2026-08-19 |  | PI2, S4 | Navya | 2026-08-07 | 2026-08-28 | 2026-08-28 |  | Preety | 2026-08-21 | 2026-09-02 | 2026-09-04 | 2026-09-04 |  | 2026-08-26 | 2026-09-17 | 2026-09-17 | Reginald Durham | Ops |  |  |  |  | Yes – Blocked in Prod | Blocked - log it on Rework Log
CMS | RPT_02_UTC Report | DPO Approval | Overdue | 31 | Bardia |  | 2026-09-30 | September | Rupa | 2026-08-28 | 2026-08-19 | 2026-08-19 |  | PI2, S5 | Shraddha | 2026-09-04 | 2026-09-02 | 2026-09-30 | PI2,S6 | Preety | 2026-09-02 | 2026-10-05 | 2026-09-28 |  |  | 2026-09-25 | 2026-10-14 |  | Simone Brooks | compliance |  |  |  |  | No |  | 9/11 : Ready for review | 2026-09-15
CMS | RPT_02_Adjacent Property Checks | DPO Approval | Blocked by PBI Issue | 32 | Kushal |  | 2026-09-30 | September | Rupa | 2026-08-28 | 2026-08-19 | 2026-08-19 | Hybrid | PI2, S5 | Navya | 2026-09-04 | 2026-09-01 | 2026-09-01 | PI2,S6 | Olu | 2026-09-11 | 2026-09-20 | 2026-09-09 | 2026-09-23 |  | 2026-09-25 | 2026-10-02 |  | Anthony Massimino | compliance |  |  |  |  | Yes – needs DPO Approval to fix | Blocked - log it on Rework Log | Ready For PBI
CMS | RPT_02_High Bill Investigations | Ready for Release in Prod | Blocked - Blocked in Prod | 33 | Bardia |  | 2026-09-30 | September | Sree | 2026-08-28 | 2026-08-20 |  | Hybrid | PI2, S5 | Sarath | 2026-09-04 | 2026-09-03 | 2026-09-03 | PI2,S6 | Preety | 2026-09-11 | 2026-09-17 | 2026-09-10 | 2026-09-17 |  | 2026-09-25 | 2026-09-21 | 2026-09-21 | Oneil Lashley | compliance |  |  |  |  | Yes – Blocked in Prod | Blocked - log it on Rework Log | Ready for review
CMS | RPT_02_Emergency Order Type | QA | Overdue | 34 | Kushal |  | 2026-09-30 | September | Sree | 2026-08-28 | 2026-08-20 | 2026-10-03 | Hybrid | PI2, S5 | Shraddha | 2026-09-04 | 2026-09-07 | 2026-10-06 | PI2,S6 | Kushal | 2026-09-11 |  |  |  |  | 2026-09-25 |  |  | Jeanne Waldron, Anthony Massimino | compliance |  |  |  |  | No | Move status back to PBI Dev | Need Kushal's help to get sharepoint file access. --- Update DB dev moved the hierachy logic to snowflake view on 10/03
CMS | RPT_02_Cut Out Curb Box | RELEASED IN PROD | Blocked - Blocked in Prod | 35 | olu |  | 2026-09-30 | September | Fetwi | 2026-08-28 | 2026-08-19 | 2026-08-19 |  | PI2, S5 | Navya | 2026-09-04 | 2026-09-01 | 2026-09-01 | PI2,S6 | Preety | 2026-09-11 | 2026-09-24 | 2026-09-23 | 2026-09-25 |  | 2026-09-25 | 2026-10-02 | 2026-10-06 | Oneil Lashley | compliance | Yes | 2026-10-09 |  |  | Yes – Blocked in Prod | Blocked - log it on Rework Log | Ready for review | 2026-09-23
CMS | RPT_02_New York Incident | RELEASED IN PROD | Delivered | 36 | olu |  | 2026-09-30 | September | Nick | 2026-08-28 | 2026-08-21 | 2026-08-21 | Hybrid | PI2, S5 | Sarath | 2026-09-04 | 2026-09-08 | 2026-09-08 | PI2,S6 | Preety | 2026-09-11 | 2026-09-22 |  | 2026-09-21 |  | 2026-09-25 | 2026-10-01 | 2026-09-30 | Bryan Patterson, Reginald Durham, Bill Contreras | Ops | Yes | 2026-10-02 |  |  | No |  | Ready for review | 2026-09-22
CMS | RPT_02_Outside Repeat Leaks | DPO Approval | On track | 37 | Kushal |  | 2026-09-30 | September | Fetwi | 2026-08-28 | 2026-08-21 | 2026-08-21 |  | PI2, S5 | Navya | 2026-09-04 | 2026-09-03 | 2026-09-03 | PI2,S6 | Preety | 2026-09-11 | 2026-10-01 | 2026-09-16 | 2026-09-30 |  | 2026-09-25 | 2026-10-23 |  | Reginald Durham, Simone Brooks, Bill Contreras | Ops |  |  |  |  | No |  | Ready for review
CMS | RPT_02_Meter Change | DPO Approval | Blocked - needs DPO Approval to fix | 38 | olu |  | 2026-09-30 | September | Siddu | 2026-08-28 | 2026-08-26 | 2026-08-25 |  | PI2, S5 | Shraddha | 2026-09-04 | 2026-09-15 | 2026-09-17 | PI2,S6 | Olu | 2026-09-11 | 2026-09-23 | 2026-09-18 | 2026-09-24 |  | 2026-09-25 | 2026-10-19 |  | Michelle Fitten | Ops |  |  |  |  | Yes – needs DPO Approval to fix | Blocked - log it on Rework Log
CMS | RPT_02_Field Order Value | DPO Approval | On track | 39 | olu |  | 2026-09-30 | September | Siddu | 2026-09-11 | 2026-09-11 | 2026-09-01 |  | PI2, S5 | Navya | 2026-09-21 | 2026-09-10 | 2026-09-29 | PI2,S6 | Preety | 2026-09-25 | 2026-10-05 | 2026-09-30 | 2026-10-05 |  | 2026-09-30 | 2026-10-20 |  | Alex Giangolini | Ops |  |  |  |  | No |  | Ready for review | 2026-10-08
CMS | RPT_02_Same Day Reconnect | QA | Overdue | 40 | Kushal |  | 2026-09-30 | September | Geetha | 2026-09-11 | 2026-08-31 | 2026-09-01 | Hybrid | PI2, S5 | Navya | 2026-09-21 | 2026-09-04 | 2026-09-04 | PI2,S6 | Preety | 2026-09-25 |  | 2026-09-30 |  |  | 2026-09-30 |  |  | Bryan Patterson | Ops |  |  |  |  | No |  | Ready for Kushal's review
CMS | RPT_02_Site Specific Analysis | DPO Approval | On track | 41 | Kushal |  | 2026-09-30 | September | Nick | 2026-09-11 | 2026-08-28 | 2026-08-31 | Curated | PI2, S5 | Shraddha | 2026-09-21 | 2026-09-08 | 2026-09-08 | PI2,S6 | Olu | 2026-09-25 |  | 2026-09-15 | 2026-09-23 |  | 2026-09-30 | 2026-10-16 |  | Jeanne Waldron, Anthony Massimino | compliance |  |  |  |  | No
CMS | RPT_02_PSC Wire Down Response Time | PBI Dev | Overdue | 42 | Kushal |  | 2026-09-30 | September | Fetwi | 2026-09-11 | 2026-09-11 | 2026-09-17 |  | PI2, S5 | Sarath | 2026-09-21 | 2026-09-08 |  | PI2,S6 |  | 2026-09-25 |  |  |  |  | 2026-09-30 |  |  | Bryan Patterson | Regulatory |  |  |  |  | No
CMS | RPT_02_Hazardous Above Ground Leak | DPO Approval | On track | 43 | Kushal |  | 2026-09-30 | September | Fetwi | 2026-09-11 | 2026-08-20 | 2026-08-20 |  | PI2, S5 | Navya | 2026-09-21 | 2026-08-20 | 2026-08-20 | PI2,S6 | Kushal | 2026-09-25 | 2026-10-01 |  |  |  | 2026-09-30 | 2026-09-03 |  | Reginald Durham, Simone Brooks, Shaunna Peters, Bill Contreras | Regulatory |  |  |  |  | No | This is in QA | I don't see any mismatch on this. Please review it again. I attached the evidence to the JIRA
CMS | RPT_02_AMI Contractor Completion Report | PBI Dev | Overdue | 44 | Kushal |  | 2026-09-30 | September | Michael | 2026-09-11 | 2026-08-24 | 2026-08-24 |  | PI2, S5 | Shraddha | 2026-09-21 |  |  | PI2,SIP |  | 2026-09-25 |  |  |  |  | 2026-09-30 |  |  | Meredith Dube | Ops |  |  |  |  | No |  | 08/26: Report not required per Bardia
CMS | RPT_02_Collection Statistic | NOT STARTED | Review - planned start passed | 45 | olu |  | 2026-09-30 | September | Siva | 2026-09-11 |  |  |  | PI2, S5 | Sarath | 2026-09-21 |  |  | PI2,SIP |  | 2026-09-25 |  |  |  |  | 2026-09-30 |  |  | Brett Palmeri | Ops |  |  |  |  | No |  | 08/26: Out of scope per Bardia.
CMS | RPT_02_First and Last Job | QA | Overdue | 46 | olu |  | 2026-09-30 | September | Sree | 2026-09-11 | 2026-08-28 | 2026-09-11 | Hybrid | PI2, S5 | Shraddha | 2026-09-21 | 2026-09-18 | 2026-10-08 | PI2,SIP |  | 2026-09-25 |  |  |  |  | 2026-09-30 |  |  | Oneil Lashley | Ops |  |  |  |  | No |  | Update DB dev: moved the hierachy logic to snowflake view on 10/03
CMS | RPT_02_Rate Class | Ready for Release in Prod | Blocked - Blocked in Prod | 47 | olu |  | 2026-09-30 | September | Fetwi | 2026-09-11 | 2026-08-25 | 2026-08-25 |  | PI2, S5 | Navya | 2026-09-21 | 2026-09-16 | 2026-09-16 | PI2,SIP | Preety | 2026-09-25 | 2026-10-01 |  | 2026-09-28 |  | 2026-09-30 | 2026-10-09 | 2026-10-02 | Zishan Momin | Regulatory |  |  |  |  | Yes – Blocked in Prod | Blocked - log it on Rework Log | Missing SF WO in the view
CMS | RPT_04_Leak Recheck Times | DPO Approval | Overdue | 48 | Kushal |  | 2026-09-30 | September | Rupa | 2026-09-11 | 2026-08-24 | 2026-08-24 | Curated | PI2, S5 | Shraddha | 2026-09-21 | 2026-09-11 | 2026-09-11 | PI2,SIP | Preety | 2026-09-25 | 2026-10-01 | 2026-09-15 | 2026-10-06 |  | 2026-09-30 | 2026-10-14 |  | Shaunna Peters | compliance |  |  |  |  | No
CMS | RPT_02_Service Resource Activity | DPO Approval | Overdue | 49 | olu |  | 2026-10-30 | October | Rupa | 2026-10-09 | 2026-08-25 | 2026-08-25 | Curated | PI2, S5 | Shraddha | 2026-10-18 | 2026-09-24 | 2026-09-24 | PI3,S1 | Preety | 2026-10-21 |  | 2026-10-01 | 2026-10-03 |  | 2026-10-30 | 2026-10-13 |  | Simone Brooks | Ops | [6 empty] | Ready for Olu's review
CMS | RPT_02_Incomplete Service Appointments | QA | On track | 50 | olu |  | 2026-10-30 | October | Michael | 2026-10-09 | 2026-09-04 | 2026-09-04 |  | PI2, S5 | Shraddha | 2026-10-18 | 2026-10-05 | 2026-10-08 | PI3,S1 | Preety | 2026-10-21 |  |  |  |  | 2026-10-30 |  |  | Shaunna Peters | Regulatory
CMS | RPT_02_Emergency Response Time Review Report | NOT STARTED | On track | 51 |  |  | 2026-10-30 | October | Siva | 2026-10-09 |  |  |  | PI2, S5 |  | 2026-10-18 |  |  | PI3,S1 |  | 2026-10-21 |  |  |  |  | 2026-10-30 |  |  | Christina Illingworth | Regulatory
CMS | RPT_02_Personal Injury and Shock Investigation | NOT STARTED | On track | 52 |  |  | 2026-10-30 | October | Siva | 2026-10-09 |  |  |  | PI2, S5 |  | 2026-10-18 |  |  | PI3,S1 |  | 2026-10-21 |  |  |  |  | 2026-10-30 |  |  | Christina Illingworth | Regulatory
CMS | RPT_02_Emergency Response Statistics | NOT STARTED | On track | 53 |  |  | 2026-10-30 | October | Nick | 2026-10-09 |  |  |  | PI2, S5 |  | 2026-10-18 |  |  | PI3,S1 |  | 2026-10-21 |  |  |  |  | 2026-10-30 |  |  | Christina Illingworth | Regulatory
CMS | RPT_02_Emergency Time Adjustments Log | PBI Dev | Blocked - needs DB Dev to fix | 54 | Kushal |  | 2026-10-30 | October | Fetwi | 2026-10-09 | 2026-09-01 | 2026-09-01 |  | PI2, S6 | Navya | 2026-10-18 | 2026-10-07 |  | PI3,S1 |  | 2026-10-21 | 2026-10-01 |  |  |  | 2026-10-30 |  |  | Bryan Patterson, Reginald Durham, Shaunna Peters, Simone Brooks, Bill Contreras | Regulatory |  |  |  |  | Yes – needs DB Dev to fix | Blocked - log it on Rework Log | view to be reworked
CMS | RPT_02_PSC Soft Off Report | PBI Dev | Overdue | 55 | Kushal |  | 2026-10-31 | October | Rupa | 2026-10-09 | 2026-09-01 | 2026-09-01 | Raw | PI2, S5 | Navya | 2026-10-18 | 2026-10-02 |  | PI3,S1 |  | 2026-10-21 |  |  |  |  | 2026-10-30 |  |  | Angela Keegan | Regulatory | [6 empty] | As we have CSS dev data in GDM QA, Unit testing wouldn't be possible for all columns
CMS | RPT_02_Service Interruptions | QA | On track | 56 | Kushal |  | 2026-10-30 | October | Geetha | 2026-10-09 | 2026-09-11 | 2026-09-15 | Curated | PI2, S6 | Navya | 2026-10-18 | 2026-10-07 |  | PI3,S1 | Preety | 2026-10-21 |  | 2026-10-14 |  |  | 2026-10-30 |  |  | Bryan Patterson, Reginald Durham, Bill Contreras | Regulatory |  |  |  |  | No |  | Ready for Kushal's review
CMS | RPT_02_Duty to Inspect | QA | On track | 57 | Kushal |  | 2026-10-30 | October | Geetha | 2026-10-09 | 2026-09-22 | 2026-09-22 | Raw | PI2, S6 | Navya | 2026-10-18 | 2026-09-30 | 2026-09-29 | PI3,S1 | Preety | 2026-10-21 |  | 2026-10-06 |  |  | 2026-10-30 |  |  | Bryan Patterson | Regulatory | [6 empty] | Ready for Kushal's review
CMS | RPT_02_Service Appointment Life Cycle | DB Dev | On track | 58 | Kushal |  | 2026-10-30 | October | Nick | 2026-10-09 | 2026-09-16 | 2026-09-18 | Hybrid | PI2, S6 | Shraddha | 2026-10-18 | 2026-10-09 |  | PI3,S2 | Preety | 2026-10-21 |  |  |  |  | 2026-10-30 |  |  | Megan Piccarreto | Regulatory | [5 empty] | Move status to PBI Dev
CMS | RPT_02_PSC Inactive Account | QA | On track | 59 | Kushal |  | 2026-10-30 | October | Rupa | 2026-10-09 | 2026-09-03 | 2026-09-03 | Raw | PI2, S6 | Shraddha | 2026-10-18 | 2026-09-29 | 2026-09-29 | PI3,S1 | Preety | 2026-10-21 |  | 2026-10-08 |  |  | 2026-10-30 |  |  | Reginald Durham, Simone Brooks | Regulatory | [6 empty] | Ready for Kushal's review
CMS | RPT_02_Service Resource Performance | PBI Dev | Overdue | 60 | olu |  | 2026-10-30 | October | Rupa | 2026-10-09 | 2026-09-21 | 2026-09-21 | Raw | PI2, S6 | Navya | 2026-10-18 | 2026-10-07 |  | PI3,S1 |  | 2026-10-21 |  |  |  |  | 2026-10-30 |  |  | Oneil Lashley | Ops
CMS | RPT_02_Emergency Leak Response Metric (6 sub reports) | QA | On track | 61, 62, 63, 64, 65, 66 | olu |  | 2026-10-30 | October | Fetwi | 2026-10-09 | 2026-09-11 | 2026-09-21 | Raw | PI2, S6 | Navya | 2026-10-18 |  |  | PI3,S2 |  | 2026-10-21 |  |  |  |  | 2026-10-30 |  |  | Bryan Patterson, Reginald Durham, Shaunna Peters, Simone Brooks, Bill Contreras | Regulatory
CMS | RPT_02_Fixed Factor Mismatch | NOT STARTED | On track | 67 | olu |  | 2026-11-30 | November | Siddu | 2026-11-06 | 2026-11-06 | 2026-09-25 |  | PI2, S6 | Navya | 2026-11-13 |  |  | PI3,S2 |  | 2026-11-18 |  |  |  |  | 2026-11-30 |  |  | Matthew Menicucci | compliance | [5 empty] | Move status to PBI Dev | GDM_RPT.VW_FIXED_FACTOR_MISMATCH and GDM_RPT.VW_FIXED_FACTOR_MISMATCH_NL
CMS | RPT_02_Light Up Orders | NOT STARTED | On track | 68 | olu |  | 2026-11-30 | November | Siva | 2026-11-06 |  |  |  | PI2, S6 | Navya | 2026-11-13 |  |  | PI3,S2 |  | 2026-11-18 |  |  |  |  | 2026-11-30 |  |  | Shaunna Peters | compliance
CMS | RPT_02_Meter To Billing Report | NOT STARTED | On track | 69 | olu |  | 2026-11-30 | November | Siva | 2026-11-06 |  |  |  | PI2, S6 | Shraddha | 2026-11-13 |  |  | PI3,S3 |  | 2026-11-18 |  |  |  |  | 2026-11-30 |  |  | Shaunna Peters | Ops
CMS | RPT_02_Install Meter Orders | NOT STARTED | On track | 70 | olu |  | 2026-11-30 | November | Michael | 2026-11-06 | 2026-09-17 | 2026-09-17 |  | PI2, S6 | Shraddha | 2026-11-13 |  |  | PI3,S3 |  | 2026-11-18 |  |  |  |  | 2026-11-30 |  |  | Shaunna Peters | Ops | [5 empty] | Move status to PBI Dev
CMS | RPT_02_Non Emergency Orders | NOT STARTED | On track | 71 | olu |  | 2026-11-30 | November | Michael | 2026-11-06 | 2026-10-08 | 2026-10-08 |  | PI3, S1 | Navya | 2026-11-13 |  |  | PI3,S3 |  | 2026-11-18 |  |  |  |  | 2026-11-30 |  |  | Shaunna Peters | Ops | [5 empty] | Move status to PBI Dev
CMS | RPT_02_Carbon Monoxide | NOT STARTED | On track | 72 | Kushal |  | 2026-11-30 | November | Sree | 2026-11-06 | 2026-09-08 | 2026-09-08 | Hybrid | PI2, S6 | Navya | 2026-11-13 |  |  | PI3,S3 |  | 2026-11-18 |  |  |  |  | 2026-11-30 |  |  | Bryan Patterson, Reginald Durham, Simone Brooks, Bill Contreras | Ops | [5 empty] | Move status to PBI Dev
CMS | RPT_02_All Jobs | NOT STARTED | On track | 73 | olu |  | 2026-11-30 | November | Siddu | 2026-11-06 | 2026-11-06 | 2026-09-10 |  | PI2, S6 | Shraddha | 2026-11-13 |  |  | PI3,S3 |  | 2026-11-18 |  |  |  |  | 2026-11-30 |  |  | Shaunna Peters | Ops | [5 empty] | Move status to PBI Dev | VW_All_Jobs
CMS | RPT_02_BCP Service Appointment WOs | PBI Dev | On track | 74 | Kushal |  | 2026-11-30 | November | Nick | 2026-11-06 | 2026-10-08 | 2026-10-13 | Hybrid | PI3, S1 | Navya | 2026-11-13 |  |  | PI3,S3 |  | 2026-11-18 |  |  |  |  | 2026-11-30 |  |  | Reginald Durham, Bill Contreras | Regulatory
CMS | RPT_02_Meter Order Tracking | PBI Dev | On track | 80 | olu |  | 2026-11-30 | November | Nick | 2026-11-06 | 2026-10-06 | 2026-10-06 | Hybrid | PI3, S1 | Shraddha | 2026-11-13 |  |  | PI3,S3 |  | 2026-11-18 |  |  |  |  | 2026-11-30 |  |  | Oneil Lashley | Ops
CMS | RPT_02_Tech Availability, Utilization & Absence | DB Dev | On track | 81 | olu |  | 2026-11-30 | November | Rupa | 2026-11-06 |  |  |  | PI3, S1 | Shraddha | 2026-11-13 |  |  | PI3,S4 |  | 2026-11-18 |  |  |  |  | 2026-11-30 |  |  | Reginald Durham, Bill Contreras, Bill Contreras | Ops
CMS | RPT_02_Job Productivity | PBI Dev | On track | 82 | Kushal |  | 2026-11-30 | November | Rupa | 2026-11-06 | 2026-10-02 |  | Raw | PI3, S1 | Navya | 2026-11-13 |  |  | PI3,S4 |  | 2026-11-18 |  |  |  |  | 2026-11-30 |  |  | Laura Capasso, Michelle Fitten, Anthony Jenson | Ops
CMS | RPT_02_Post Capacity Service Appointments | DB Dev | On track | 83 | Kushal |  | 2026-11-30 | November | Greeta | 2026-11-06 | 2026-11-06 |  |  | PI3, S1 | Shraddha | 2026-11-13 |  |  | PI3,S4 |  | 2026-11-18 |  |  |  |  | 2026-11-30 |  |  | Ryan Flaherty | Ops
CMS | RPT_02_Check Estimate | PBI Dev | On track | 84 | olu |  | 2026-11-30 | November | Greeta | 2026-11-06 | 2026-11-06 | 2026-10-01 | Hybrid | PI3, S1 | Navya | 2026-11-13 |  |  | PI3,S4 |  | 2026-11-18 |  |  |  |  | 2026-11-30 |  |  | Shaunna Peters | compliance
CMS | RPT_02_Service Appointments (5 sub reports) | DB Dev | Overdue | 75,76,77,78,79 | Kushal |  | 2026-11-30 | November | Sree | 2026-11-06 | 2026-10-07 |  | Hybrid | PI2, S6 | Navya | 2026-11-13 |  |  | PI3,S4 |  | 2026-11-18 |  |  |  |  | 2026-11-30 |  |  | Reginald Durham, Bill Contreras, Megan Piccarreto, Bryan Patterson, Bill Contreras | Regulatory
CMS | RPT_02_Job Unit Count | NOT STARTED | On track | 85 | Kushal |  | 2026-11-30 | November | Siddu | 2026-11-06 | 2026-11-06 | 2026-10-02 |  | PI3, S1 | Shraddha | 2026-11-13 |  |  | PI3,S4 |  | 2026-11-18 |  |  |  |  | 2026-11-30 |  |  | Laura Capasso, Michelle Fitten | Ops | [5 empty] | Move status to PBI Dev
Assets and Engineering | RPT_05_Department of Transportation | DB Dev | On track | 1 | Kushal |  | 2026-12-31 | December | Siva | 2026-12-07 |  |  |  | PI3, S1 |  | 2026-12-14 |  |  | PI3,S4 |  | 2026-12-17 |  |  |  |  | 2026-12-30 |  |  | Christie DeWolff, Kevin Peters | Regulatory
Assets and Engineering | RPT_05_ Inside Meter Relocation | PBI Dev | On track | 2 | Kushal |  | 2026-12-31 | December | Fetwi | 2026-12-07 |  |  |  | PI3, S1 |  | 2026-12-14 |  |  | PI3,S5 |  | 2026-12-17 |  |  |  |  | 2026-12-30 |  |  | Matthew Pitta | Regulatory
Assets and Engineering | RPT_05_Mapped Work Order Information | PBI Dev | On track | 3 | Kushal |  | 2026-12-31 | December | Fetwi | 2026-12-07 |  |  |  | PI3, S1 |  | 2026-12-14 |  |  | PI3,S5 |  | 2026-12-17 |  |  |  |  | 2026-12-30 |  |  | Carla Scibelli | Regulatory
Meter Management | RPT_06_Retired Meters | NOT STARTED | On track | 4 | Bardia |  | 2026-12-31 | December | Siddu | 2026-12-07 | 2026-10-09 | 2026-10-07 |  | PI3, S1 |  | 2026-12-14 |  |  | PI3,S5 |  | 2026-12-17 |  |  |  |  | 2026-12-30 |  |  | Shawn Oliveira | compliance | [5 empty] | Move status to PBI Dev
Assets and Engineering | RPT_13_Survey Book | PBI Dev | On track | 5 | Kushal |  | 2026-12-31 | December | Siddu | 2026-12-07 | 2026-12-07 | 2026-10-15 |  | PI3, S2 |  | 2026-12-14 |  |  | PI3,S5 |  | 2026-12-17 |  |  |  |  | 2026-12-30 |  |  | Michelle Roche | Ops
Assets and Engineering | RPT_05_Leak Survey Mains Summary | PBI Dev | On track | 6 | Kushal |  | 2026-12-31 | December | Siddu | 2026-12-07 | 2026-12-07 | 2026-10-12 |  | PI3, S2 |  | 2026-12-14 |  |  | PI3,S5 |  | 2026-12-17 |  |  |  |  | 2026-12-30 |  |  | John Kashmanian | Ops
Assets and Engineering | RPT_13_Customer Service Point | PBI Dev | On track | 7 | Kushal |  | 2026-12-31 | December | Siddu | 2026-12-07 | 2026-12-07 | 2026-10-13 |  | PI3, S2 |  | 2026-12-14 |  |  | PI3,S5 |  | 2026-12-17 |  |  |  |  | 2026-12-30 |  |  | Kevin Peters, Sadaat Khan | Ops
Assets and Engineering | RPT_02_Emergency Operation Checklist | DB Dev | On track | 8 | Kushal |  | 2026-12-31 | December | Greeta | 2026-12-07 |  |  |  | PI3, S2 |  | 2026-12-14 |  |  | PI3,S5 |  | 2026-12-17 |  |  |  |  | 2026-12-30 |  |  | Omesh Kamat, Michelle Roche, Ed Graziano | Ops
Meter Management | RPT_06_ERT List | PBI Dev | On track | 9 | Bardia |  | 2026-12-31 | December | Nick | 2026-12-07 | 2026-10-20 | 2026-10-15 | Raw | PI3, S2 |  | 2026-12-14 |  |  | PI3,S6 |  | 2026-12-17 |  |  |  |  | 2026-12-30 |  |  | Austin Whitney | Ops
Assets and Engineering | RPT_13_Blue Card | PBI Dev | On track | 10 | Kushal |  | 2026-12-31 | December | Nick | 2026-12-07 | 2026-10-15 | 2026-10-13 | Raw | PI3, S2 |  | 2026-12-14 |  |  | PI3,S6 |  | 2026-12-17 |  |  |  |  | 2026-12-30 |  |  | Nikki Shattuck | Ops
Meter Management | RPT_06_Out of Route Meters Gas | NOT STARTED | On track | 11 | Bardia |  | 2026-12-31 | December | Rupa | 2026-12-07 |  |  |  | PI3, S2 |  | 2026-12-14 |  |  | PI3,S6 |  | 2026-12-17 |  |  |  |  | 2026-12-30 |  |  | Bryan Smiley | Ops
Meter Management | RPT_06_Yard Meter Inventory | NOT STARTED | On track | 12 | Bardia |  | 2026-12-31 | December | Michael | 2026-12-07 |  |  |  | PI3, S2 |  | 2026-12-14 |  |  | PI3,S6 |  | 2026-12-17 |  |  |  |  | 2026-12-30 |  |  | Austin Whitney | Ops
Meter Management | RPT_06_ERTtoEPSLoadReportbyReceiptNumber | DB Dev | On track | 13 | Bardia |  | 2026-12-31 | December | Nick | 2026-12-07 | 2026-10-23 |  |  | PI3, S2 |  | 2026-12-14 |  |  | PI3,S6 |  | 2026-12-17 |  |  |  |  | 2026-12-30 |  |  | Austin Whitney | Ops
Meter Management | RPT_06_Out of Route Meters Electric | NOT STARTED | On track | 14 | Bardia |  | 2026-12-31 | December | Siddu | 2026-12-07 |  |  |  | PI3, S2 |  | 2026-12-14 |  |  | PI3,S6 |  | 2026-12-17 |  |  |  |  | 2026-12-30 |  |  | Bryan Smiley | Ops
Meter Management | RPT_06_Installed Meters | NOT STARTED | On track | 15 | Bardia |  | 2026-12-31 | December |  | 2026-12-07 |  |  |  | PI3, S5 |  | 2026-12-14 |  |  | PI3,S6 |  | 2026-12-17 |  |  |  |  | 2026-12-30 |  |  | Matthew Menicucci | Ops
Maintenance and Construction | RPT_05_Gateboxes | NOT STARTED |  | 1 | Bardia |  | 2027-01-31 | January |  | 2026-12-31 | [5 empty] | 2027-01-15 |  |  |  |  | 2027-01-10 | [13 empty] | Yes – Blocked in Prod
Maintenance and Construction | RPT_05_Kedny Compliance | NOT STARTED |  | 2 | Bardia |  | 2027-01-31 | January |  | 2026-12-31 | [5 empty] | 2027-01-15 |  |  |  |  | 2027-01-10
Maintenance and Construction | RPT_05_CI Encroachment | NOT STARTED |  | 3 | Bardia |  | 2027-01-31 | January |  | 2026-12-31 | [5 empty] | 2027-01-15 |  |  |  |  | 2027-01-10
Maintenance and Construction | RPT_05_Design Processing | NOT STARTED |  | 4 | Bardia |  | 2027-01-31 | January |  | 2026-12-31 | [5 empty] | 2027-01-15 |  |  |  |  | 2027-01-10
Note on C1: Required Step: Once your completion date is filled out, immediately update this Current Status column to the next dev receiving stage.

## Find a Report (hidden)
Find a Report
Pick a report below - everything updates automatically.
Report Name:
Domain
Current Status
Status Flag
Business Value Rank
PO
DB Developer
PBI Developer
QA Tester
DB Dev Expected
DB Dev Actual
PBI Dev Expected
PBI Dev Actual
QA Expected
QA Actual
DPO Approval Expected
DPO Approval Reviewer
Confirmed Deployed?
Confirmed Deployed Date
Blocked?
Data Check
Times Sent Back
Open Reworks
Last Sent Back Date
Last From -> To
Comments

## Rework Log
Report Name | Date Sent Back | From Stage | To Stage | Sent Back By | What Was Wrong | Resolved? | Fix Sent To | Expected Fix Date | Date Fixed | Fixed By | What Was Fixed | Aging | Notified | Report Name | Times Sent Back | Open Reworks | Last Sent Back Date | Last From -> To
RPT_02_Required Regulator Inspection Performed Control | 2026-07-27 | QA | DB Dev | Bardia | the count does not match(count of records between ods and gdm | Yes | Siddu |  | 2026-08-13 |  |  | Fixed | Yes | RPT_04_Active Leaks | 0 | 0
RPT_02_Fixed Factor | 2026-08-03 | QA | DB Dev | Bardia | count and value mismatch | Yes | Nick |  | 2026-08-13 | Navya | Mismatched in assigned technician value | Fixed | Yes | RPT_04_Count of Active Leaks On Hand | 0 | 0
RPT_02_CO Flue Warning Tag Control | 2026-08-04 | QA | DB Dev | Kushal | Count mismatch | Yes | Rupa |  | 2026-08-11 |  |  | Fixed | Yes | #REF! | #REF! | #REF! | #REF! | #REF!
RPT_02_House Pipe Test Comment Control | 2026-07-31 | QA | DB Dev | Kushal | SF/MX Comments field mismatch | Yes | Geetha |  | 2026-08-17 |  |  | Fixed | Yes | RPT_04_Leak Days Remaining | 0 | 0
RPT_02_Warning Tag HEFPA | 2026-08-05 | QA | DB Dev | Kushal | SF/MX Comments and Lettering Status Mismatch | Yes | Sree |  | 2026-08-17 |  |  | Fixed | Yes | RPT_04_Cleared Leaks | 0 | 0
RPT_02_Warning Tag HEFPA | 2026-08-12 | QA | DB Dev | Kushal | Equipments missing | Yes | Sree |  | 2026-08-17 |  |  | Fixed | yes | RPT_04_Rechecks Completed less than 14 days | 0 | 0
RPT_02_Fixed Factor | 2026-08-17 | QA | DB Dev | Bardia | Average biometric value rounding up | Yes | Nick |  | 2026-08-20 |  |  | Fixed | yes | RPT_04_SEI Leak Activity | 0 | 0
RPT_02_Required Regulator Inspection Performed Control | 2026-08-03 | QA | DB Dev | Bardia | count and value mismatch | Yes | Siddu |  | 2026-08-18 |  |  | Fixed | yes | RPT_04_CMS Leak Productivity | 0 | 0
RPT_02_Warning Tag HEFPA | 2026-08-20 | QA | DB Dev | Kushal | Count mismatch | Yes | Sree |  | 2026-08-21 |  |  | Fixed | Yes | RPT_04_Main Break Corrosion and Leak Cluster | 0 | 0
RPT_02_20 Year Regulator Inspection | 2026-08-20 | QA | DB Dev | Bardia | Customer Contact Detail column missing in Mandated tab | Yes | Siddu |  | 2026-08-21 |  |  | Fixed | Yes | RPT_04_Leak Summary Status | 0 | 0
RPT_02_Corrosion | 2026-08-24 | QA | DB Dev | Kushal | Count mismatch in Summary | Yes | Siva |  | 2026-08-24 |  |  | Fixed | Yes | RPT_04_PSC Leak Printout | 0 | 0
RPT_02_Service Regulator Inspections | 2026-08-24 | QA | PBI Dev | Bardia | Count mismatch. SPIPE# is incorrect | Yes | Sarath |  | 2026-08-24 |  |  | Fixed | Yes | RPT_04_Leak Control Report | 0 | 0
RPT_02_Fixed Factor Printout | 2026-08-24 | QA | PBI Dev | Bardia | Protection Seal In Place column is having mismatches | Yes | Shraddha |  | 2026-08-24 |  |  | Fixed | Yes | RPT_04_Leak Life Cycle | 0 | 0
RPT_02_Service Regulator Inspection Printout | 2026-08-24 | QA | DB Dev | Bardia | MX WO# 18224253 is not showing up in the printout | Yes | Sree |  | 2026-08-24 |  |  | Fixed | Yes | RPT_04_Rechecks Completed less than 14 days | 0 | 0
RPT_02_Service Regulator Inspections | 2026-08-26 | QA | PBI Dev | Bardia | Column mismatch and Column orders | Yes | Sarath
RPT_02_Large Gas Outage | 2026-08-27 | QA | DB Dev | Kushal | Count Mismatch for both Turn on and Turn Off | Yes | Nick |  | 2026-08-27 | Nick |  | Fixed | Yes | RPT_04_CMS Leak Productivity | 0 | 0
RPT_02_Service Regulator Inspections | 2026-08-28 | QA | PBI Dev | Bardia | Count mismatch for Elevated Pressure tab | Yes | Sarath |  | 2026-09-01 |  |  | Fixed | yes | RPT_04_Main Break Corrosion and Leak Cluster | 0 | 0
RPT_02_Cut Out Orders | 2026-08-31 | QA | PBI Dev | Preety | Data last refresh showing incorrect for older data in the report | Yes | Shraddha | 2026-08-31 | 2026-08-31 | Shraddha | Data refresh Date is showing correct date for older data | Fixed | Yes | RPT_04_Leak Summary Status | 0 | 0
RPT_02_Gas Trouble | 2026-08-31 | QA | DB Dev | Preety | Count mismatch between ODS and GDm | Yes | Siddu | 2026-09-01 | 2026-09-01 |  | All issues are fixed | Fixed | Yes | RPT_04_PSC Leak Printout | 0 | 0
RPT_02_Corrosion | 2026-08-31 | QA | DB Dev | Kushal | ASsigned Tech difference | Yes | Siva |  | 2026-09-01 | Siva |  | Fixed | Yes | RPT_04_Leak Life Cycle | 0 | 0
RPT_02_Investigate Wall Check and Service Check | 2026-09-01 | QA | PBI Dev | Preety | Count mismatch between ODS and GDM | Yes | Sarath | 2026-09-02 | 2026-09-03 | Sarath | All issues are fixed | Fixed | Yes | RPT_04_Leak Life Cycle Legacy LMS LI | 0 | 0
RPT_02_Investigate Wall Check and Service Check | 2026-09-01 | QA | PBI Dev | Preety | Mismatches found in LEAK_FOUND in GDM reports when compared to ODS | Yes | Sarath | 2026-09-02 | 2026-09-03 | Sarath | All issues are fixed | Fixed | Yes | RPT_04_Leak Increase Reads | 0 | 0
RPT_02_Investigate Wall Check and Service Check | 2026-09-02 | QA | PBI Dev | Preety | Count of records displaying for No Wall check Performed is incorrect , it’s not matching with the export. Count of records displaying for No Service check Performed is incorrect , it’s not matching with the export. | Yes | Sarath | 2026-09-02 | 2026-09-03 | Sarath | All issues are fixed | Fixed | Yes | Leak 360 Dashboard | 0 | 0
RPT_02_Turn On for Non-Payment | 2026-09-02 | QA | PBI Dev | Kushal | PBI Source and formatting broken | Yes | Sarath |  |  |  |  | UNCLAIMED 44 d | Yes | RPT_04_Leak Recheck Control | 0 | 0
RPT_02_Large Gas Outage | 2026-09-02 | QA | DB Dev | Kushal | Count Mismatch for both Turn on and Turn Off | Yes | Nick |  | 2026-09-02 | Nick |  | Fixed | Yes | RPT_04_Main_Replacement Report | 0 | 0
RPT_02_Fixed Factor Printout | 2026-09-02 | QA | PBI Dev | Bardia | Report not working for DPO | Yes | Shraddha |  | 2026-09-02 | Shraddha | Access was given to the Semantic Model | Fixed | Yes | New Report: Leak Repair Exception | 0 | 0
RPT_02_Warning tag Printout | 2026-09-02 | QA | PBI Dev | Kushal | Report not working for DPO | Yes | Shraddha |  | 2026-09-02 | Shraddha | Access was given to the Semantic Model | Fixed | Yes | New Report: (Leak reading sample point mismatch ) Creating a new report that... | 0 | 0
RPT_02_Work Order Completion Printout | 2026-09-02 | QA | PBI Dev | Kushal | Report not working for DPO | Yes | Shraddha |  | 2026-09-02 | Shraddha | Access was given to the Semantic Model | Fixed | Yes | RPT_02_CO Flue Warning Tag Control | 1 | 0 | 2026-08-04 | QA -> DB Dev
RPT_02_Large Gas Outage | 2026-09-02 | QA | DB Dev | Kushal | Mismatch for County, phone number, name and phone extension | Yes | Nick |  | 2026-09-02 | Nick |  | Fixed | Yes | RPT_02_Warning Tag HEFPA | 3 | 0 | 2026-08-20 | QA -> DB Dev
RPT_02_Public Buildings Inspection | 2026-09-03 | QA | DB Dev | Preety | Count mismatch , Mismatch in PM description | Yes | Geetha | 2026-09-04 | 2026-09-04 |  | All issues are fixed | Fixed | Yes | RPT_02_Warning tag Printout | 1 | 0 | 2026-09-02 | QA -> PBI Dev
RPT_02_Fitting Work | 2026-09-02 | QA | DB Dev | Olu | Value mismatch | Yes | Fetwi |  | 2026-09-03 |  |  | Fixed | Yes | RPT_02_Corrosion | 2 | 0 | 2026-08-31 | QA -> DB Dev
RPT_02_Public Buildings Inspection | 2026-09-08 | QA | DB Dev | Preety | Mandated Report is experiencing data refresh issue,. Last refresh date is showing the current date. | Yes | Geetha | 2026-09-09 | 2026-09-09 |  | All issues are fixed | Fixed | Yes | RPT_02_House Pipe Test Comment Control | 1 | 0 | 2026-07-31 | QA -> DB Dev
RPT_02_UTC Report | 2026-09-09 | QA | PBI Dev | Preety | Drill through details functionality is not available in Overview report (Graph and data). Getting error to the user if accidently clicked the link present in Radio button. While clicking on any record in the detail record , total record count changing. Back button (navigation) in the report is not working. Logo and text are not clearly visible in the report , it’s incomplete. Total record count mismatch between backend view and report (GDM QA). | Yes | Shraddha | 2026-09-10 | 2026-09-10 | Shraddha | All the issues are fixed | Fixed | Yes | RPT_02_Required Regulator Inspection Performed Control | 2 | 0 | 2026-08-03 | QA -> DB Dev
RPT_02_Large Gas Outage | 2026-09-10 | QA | DB Dev | Kushal | Primary Phone Number not matching | Yes | Nick |  | 2026-09-11 | Nick |  | Fixed | Yes | RPT_02_Service Regulator Inspection Printout | 1 | 0 | 2026-08-24 | QA -> DB Dev
RPT_02_Turn On for Non-Payment | 2026-09-10 | QA | DB Dev | Kushal | Response time is extracting as hashtags in certain cases | No | Sree |  | 2026-09-23 |  |  | Fixed | Yes | RPT_02_20 Year Regulator Inspection | 1 | 0 | 2026-08-20 | QA -> DB Dev
RPT_02_Large Gas Outage | 2026-09-14 | QA | DB Dev | Kushal | The Billing account Email is not matching between the systems | Yes | Nick | 2026-09-17 | 2026-09-17 | Nick | Do nothing on DDL. Data match between ODS and GDM | Fixed | Yes | RPT_02_Fixed Factor | 2 | 0 | 2026-08-17 | QA -> DB Dev
RPT_02_Collector Payment Recap | 2026-09-14 | QA | PBI Dev | Bardia | Performance Issue. Data mismatch. Format Mismatch | Yes | Shraddha | 2026-09-16 | 2026-09-16 | Shraddha | Format changes | Fixed | Yes | RPT_02_Fixed Factor Printout | 2 | 0 | 2026-09-02 | QA -> PBI Dev
RPT_02_Cut Out Curb Box | 2026-09-15 | QA | DB Dev | Preety | Performance issue | Yes | Fetwi | 2026-09-18 | 2026-09-18 |  | Performance | Fixed | Yes | RPT_02_Work Order Completion Printout | 1 | 0 | 2026-09-02 | QA -> PBI Dev
RPT_02_High Bill Investigations | 2026-09-16 | QA | PBI Dev | Olu | Report not rendering | Yes | Sarath |  |  |  |  | UNCLAIMED 30 d |  | RPT_02_GRO Control | 0 | 0
RPT_02_New York Incident | 2026-09-17 | QA | DB Dev | Preety | Count mismatch issue | Yes | Nick | 2026-09-17 | 2026-09-17 |  | Do nothing on DDL. All match when query on 2026-09-17 | Fixed |  | RPT_02_GRO Monitor | 0 | 0
RPT_02_Outside Repeat Leaks | 2026-09-22 | QA | DB Dev | Kushal | Count mismatch issue. postal code and Service Territory mismatch as well | Yes | Fetwi |  |  |  |  | UNCLAIMED 24 d | Yes | RPT_02_Public Buildings Inspection | 3 | 0 | 2026-09-23 | DPO Approval -> PBI Dev
RPT_02_Public Buildings Inspection | 2026-09-23 | DPO Approval | PBI Dev | Bardia | DPO nees the paginated version or the visual with title to see the report name after exporting to Excel | Yes | Navya | 2026-09-29 | 2026-09-30 | Navya | Created Paginated report | Fixed | Yes | RPT_02_Investigate Wall Check and Service Check | 3 | 0 | 2026-09-02 | QA -> PBI Dev
RPT_02_Hazardous Above Ground Leak | 2026-09-30 | QA | DB Dev | Kushal | Count Mismatch | No | Fetwi |  |  |  |  | UNCLAIMED 16 d | Yes | RPT_02_Cut Out Orders | 1 | 0 | 2026-08-31 | QA -> PBI Dev
RPT_02_Field Order Value | 2026-10-02 | QA | DB Dev | Olu | Data mismatch for VA and NVA column | Yes | Siddu |  | 2026-10-05 | Siddu |  | Fixed | Yes
RPT_02_Emergency Order Type | 2026-10-14 | QA | PBI Dev | Kushal | Data mismatch for summary page between ods vs gdm | No | Shraddha |  |  |  |  | UNCLAIMED 2 d | Yes | RPT_02_Wall Check Control | 0 | 0
|  | QA |  |  |  | No | [7 empty] | RPT_02_High Pressure Steel Inside Inspection | 0 | 0
|  | QA |  |  |  | No | [7 empty] | RPT_02_Large Gas Outage | 5 | 0 | 2026-09-14 | QA -> DB Dev
|  | QA |  |  |  | No | [7 empty] | RPT_02_Fitting Work | 1 | 0 | 2026-09-02 | QA -> DB Dev
|  | QA |  |  |  | No | [7 empty] | RPT_02_Field Collector Report | 0 | 0
|  | QA |  |  |  | No | [7 empty] | RPT_02_Turn On for Non-Payment | 2 | 1 | 2026-09-10 | QA -> DB Dev
|  | QA |  |  |  | No | [7 empty] | RPT_02_Collector Payment Recap | 1 | 0 | 2026-09-14 | QA -> PBI Dev
|  | QA |  |  |  | No | [7 empty] | RPT_02_Incentive Management | 0 | 0
|  | QA |  |  |  | No | [7 empty] | RPT_02_UTC Report | 1 | 0 | 2026-09-09 | QA -> PBI Dev
|  | QA |  |  |  | No | [7 empty] | RPT_02_Adjacent Property Checks | 0 | 0
|  | QA |  |  |  | No | [7 empty] | RPT_02_High Bill Investigations | 1 | 0 | 2026-09-16 | QA -> PBI Dev
|  | QA |  |  |  | No | [7 empty] | RPT_02_Emergency Order Type | 1 | 1 | 2026-10-14 | QA -> PBI Dev
|  | QA |  |  |  | No | [7 empty] | RPT_02_Cut Out Curb Box | 1 | 0 | 2026-09-15 | QA -> DB Dev
|  | QA |  |  |  | No | [7 empty] | RPT_02_New York Incident | 1 | 0 | 2026-09-17 | QA -> DB Dev
|  | QA |  |  |  | No | [7 empty] | RPT_02_Outside Repeat Leaks | 1 | 0 | 2026-09-22 | QA -> DB Dev
|  | QA |  |  |  | No | [7 empty] | RPT_02_Meter Change | 0 | 0
|  | QA |  |  |  | No | [7 empty] | RPT_02_Field Order Value | 1 | 0 | 2026-10-02 | QA -> DB Dev
|  | QA |  |  |  | No | [7 empty] | RPT_02_Same Day Reconnect | 0 | 0
|  | QA |  |  |  | No | [7 empty] | RPT_02_Site Specific Analysis | 0 | 0
|  | QA |  |  |  | No | [7 empty] | RPT_02_PSC Wire Down Response Time | 0 | 0
|  | QA |  |  |  | No | [7 empty] | RPT_02_Hazardous Above Ground Leak | 1 | 1 | 2026-09-30 | QA -> DB Dev
|  | QA |  |  |  | No | [7 empty] | RPT_02_AMI Contractor Completion Report | 0 | 0
|  | QA |  |  |  | No | [7 empty] | RPT_02_Collection Statistic | 0 | 0
|  | QA |  |  |  | No | [7 empty] | RPT_02_First and Last Job | 0 | 0
|  | QA |  |  |  | No | [7 empty] | RPT_02_Rate Class | 0 | 0
|  | QA |  |  |  | No | [7 empty] | RPT_04_Leak Recheck Times | 0 | 0
|  | QA |  |  |  | No | [7 empty] | RPT_02_Service Resource Activity | 0 | 0
|  | QA |  |  |  | No | [7 empty] | RPT_05_Department of Transportation | 0 | 0
|  | QA |  |  |  | No | [7 empty] | RPT_05_ Inside Meter Relocation | 0 | 0
|  | QA |  |  |  | No | [7 empty] | RPT_05_Mapped Work Order Information | 0 | 0
|  | QA |  |  |  | No | [7 empty] | RPT_06_Retired Meters | 0 | 0
|  | QA |  |  |  | No | [7 empty] | RPT_13_Survey Book | 0 | 0
|  | QA |  |  |  | No | [7 empty] | RPT_05_Leak Survey Mains Summary | 0 | 0
|  | QA |  |  |  | No | [7 empty] | RPT_13_Customer Service Point | 0 | 0
|  | QA |  |  |  | No | [7 empty] | RPT_02_Emergency Operation Checklist | 0 | 0
|  | QA |  |  |  | No | [7 empty] | RPT_06_ERT List | 0 | 0
|  | QA |  |  |  | No | [7 empty] | RPT_13_Blue Card | 0 | 0
|  | QA |  |  |  | No | [7 empty] | RPT_06_Out of Route Meters Gas | 0 | 0
|  | QA |  |  |  | No | [7 empty] | RPT_06_Yard Meter Inventory | 0 | 0
|  | QA |  |  |  | No | [7 empty] | RPT_06_ERTtoEPSLoadReportbyReceiptNumber | 0 | 0
|  | QA |  |  |  | No | [7 empty] | RPT_06_Out of Route Meters Electric | 0 | 0
|  | QA |  |  |  | No | [7 empty] | RPT_06_Installed Meters | 0 | 0
|  | QA |  |  |  | No | [7 empty] | RPT_05_Kedny Compliance | 0 | 0
|  | QA |  |  |  | No | [7 empty] | RPT_05_CI Encroachment | 0 | 0
|  | QA |  |  |  | No | [7 empty] | RPT_05_Design Processing | 0 | 0
|  | QA |  |  |  | No | [7 empty] | 0 | 0 | 451 | 0 | ->
|  | QA |  |  |  | No | [7 empty] | 0 | 0 | 451 | 0 | ->
|  | QA |  |  |  | No | [7 empty] | 0 | 0 | 451 | 0 | ->
|  | QA |  |  |  | No | [7 empty] | 0 | 0 | 451 | 0 | ->
|  | QA |  |  |  | No | [7 empty] | 0 | 0 | 451 | 0 | ->
|  | QA |  |  |  | No | [7 empty] | 0 | 0 | 451 | 0 | ->
|  | QA |  |  |  | No | [7 empty] | 0 | 0 | 451 | 0 | ->
|  | QA |  |  |  | No | [7 empty] | 0 | 0 | 451 | 0 | ->
|  | QA |  |  |  | No | [7 empty] | 0 | 0 | 451 | 0 | ->
|  | QA |  |  |  | No | [7 empty] | 0 | 0 | 451 | 0 | ->
|  | QA |  |  |  | No | [7 empty] | 0 | 0 | 451 | 0 | ->
|  | QA |  |  |  | No | [7 empty] | 0 | 0 | 451 | 0 | ->
|  | QA |  |  |  | No | [7 empty] | 0 | 0 | 451 | 0 | ->
|  | QA |  |  |  | No | [7 empty] | 0 | 0 | 451 | 0 | ->
|  | QA |  |  |  | No | [7 empty] | 0 | 0 | 451 | 0 | ->
|  | QA |  |  |  | No | [7 empty] | 0 | 0 | 451 | 0 | ->
|  | QA |  |  |  | No | [7 empty] | 0 | 0 | 451 | 0 | ->
|  | QA |  |  |  | No | [7 empty] | 0 | 0 | 451 | 0 | ->
|  | QA |  |  |  | No | [7 empty] | 0 | 0 | 451 | 0 | ->
|  | QA |  |  |  | No | [7 empty] | 0 | 0 | 451 | 0 | ->
|  | QA |  |  |  | No | [7 empty] | 0 | 0 | 451 | 0 | ->
|  | QA |  |  |  | No | [7 empty] | 0 | 0 | 451 | 0 | ->
|  | QA |  |  |  | No | [7 empty] | 0 | 0 | 451 | 0 | ->
|  | QA |  |  |  | No | [7 empty] | 0 | 0 | 451 | 0 | ->
|  | QA |  |  |  | No | [7 empty] | 0 | 0 | 451 | 0 | ->
|  | QA |  |  |  | No | [7 empty] | 0 | 0 | 451 | 0 | ->
|  | QA |  |  |  | No | [7 empty] | 0 | 0 | 451 | 0 | ->
|  | QA |  |  |  | No | [7 empty] | 0 | 0 | 451 | 0 | ->
|  | QA |  |  |  | No | [7 empty] | 0 | 0 | 451 | 0 | ->
|  | QA |  |  |  | No | [7 empty] | 0 | 0 | 451 | 0 | ->
|  | QA |  |  |  | No | [7 empty] | 0 | 0 | 451 | 0 | ->
|  | QA |  |  |  | No | [7 empty] | 0 | 0 | 451 | 0 | ->
|  | QA |  |  |  | No | [7 empty] | 0 | 0 | 451 | 0 | ->
|  | QA |  |  |  | No | [7 empty] | 0 | 0 | 451 | 0 | ->
|  | QA |  |  |  | No | [7 empty] | 0 | 0 | 451 | 0 | ->
|  | QA |  |  |  | No | [7 empty] | 0 | 0 | 451 | 0 | ->
|  | QA |  |  |  | No | [7 empty] | 0 | 0 | 451 | 0 | ->
|  | QA |  |  |  | No | [7 empty] | 0 | 0 | 451 | 0 | ->
|  | QA |  |  |  | No | [7 empty] | 0 | 0 | 451 | 0 | ->
|  | QA |  |  |  | No | [7 empty] | 0 | 0 | 451 | 0 | ->
|  | QA |  |  |  | No | [7 empty] | 0 | 0 | 451 | 0 | ->
|  | QA |  |  |  | No | [7 empty] | 0 | 0 | 451 | 0 | ->
|  | QA |  |  |  | No | [7 empty] | 0 | 0 | 451 | 0 | ->
|  | QA |  |  |  | No | [7 empty] | 0 | 0 | 451 | 0 | ->
|  | QA |  |  |  | No | [7 empty] | 0 | 0 | 451 | 0 | ->
|  | QA |  |  |  | No | [7 empty] | 0 | 0 | 451 | 0 | ->
|  | QA |  |  |  | No | [7 empty] | 0 | 0 | 451 | 0 | ->
|  | QA |  |  |  | No | [7 empty] | 0 | 0 | 451 | 0 | ->
|  | QA |  |  |  | No | [7 empty] | 0 | 0 | 451 | 0 | ->
|  | QA |  |  |  | No | [7 empty] | 0 | 0 | 451 | 0 | ->
|  | QA |  |  |  | No | [7 empty] | 0 | 0 | 451 | 0 | ->
|  | QA |  |  |  | No | [7 empty] | 0 | 0 | 451 | 0 | ->
|  | QA |  |  |  | No | [7 empty] | 0 | 0 | 451 | 0 | ->
|  | QA |  |  |  | No | [7 empty] | 0 | 0 | 451 | 0 | ->
|  | QA |  |  |  | No | [7 empty] | 0 | 0 | 451 | 0 | ->
|  | QA |  |  |  | No | [7 empty] | 0 | 0 | 451 | 0 | ->
|  | QA |  |  |  | No | [7 empty] | 0 | 0 | 451 | 0 | ->
|  | QA |  |  |  | No | [7 empty] | 0 | 0 | 451 | 0 | ->
|  | QA |  |  |  | No | [7 empty] | 0 | 0 | 451 | 0 | ->
|  | QA |  |  |  | No | [7 empty] | 0 | 0 | 451 | 0 | ->
|  | QA |  |  |  | No | [7 empty] | 0 | 0 | 451 | 0 | ->
|  | QA |  |  |  | No | [7 empty] | 0 | 0 | 451 | 0 | ->
|  | QA |  |  |  | No | [7 empty] | 0 | 0 | 451 | 0 | ->
|  | QA |  |  |  | No | [7 empty] | 0 | 0 | 451 | 0 | ->
|  | QA |  |  |  | No | [7 empty] | 0 | 0 | 451 | 0 | ->
|  | QA |  |  |  | No | [7 empty] | 0 | 0 | 451 | 0 | ->
|  | QA |  |  |  | No | [7 empty] | 0 | 0 | 451 | 0 | ->
|  | QA |  |  |  | No | [7 empty] | 0 | 0 | 451 | 0 | ->
|  | QA |  |  |  | No | [7 empty] | 0 | 0 | 451 | 0 | ->
|  | QA |  |  |  | No | [7 empty] | 0 | 0 | 451 | 0 | ->
|  | QA |  |  |  | No | [7 empty] | 0 | 0 | 451 | 0 | ->
|  | QA |  |  |  | No | [7 empty] | 0 | 0 | 451 | 0 | ->
|  | QA |  |  |  | No | [7 empty] | 0 | 0 | 451 | 0 | ->
|  | QA |  |  |  | No | [7 empty] | 0 | 0 | 451 | 0 | ->
|  | QA |  |  |  | No | [7 empty] | 0 | 0 | 451 | 0 | ->
|  | QA |  |  |  | No | [7 empty] | 0 | 0 | 451 | 0 | ->
|  | QA |  |  |  | No | [7 empty] | 0 | 0 | 451 | 0 | ->
|  | QA |  |  |  | No | [7 empty] | 0 | 0 | 451 | 0 | ->
|  | QA |  |  |  | No | [7 empty] | 0 | 0 | 451 | 0 | ->
|  | QA |  |  |  | No | [7 empty] | 0 | 0 | 451 | 0 | ->
|  | QA |  |  |  | No | [7 empty] | 0 | 0 | 451 | 0 | ->
|  | QA |  |  |  | No | [7 empty] | 0 | 0 | 451 | 0 | ->
|  | QA |  |  |  | No | [7 empty] | 0 | 0 | 451 | 0 | ->
|  | QA |  |  |  | No | [7 empty] | 0 | 0 | 451 | 0 | ->
|  | QA |  |  |  | No | [7 empty] | 0 | 0 | 451 | 0 | ->
|  | QA |  |  |  | No | [7 empty] | 0 | 0 | 451 | 0 | ->
|  | QA |  |  |  | No | [7 empty] | 0 | 0 | 451 | 0 | ->
|  | QA |  |  |  | No | [7 empty] | 0 | 0 | 451 | 0 | ->
|  | QA |  |  |  | No | [7 empty] | 0 | 0 | 451 | 0 | ->
|  | QA |  |  |  | No | [7 empty] | 0 | 0 | 451 | 0 | ->
|  | QA |  |  |  | No | [7 empty] | 0 | 0 | 451 | 0 | ->
|  | QA |  |  |  | No | [7 empty] | 0 | 0 | 451 | 0 | ->
|  | QA |  |  |  | No | [7 empty] | 0 | 0 | 451 | 0 | ->
|  | QA |  |  |  | No | [7 empty] | 0 | 0 | 451 | 0 | ->
|  | QA |  |  |  | No | [7 empty] | 0 | 0 | 451 | 0 | ->
|  | QA |  |  |  | No | [7 empty] | 0 | 0 | 451 | 0 | ->
|  | QA |  |  |  | No | [7 empty] | 0 | 0 | 451 | 0 | ->
|  | QA |  |  |  | No | [7 empty] | 0 | 0 | 451 | 0 | ->
|  | QA |  |  |  | No | [7 empty] | 0 | 0 | 451 | 0 | ->
|  | QA |  |  |  | No | [7 empty] | 0 | 0 | 451 | 0 | ->
|  | QA |  |  |  | No | [7 empty] | 0 | 0 | 451 | 0 | ->
|  | QA |  |  |  | No | [7 empty] | 0 | 0 | 451 | 0 | ->
|  | QA |  |  |  | No | [7 empty] | 0 | 0 | 451 | 0 | ->
|  | QA |  |  |  | No | [7 empty] | 0 | 0 | 451 | 0 | ->
|  | QA |  |  |  | No | [7 empty] | 0 | 0 | 451 | 0 | ->
|  | QA |  |  |  | No | [7 empty] | 0 | 0 | 451 | 0 | ->
|  | QA |  |  |  | No | [7 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
[14 empty] | 0 | 0 | 451 | 0 | ->
Formulas:
Last Sent Back Date = IF([Report Name]="","",IF(SUMPRODUCT(MAX((A2:A497=[Report Name])*ROW(A2:A497)))=0,"",INDEX($B:$B,SUMPRODUCT(MAX((A2:A497=[Report Name])*ROW(A2:A497))))))
Note on F37: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: It is confirmed that both the new GDM View GDM_RPT.VW_LARGE_GAS_OUTAGE and ODS Prod Procedure [RPT].[usp_DH_Large_Gas_Outage] yielded exactly the same Billing Email Address for same Billing Account Number. No need change the DDL for view GDM_RPT.VW_LARGE_GAS_OUTAGE
Note on F41: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: No mismatch found when querying on 2026-09-17

## Dim Table (hidden)
This tab is manually maintained - edit Expected Report Count / Expected Release Date directly, or add new domain/month rows, as delivery plans change. Unlike Fact Table, the app always reads this sheet as-is.
Domain | Expected Report Count | Expected Release Date | Delivery Wave | Original Target | Revised Committed Milestone | Ready for Prod Deployment
Leaks | 8 | 2026-04-30 | July Reports | 2026-07-30 | 2026-09-09
Leaks | 10 | 2026-05-30 | August Reports | 2026-08-30 | 2026-09-30
Leaks | 9 | 2026-06-30 | September Reports | 2026-09-30 | 2026-10-30
CMS | 15 | 2026-07-30 | October Reports | 2026-10-30 | 2026-11-30
CMS | 15 | 2026-08-30 | November Reports | 2026-11-30 | 2026-12-31
CMS | 17 | 2026-09-30 | December Reports | 2026-12-31 | 2027-01-30
CMS | 20 | 2026-10-30 | January Reports | 2027-01-30 | 2027-02-27
CMS | 20 | 2026-11-30 | February Reports | 2027-02-28 | 2027-03-31
Maintenance and Construction | 18 | 2027-01-30 | March Reports | 2027-03-31 | 2027-04-03
Maintenance and Construction | 18 | 2027-02-28
Maintenance and Construction | 19 | 2027-03-31
Meter Management | 9 | 2026-12-31
Assets and Engineering | 8 | 2026-12-31

## Fact Table (hidden)
Reference snapshot only - the app rebuilds this automatically from Combined Delivery Data on every upload. Editing this tab directly has no effect.
Domain | Status | Report Name | DB Developers | PBI Developers | Schema | PO | Status Start Date | Expected Release Date | Actual Release Date
Leaks | DB Dev | RPT_04_Active Leaks | Fetwi | Sarath |  |  |  | 2026-04-03 | 2026-04-03
Leaks | PBI Dev | RPT_04_Active Leaks | Fetwi | Sarath |  |  | 2026-04-03 | 2026-04-02 | 2026-04-02
Leaks | QA | RPT_04_Active Leaks | Fetwi | Sarath |  |  | 2026-04-02 | 2026-04-10 | 2026-04-10
Leaks | DPO Approval | RPT_04_Active Leaks | Fetwi | Sarath |  |  | 2026-04-10
Leaks | RELEASED IN PROD | RPT_04_Active Leaks | Fetwi | Sarath
Leaks | DB Dev | RPT_04_Count of Active Leaks On Hand | Fetwi | Sarath |  |  |  | 2026-04-03 | 2026-04-03
Leaks | PBI Dev | RPT_04_Count of Active Leaks On Hand | Fetwi | Sarath |  |  | 2026-04-03 | 2026-04-02 | 2026-04-02
Leaks | QA | RPT_04_Count of Active Leaks On Hand | Fetwi | Sarath |  |  | 2026-04-02 | 2026-04-10 | 2026-04-10
Leaks | DPO Approval | RPT_04_Count of Active Leaks On Hand | Fetwi | Sarath |  |  | 2026-04-10
Leaks | RELEASED IN PROD | RPT_04_Count of Active Leaks On Hand | Fetwi | Sarath
Leaks | DB Dev | RPT_04_Leak Scheduling | Sreevarsha | Sarath |  |  |  | 2026-04-03 | 2026-04-03
Leaks | PBI Dev | RPT_04_Leak Scheduling | Sreevarsha | Sarath |  |  | 2026-04-03 | 2026-04-08 | 2026-04-08
Leaks | QA | RPT_04_Leak Scheduling | Sreevarsha | Sarath |  |  | 2026-04-08 | 2026-04-10 | 2026-04-10
Leaks | DPO Approval | RPT_04_Leak Scheduling | Sreevarsha | Sarath |  |  | 2026-04-10
Leaks | RELEASED IN PROD | RPT_04_Leak Scheduling | Sreevarsha | Sarath
Leaks | DB Dev | RPT_04_Leak Days Remaining | Siva | Navya |  |  |  | 2026-04-03 | 2026-04-03
Leaks | PBI Dev | RPT_04_Leak Days Remaining | Siva | Navya |  |  | 2026-04-03 | 2026-04-14 | 2026-04-14
Leaks | QA | RPT_04_Leak Days Remaining | Siva | Navya |  |  | 2026-04-14 | 2026-04-10 | 2026-04-10
Leaks | DPO Approval | RPT_04_Leak Days Remaining | Siva | Navya |  |  | 2026-04-10
Leaks | RELEASED IN PROD | RPT_04_Leak Days Remaining | Siva | Navya
Leaks | DB Dev | RPT_04_Cleared Leaks | Sreevarsha | Sarath |  |  |  | 2026-04-03 | 2026-04-03
Leaks | PBI Dev | RPT_04_Cleared Leaks | Sreevarsha | Sarath |  |  | 2026-04-03 | 2026-04-08 | 2026-04-08
Leaks | QA | RPT_04_Cleared Leaks | Sreevarsha | Sarath |  |  | 2026-04-08 | 2026-04-10 | 2026-04-10
Leaks | DPO Approval | RPT_04_Cleared Leaks | Sreevarsha | Sarath |  |  | 2026-04-10
Leaks | RELEASED IN PROD | RPT_04_Cleared Leaks | Sreevarsha | Sarath
Leaks | DB Dev | RPT_04_Leaks Repaired Detail | Rupa | Navya |  |  |  | 2026-04-03 | 2026-04-03
Leaks | PBI Dev | RPT_04_Leaks Repaired Detail | Rupa | Navya |  |  | 2026-04-03 | 2026-04-14 | 2026-04-14
Leaks | QA | RPT_04_Leaks Repaired Detail | Rupa | Navya |  |  | 2026-04-14 | 2026-04-10 | 2026-04-10
Leaks | DPO Approval | RPT_04_Leaks Repaired Detail | Rupa | Navya |  |  | 2026-04-10
Leaks | RELEASED IN PROD | RPT_04_Leaks Repaired Detail | Rupa | Navya
Leaks | DB Dev | RPT_04_Leaks Aging | Sreevarsha | Navya |  |  |  | 2026-04-10 | 2026-04-10
Leaks | PBI Dev | RPT_04_Leaks Aging | Sreevarsha | Navya |  |  | 2026-04-10 | 2026-04-14 | 2026-04-14
Leaks | QA | RPT_04_Leaks Aging | Sreevarsha | Navya |  |  | 2026-04-14 | 2026-04-10 | 2026-04-10
Leaks | DPO Approval | RPT_04_Leaks Aging | Sreevarsha | Navya |  |  | 2026-04-10
Leaks | RELEASED IN PROD | RPT_04_Leaks Aging | Sreevarsha | Navya
Leaks | DB Dev | RPT_04_Prior Leak Readings | Siddu | Navya |  |  |  | 2026-04-10 | 2026-04-10
Leaks | PBI Dev | RPT_04_Prior Leak Readings | Siddu | Navya |  |  | 2026-04-10 | 2026-04-14 | 2026-04-14
Leaks | QA | RPT_04_Prior Leak Readings | Siddu | Navya |  |  | 2026-04-14 | 2026-04-10 | 2026-04-10
Leaks | DPO Approval | RPT_04_Prior Leak Readings | Siddu | Navya |  |  | 2026-04-10
Leaks | RELEASED IN PROD | RPT_04_Prior Leak Readings | Siddu | Navya
Leaks | DB Dev | RSS_04_Leak Grade Change History | Siva | Navya |  |  |  | 2026-04-15 | 2026-04-15
Leaks | PBI Dev | RSS_04_Leak Grade Change History | Siva | Navya |  |  | 2026-04-15 | 2026-04-14 | 2026-04-14
Leaks | QA | RSS_04_Leak Grade Change History | Siva | Navya |  |  | 2026-04-14 | 2026-04-10 | 2026-04-10
Leaks | DPO Approval | RSS_04_Leak Grade Change History | Siva | Navya |  |  | 2026-04-10
Leaks | RELEASED IN PROD | RSS_04_Leak Grade Change History | Siva | Navya
Leaks | DB Dev | RPT_04_Surveillances With Zero Readings | Sreevarsha | Navya
Leaks | PBI Dev | RPT_04_Surveillances With Zero Readings | Sreevarsha | Navya |  |  |  | 2026-04-27 | 2026-04-27
Leaks | QA | RPT_04_Surveillances With Zero Readings | Sreevarsha | Navya |  |  | 2026-04-27 | 2026-04-27 | 2026-04-27
Leaks | DPO Approval | RPT_04_Surveillances With Zero Readings | Sreevarsha | Navya |  |  | 2026-04-27
Leaks | RELEASED IN PROD | RPT_04_Surveillances With Zero Readings | Sreevarsha | Navya
Leaks | DB Dev | RPT_04 High Emitter leaks | Sreevarsha | Navya
Leaks | PBI Dev | RPT_04 High Emitter leaks | Sreevarsha | Navya |  |  |  | 2026-04-29 | 2026-04-29
Leaks | QA | RPT_04 High Emitter leaks | Sreevarsha | Navya |  |  | 2026-04-29 | 2026-04-29 | 2026-04-29
Leaks | DPO Approval | RPT_04 High Emitter leaks | Sreevarsha | Navya |  |  | 2026-04-29
Leaks | RELEASED IN PROD | RPT_04 High Emitter leaks | Sreevarsha | Navya
Leaks | DB Dev | RPT_04_School Zone Leaks Without Repair | Sreevarsha | Sarath
Leaks | PBI Dev | RPT_04_School Zone Leaks Without Repair | Sreevarsha | Sarath |  |  |  | 2026-05-19 | 2026-05-19
Leaks | QA | RPT_04_School Zone Leaks Without Repair | Sreevarsha | Sarath |  |  | 2026-05-19 | 2026-05-19 | 2026-05-19
Leaks | DPO Approval | RPT_04_School Zone Leaks Without Repair | Sreevarsha | Sarath |  |  | 2026-05-19
Leaks | RELEASED IN PROD | RPT_04_School Zone Leaks Without Repair | Sreevarsha | Sarath
Leaks | DB Dev | RPT_04_PSC Quarterly Leak | Geetha | Sarath
Leaks | PBI Dev | RPT_04_PSC Quarterly Leak | Geetha | Sarath |  |  |  | 2026-06-02 | 2026-06-02
Leaks | QA | RPT_04_PSC Quarterly Leak | Geetha | Sarath |  |  | 2026-06-02 | 2026-06-02 | 2026-06-02
Leaks | DPO Approval | RPT_04_PSC Quarterly Leak | Geetha | Sarath |  |  | 2026-06-02
Leaks | RELEASED IN PROD | RPT_04_PSC Quarterly Leak | Geetha | Sarath |  |  |  | 2026-06-11 | 2026-06-11
Leaks | DB Dev | RPT_04_Rechecks Completed less than 14 days | Rupa | Shraddha
Leaks | PBI Dev | RPT_04_Rechecks Completed less than 14 days | Rupa | Shraddha |  |  |  | 2026-04-22 | 2026-04-22
Leaks | QA | RPT_04_Rechecks Completed less than 14 days | Rupa | Shraddha |  |  | 2026-04-22 | 2026-04-22 | 2026-04-22
Leaks | DPO Approval | RPT_04_Rechecks Completed less than 14 days | Rupa | Shraddha |  |  | 2026-04-22
Leaks | RELEASED IN PROD | RPT_04_Rechecks Completed less than 14 days | Rupa | Shraddha
Leaks | DB Dev | RPT_04_SEI Leak Activity | Siva | Shraddha
Leaks | PBI Dev | RPT_04_SEI Leak Activity | Siva | Shraddha |  |  |  | 2026-04-27 | 2026-04-27
Leaks | QA | RPT_04_SEI Leak Activity | Siva | Shraddha |  |  | 2026-04-27 | 2026-04-27 | 2026-04-27
Leaks | DPO Approval | RPT_04_SEI Leak Activity | Siva | Shraddha |  |  | 2026-04-27
Leaks | RELEASED IN PROD | RPT_04_SEI Leak Activity | Siva | Shraddha
Leaks | DB Dev | RPT_04_CMS Leak Productivity | Siddu | Navya
Leaks | PBI Dev | RPT_04_CMS Leak Productivity | Siddu | Navya |  |  |  | 2026-05-05 | 2026-05-05
Leaks | QA | RPT_04_CMS Leak Productivity | Siddu | Navya |  |  | 2026-05-05 | 2026-05-05 | 2026-05-05
Leaks | DPO Approval | RPT_04_CMS Leak Productivity | Siddu | Navya |  |  | 2026-05-05
Leaks | RELEASED IN PROD | RPT_04_CMS Leak Productivity | Siddu | Navya
Leaks | DB Dev | RPT_04_Main Break Corrosion and Leak Cluster | Siddu | Sarath
Leaks | PBI Dev | RPT_04_Main Break Corrosion and Leak Cluster | Siddu | Sarath |  |  |  | 2026-06-02 | 2026-06-02
Leaks | QA | RPT_04_Main Break Corrosion and Leak Cluster | Siddu | Sarath |  |  | 2026-06-02 | 2026-06-06 | 2026-06-06
Leaks | DPO Approval | RPT_04_Main Break Corrosion and Leak Cluster | Siddu | Sarath |  |  | 2026-06-06
Leaks | RELEASED IN PROD | RPT_04_Main Break Corrosion and Leak Cluster | Siddu | Sarath
Leaks | DB Dev | RPT_04_Leak Summary Status | Fetwi | Navya
Leaks | PBI Dev | RPT_04_Leak Summary Status | Fetwi | Navya |  |  |  | 2026-05-01 | 2026-05-01
Leaks | QA | RPT_04_Leak Summary Status | Fetwi | Navya |  |  | 2026-05-01 | 2026-06-02 | 2026-06-02
Leaks | DPO Approval | RPT_04_Leak Summary Status | Fetwi | Navya |  |  | 2026-06-02
Leaks | RELEASED IN PROD | RPT_04_Leak Summary Status | Fetwi | Navya |  |  |  | 2026-06-11 | 2026-06-11
Leaks | DB Dev | RPT_04_PSC Leak Printout | Fetwi | Shraddha |  |  |  | 2026-06-02 | 2026-06-02
Leaks | PBI Dev | RPT_04_PSC Leak Printout | Fetwi | Shraddha |  |  | 2026-06-02 | 2026-06-05 | 2026-06-05
Leaks | QA | RPT_04_PSC Leak Printout | Fetwi | Shraddha |  |  | 2026-06-05 | 2026-06-02 | 2026-06-02
Leaks | DPO Approval | RPT_04_PSC Leak Printout | Fetwi | Shraddha |  |  | 2026-06-02
Leaks | RELEASED IN PROD | RPT_04_PSC Leak Printout | Fetwi | Shraddha |  |  |  | 2026-06-19 | 2026-06-19
Leaks | DB Dev | RPT_04_Leak Control Report | Geetha | Navya |  |  |  | 2026-05-06 | 2026-05-06
Leaks | PBI Dev | RPT_04_Leak Control Report | Geetha | Navya |  |  | 2026-05-06 | 2026-06-10 | 2026-06-10
Leaks | QA | RPT_04_Leak Control Report | Geetha | Navya |  |  | 2026-06-10 | 2026-06-22 | 2026-06-22
Leaks | DPO Approval | RPT_04_Leak Control Report | Geetha | Navya |  |  | 2026-06-22
Leaks | RELEASED IN PROD | RPT_04_Leak Control Report | Geetha | Navya
Leaks | DB Dev | RPT_04_Leak Life Cycle | Geetha | Shraddha |  |  |  | 2026-05-20 | 2026-05-20
Leaks | PBI Dev | RPT_04_Leak Life Cycle | Geetha | Shraddha |  |  | 2026-05-20 | 2026-06-09 | 2026-06-09
Leaks | QA | RPT_04_Leak Life Cycle | Geetha | Shraddha |  |  | 2026-06-09 | 2026-06-25 | 2026-06-25
Leaks | DPO Approval | RPT_04_Leak Life Cycle | Geetha | Shraddha |  |  | 2026-06-25
Leaks | RELEASED IN PROD | RPT_04_Leak Life Cycle | Geetha | Shraddha
Leaks | DB Dev | RPT_04_Leak Life Cycle Legacy LMS LI | Fetwi | Navya |  |  |  | 2026-05-26 | 2026-05-26
Leaks | PBI Dev | RPT_04_Leak Life Cycle Legacy LMS LI | Fetwi | Navya |  |  | 2026-05-26 | 2026-06-10 | 2026-06-10
Leaks | QA | RPT_04_Leak Life Cycle Legacy LMS LI | Fetwi | Navya |  |  | 2026-06-10 | 2026-06-25 | 2026-06-25
Leaks | DPO Approval | RPT_04_Leak Life Cycle Legacy LMS LI | Fetwi | Navya |  |  | 2026-06-25
Leaks | RELEASED IN PROD | RPT_04_Leak Life Cycle Legacy LMS LI | Fetwi | Navya
Leaks | DB Dev | RPT_04_Leak Increase Reads | Fetwi | Navya |  |  |  | 2026-05-23 | 2026-05-23
Leaks | PBI Dev | RPT_04_Leak Increase Reads | Fetwi | Navya |  |  | 2026-05-23 | 2026-05-11 | 2026-05-11
Leaks | QA | RPT_04_Leak Increase Reads | Fetwi | Navya |  |  | 2026-05-11 | 2026-05-12 | 2026-05-12
Leaks | DPO Approval | RPT_04_Leak Increase Reads | Fetwi | Navya |  |  | 2026-05-12
Leaks | RELEASED IN PROD | RPT_04_Leak Increase Reads | Fetwi | Navya |  |  |  | 2026-06-11 | 2026-06-11
Leaks | DB Dev | Leak 360 Dashboard | Siva | Sarath |  |  |  | 2026-05-20 | 2026-05-20
Leaks | PBI Dev | Leak 360 Dashboard | Siva | Sarath |  |  | 2026-05-20 | 2026-06-13 | 2026-06-13
Leaks | QA | Leak 360 Dashboard | Siva | Sarath |  |  | 2026-06-13 | 2026-06-15 | 2026-06-15
Leaks | DB Dev | RPT_04_Leak Recheck Control | Siva | Shraddha |  |  |  | 2026-05-20 | 2026-05-20
Leaks | PBI Dev | RPT_04_Leak Recheck Control | Siva | Shraddha |  |  | 2026-05-20 | 2026-05-22 | 2026-05-22
Leaks | QA | RPT_04_Leak Recheck Control | Siva | Shraddha |  |  | 2026-05-22 | 2026-07-01 | 2026-07-01
Leaks | DPO Approval | RPT_04_Leak Recheck Control | Siva | Shraddha |  |  | 2026-07-01
Leaks | RELEASED IN PROD | RPT_04_Leak Recheck Control | Siva | Shraddha
Leaks | DB Dev | RPT_04_Main_Replacement Report | Sree | Navya |  |  |  | 2026-05-27 | 2026-05-27
Leaks | PBI Dev | RPT_04_Main_Replacement Report | Sree | Navya |  |  | 2026-05-27 | 2026-06-18 | 2026-06-18
Leaks | QA | RPT_04_Main_Replacement Report | Sree | Navya |  |  | 2026-06-18 | 2026-06-23 | 2026-06-23
Leaks | DPO Approval | RPT_04_Main_Replacement Report | Sree | Navya |  |  | 2026-06-23
Leaks | RELEASED IN PROD | RPT_04_Main_Replacement Report | Sree | Navya
Leaks | DB Dev | New Report: Leak Repair Exception | Geetha | Shraddha |  |  |  | 2026-05-26 | 2026-05-26
Leaks | PBI Dev | New Report: Leak Repair Exception | Geetha | Shraddha |  |  | 2026-05-26 | 2026-06-16 | 2026-06-16
Leaks | QA | New Report: Leak Repair Exception | Geetha | Shraddha |  |  | 2026-06-16 | 2026-06-16 | 2026-06-16
Leaks | DPO Approval | New Report: Leak Repair Exception | Geetha | Shraddha |  |  | 2026-06-16
Leaks | RELEASED IN PROD | New Report: Leak Repair Exception | Geetha | Shraddha |  |  |  | 2026-06-19 | 2026-06-19
Leaks | DB Dev | New Report: (Leak reading sample point mismatch ) Creating a new report that... | Siddu | Shraddha |  |  |  | 2026-05-27 | 2026-05-27
Leaks | PBI Dev | New Report: (Leak reading sample point mismatch ) Creating a new report that... | Siddu | Shraddha |  |  | 2026-05-27 | 2026-06-22 | 2026-06-22
Leaks | QA | New Report: (Leak reading sample point mismatch ) Creating a new report that... | Siddu | Shraddha |  |  | 2026-06-22 | 2026-06-24 | 2026-06-24
Leaks | DPO Approval | New Report: (Leak reading sample point mismatch ) Creating a new report that... | Siddu | Shraddha |  |  | 2026-06-24
Leaks | RELEASED IN PROD | New Report: (Leak reading sample point mismatch ) Creating a new report that... | Siddu | Shraddha
CMS | DB Dev | RPT_02_CO Flue Warning Tag Control | Rupa | Navya |  | Kushal
CMS | PBI Dev | RPT_02_CO Flue Warning Tag Control | Rupa | Navya |  | Kushal |  | 2026-07-10 | 2026-07-10
CMS | QA | RPT_02_CO Flue Warning Tag Control | Rupa | Navya |  | Kushal | 2026-07-10 | 2026-07-20 | 2026-07-20
CMS | DB Dev | RPT_02_Warning Tag HEFPA | Sree | Shraddha |  | Kushal
CMS | PBI Dev | RPT_02_Warning Tag HEFPA | Sree | Shraddha |  | Kushal |  | 2026-07-15 | 2026-07-15
CMS | QA | RPT_02_Warning Tag HEFPA | Sree | Shraddha |  | Kushal | 2026-07-15 | 2026-07-20 | 2026-07-20
CMS | DB Dev | RPT_02_Warning tag Printout | Sree | Shraddha |  | Kushal
CMS | PBI Dev | RPT_02_Warning tag Printout | Sree | Shraddha |  | Kushal |  | 2026-07-22 | 2026-07-22
CMS | QA | RPT_02_Warning tag Printout | Sree | Shraddha |  | Kushal | 2026-07-22 | 2026-07-20 | 2026-07-20
CMS | DB Dev | RPT_02_Corrosion | Siva | Sarath |  | Kushal
CMS | PBI Dev | RPT_02_Corrosion | Siva | Sarath |  | Kushal |  | 2026-07-24 | 2026-07-24
CMS | QA | RPT_02_Corrosion | Siva | Sarath |  | Kushal | 2026-07-24 | 2026-07-20 | 2026-07-20
CMS | DB Dev | RPT_02_House Pipe Test Comment Control | Geetha | Shraddha |  | Kushal
CMS | PBI Dev | RPT_02_House Pipe Test Comment Control | Geetha | Shraddha |  | Kushal |  | 2026-07-13 | 2026-07-13
CMS | QA | RPT_02_House Pipe Test Comment Control | Geetha | Shraddha |  | Kushal | 2026-07-13 | 2026-07-22 | 2026-07-22
CMS | DB Dev | RPT_02_Required Regulator Inspection Performed Control | Siddu | Navya |  | Bardia
CMS | DB Dev | RPT_02_Service Regulator Inspections | Sree | Sarath |  | Bardia
CMS | DB Dev | RPT_02_Service Regulator Inspection Printout | Sree | Sarath |  | Bardia
CMS | PBI Dev | RPT_02_Service Regulator Inspection Printout | Sree | Sarath |  | Bardia |  | 2026-07-18 | 2026-07-18
CMS | QA | RPT_02_Service Regulator Inspection Printout | Sree | Sarath |  | Bardia | 2026-07-18 | 2026-07-20 | 2026-07-20
CMS | DB Dev | RPT_02_20 Year Regulator Inspection | Siddu | Navya |  | Bardia
CMS | PBI Dev | RPT_02_20 Year Regulator Inspection | Siddu | Navya |  | Bardia |  | 2026-07-17 | 2026-07-17
CMS | QA | RPT_02_20 Year Regulator Inspection | Siddu | Navya |  | Bardia | 2026-07-17 | 2026-07-20 | 2026-07-20
CMS | DB Dev | RPT_02_Fixed Factor | Nick | Navya |  | Bardia
CMS | PBI Dev | RPT_02_Fixed Factor | Nick | Navya |  | Bardia |  | 2026-07-21 | 2026-07-21
CMS | QA | RPT_02_Fixed Factor | Nick | Navya |  | Bardia | 2026-07-21 | 2026-07-20 | 2026-07-20
CMS | DB Dev | RPT_02_Fixed Factor Printout | Nick | Shraddha |  | Bardia
CMS | PBI Dev | RPT_02_Fixed Factor Printout | Nick | Shraddha |  | Bardia |  | 2026-07-22 | 2026-07-22
CMS | QA | RPT_02_Fixed Factor Printout | Nick | Shraddha |  | Bardia | 2026-07-22 | 2026-07-20 | 2026-07-20
CMS | DB Dev | RPT_02_Work Order Completion Printout | Rupa | Sarath |  | Kushal
CMS | PBI Dev | RPT_02_Work Order Completion Printout | Rupa | Sarath |  | Kushal |  | 2026-07-23 | 2026-07-23
CMS | QA | RPT_02_Work Order Completion Printout | Rupa | Sarath |  | Kushal | 2026-07-23 | 2026-07-20 | 2026-07-20
CMS | DB Dev | RPT_02_GRO Control | Siva | Navya |  | Kushal
CMS | PBI Dev | RPT_02_GRO Control | Siva | Navya |  | Kushal |  | 2026-07-22 | 2026-07-22
CMS | QA | RPT_02_GRO Control | Siva | Navya |  | Kushal | 2026-07-22 | 2026-07-20 | 2026-07-20
CMS | DB Dev | RPT_02_GRO Monitor | Rupa | Shraddha |  | Bardia
CMS | PBI Dev | RPT_02_GRO Monitor | Rupa | Shraddha |  | Bardia |  | 2026-07-22 | 2026-07-22
CMS | QA | RPT_02_GRO Monitor | Rupa | Shraddha |  | Bardia | 2026-07-22 | 2026-07-27 | 2026-07-27
CMS | DB Dev | RPT_02_Public Buildings Inspection | Geetha
CMS | PBI Dev | RPT_02_Public Buildings Inspection | Geetha
CMS | QA | RPT_02_Public Buildings Inspection | Geetha
CMS | DB Dev | RPT_02_Gas Trouble | Siddu
CMS | PBI Dev | RPT_02_Gas Trouble | Siddu
CMS | QA | RPT_02_Gas Trouble | Siddu

## Data Validation (hidden)
Domain | DB Developer | PBI Developer | PO | Yes / No | Current Status | All Developers | QA Tester | Blocked? | Rework Stage | DPO Approval | Resolved? | Person | Email | Build Source | compliance or Regulatory
-> feeds column A on Combined Delivery Data | -> feeds column G on Combined Delivery Data | -> feeds column H on Combined Delivery Data | -> feeds column F on Combined Delivery Data | -> feeds column U (Confirmed Deployed?) on Combined Delivery Data | -> feeds column C on Combined Delivery Data | -> legacy combined list (Rework Log now uses per-stage lists via B/C/H/K) | -> feeds column I on Combined Delivery Data | -> feeds column Y on Combined Delivery Data | -> feeds From/To Stage on Rework Log | -> feeds Sent Back By / Fixed By when stage is DPO Approval | -> feeds Resolved? on Rework Log (sender-owned) | Bardia | Bardia.Mouhebat@nationalgrid.com | Raw | compliance
Leaks | Fetwi | Navya | Kushal | Yes | NOT STARTED | Fetwi | Preety | No | DB Dev | Kelvin Hu | No | Fetwi | Fetwi.Hayelom@nationalgrid.com | Curated | Regulatory
CMS | Siva | Sarath | Bardia | No | DB Dev | Siva | Kelvin | Yes – other | PBI Dev |  | Yes | Geetha | Geetha.S1@nationalgrid.com | hybrid | Ops
Maintenance and Construction | Sreevarsha | Shraddha |  |  | PBI Dev | Sreevarsha | Kushal | Yes – needs DB Dev to fix | QA |  | Did not pass re-test | Kelvin | Yuehua.Hu@nationalgrid.com
Meter Management | Siddu |  |  |  | QA | Siddu | Bardia | Yes – needs PBI Dev to fix | DPO Approval |  |  | Kelvin Hu | Yuehua.Hu@nationalgrid.com
Assets and Engineering | Sree |  |  |  | DPO Approval | Sree | Olu | Yes – needs QA to fix |  |  |  | Kushal | Kushal.Shah@nationalgrid.com
| Rupa |  |  |  | Ready for Release in Prod | Rupa |  | Yes – needs DPO Approval to fix |  |  |  | Navya | Navya.ChowdarySaimpu@nationalgrid.com
| Geetha |  |  |  | RELEASED IN PROD | Geetha |  | Yes – Blocked in Prod |  |  |  | Nick | Nick.Virdi@nationalgrid.com
| Nick |  |  |  |  | Nick |  | rework for views with new dynamic tables. |  |  |  | Preety | Preety.Jha@nationalgrid.com
| Mejo George |  |  |  |  | Navya | [5 empty] | Rupa | Rupa.Koduru@nationalgrid.com
| Michael Ayedun |  |  |  |  | Sarath | [5 empty] | Sarath | Sarath.Neela@nationalgrid.com
[6 empty] | Shraddha | [5 empty] | Shraddha | Shraddha.TC@nationalgrid.com
[12 empty] | Siddu | Siddharoodh.Hiregoudar@nationalgrid.com
[12 empty] | Siva | Sivaram.Kanda1@nationalgrid.com
[12 empty] | Sree | Sreevarsha.Potluri@nationalgrid.com
[12 empty] | Sreevarsha | Sreevarsha.Potluri@nationalgrid.com
[12 empty] | Michael | Michael.Ayedun@nationalgrid.com
[12 empty] | Olu | Oluwademilade.Adeniji@nationalgrid.com
Note on A1: This list feeds the dropdown on Combined Delivery Data, column A (Domain). Add, remove, or rename values here and the dropdown updates automatically.
Note on B1: This list feeds the dropdown on Combined Delivery Data, column F (DB Developer). Add, remove, or rename values here and the dropdown updates automatically.
Note on C1: This list feeds the dropdown on Combined Delivery Data, column G (PBI Developer). Add, remove, or rename values here and the dropdown updates automatically.
Note on D1: This list feeds the dropdown on Combined Delivery Data, column E (PO). Add, remove, or rename values here and the dropdown updates automatically.
Note on E1: This list feeds the dropdown on Combined Delivery Data, column Z (Blocked?). Add, remove, or rename values here and the dropdown updates automatically.
Note on F1: This list feeds the dropdown on Combined Delivery Data, column C (Current Status). Add, remove, or rename values here and the dropdown updates automatically.

## Dashboard (hidden)
CMS reports | [10 empty] | As of 16 Oct 2026. Live from Combined Delivery Data.
GDM migration. 72 reports in the July to November waves. Milestones are the revised committed dates.
30 of 72 | reports are blocked. 27 are approved and waiting for a production release, 3 are blocked in build or QA.
| 27 |  | 3 |  | 28 |  | 12 |  | 2 |  | Checks
| Waiting for a production release |  | Blocked in build or QA |  | In progress, DB Dev to DPO Approval |  | Not started |  | Released to production |  | Counts reconcile, 72 of 72 reports. Status column behind the dates: 41.
By month | Reports by Plan Delivery Month and Current Status. Milestone is the revised committed date from the Dim Table.
Month | Waiting for release | Blocked in build/QA | DPO Approval | QA | PBI Dev | DB Dev | Not started | Released | Reports | Milestone | Milestone status
July | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 2026-09-09 | 37 days past milestone, 14 of 14 not released
August | 11 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 2026-09-30 | 16 days past milestone, 12 of 12 not released
September | 2 | 2 | 6 | 3 | 2 | 0 | 1 | 2 | 18 | 2026-10-30 | 14 days to milestone, 2 blocked
October | 0 | 1 | 1 | 5 | 2 | 1 | 3 | 0 | 13 | 2026-11-30 | 45 days to milestone, 1 blocked
November | 0 | 0 | 0 | 0 | 4 | 3 | 8 | 0 | 15 | 2026-12-31 | 76 days to milestone
Total | 27 | 3 | 8 | 8 | 8 | 4 | 12 | 2 | 72
Reports by month and status | Same numbers as the table, one bar per month. Amber is approved work waiting for a release; red is a defect being fixed.
Status column behind the dates (41) | A completion date is in the tracker but Current Status was not moved to the next stage. Whoever completed the stage updates it.
Report | Month | Current status | Status | Who updates it
RPT_02_CO Flue Warning Tag Control | July | Ready for Release in Prod | Blocked - log it on Rework Log
RPT_02_Warning Tag HEFPA | July | Ready for Release in Prod | Blocked - log it on Rework Log
RPT_02_Warning tag Printout | July | Ready for Release in Prod | Blocked - log it on Rework Log
RPT_02_Corrosion | July | Ready for Release in Prod | Blocked - log it on Rework Log
RPT_02_House Pipe Test Comment Control | July | Ready for Release in Prod | Blocked - log it on Rework Log
RPT_02_Required Regulator Inspection Performed Control | July | Ready for Release in Prod | Blocked - log it on Rework Log
RPT_02_Service Regulator Inspections | July | Ready for Release in Prod | Blocked - log it on Rework Log
RPT_02_Service Regulator Inspection Printout | July | Ready for Release in Prod | Blocked - log it on Rework Log
RPT_02_20 Year Regulator Inspection | July | Ready for Release in Prod | Blocked - log it on Rework Log
RPT_02_Fixed Factor | July | Ready for Release in Prod | Blocked - log it on Rework Log
Reports
| Month |  | Status |  | Person
| All |  | All |  | All |  | No reports match
Report | Month | Current status | Blocked? | DB developer | PBI developer | QA tester | DPO reviewer | DB Dev done | PBI Dev done | QA done | DPO approved | Reworks | Status column needs updating
RPT_02_CO Flue Warning Tag Control | July | Ready for Release in Prod | Yes – Blocked in Prod | Rupa | Navya | Kushal | Jeanne Waldron, Anthony Massimino | 2026-08-11 | 2026-08-11 | 2026-08-18 | 2026-09-08 | 1 | Blocked - log it on Rework Log
RPT_02_Warning Tag HEFPA | July | Ready for Release in Prod | Yes – Blocked in Prod | Sree | Shraddha | Kushal | Jeanne Waldron, Anthony Massimino | 2026-08-21 | 2026-08-12 | 2026-08-21 | 2026-09-08 | 3 | Blocked - log it on Rework Log
RPT_02_Warning tag Printout | July | Ready for Release in Prod | Yes – Blocked in Prod | Sree | Shraddha | Kushal | Jeanne Waldron, Anthony Massimino | 2026-08-12 | 2026-08-17 | 2026-08-24 | 2026-09-08 | 1 | Blocked - log it on Rework Log
RPT_02_Corrosion | July | Ready for Release in Prod | Yes – Blocked in Prod | Siva | Sarath | Preety | Jeanne Waldron, Anthony Massimino | 2026-09-01 | 2026-08-19 | 2026-09-04 | 2026-09-08 | 2 | Blocked - log it on Rework Log
RPT_02_House Pipe Test Comment Control | July | Ready for Release in Prod | Yes – Blocked in Prod | Geetha | Shraddha | Preety | Jeanne Waldron, Anthony Massimino | 2026-08-17 | 2026-08-10 | 2026-08-20 | 2026-09-08 | 1 | Blocked - log it on Rework Log
RPT_02_Required Regulator Inspection Performed Control | July | Ready for Release in Prod | Yes – Blocked in Prod | Siddu | Navya | Bardia | Jeanne Waldron, Anthony Massimino | 2026-08-18 | 2026-08-17 | 2026-08-21 | 2026-09-08 | 2 | Blocked - log it on Rework Log
RPT_02_Service Regulator Inspections | July | Ready for Release in Prod | Yes – Blocked in Prod | Sree | Sarath | Bardia | Jeanne Waldron, Anthony Massimino | 2026-08-24 | 2026-09-01 | 2026-09-02 | 2026-09-08 | 3 | Blocked - log it on Rework Log
RPT_02_Service Regulator Inspection Printout | July | Ready for Release in Prod | Yes – Blocked in Prod | Sree | Shraddha | Bardia | Jeanne Waldron, Anthony Massimino | 2026-08-24 | 2026-08-12 | 2026-09-02 | 2026-09-08 | 1 | Blocked - log it on Rework Log
RPT_02_20 Year Regulator Inspection | July | Ready for Release in Prod | Yes – Blocked in Prod | Siddu | Navya | Bardia | Natalie Lattanzio | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-09-04 | 1 | Blocked - log it on Rework Log
RPT_02_Fixed Factor | July | Ready for Release in Prod | Yes – Blocked in Prod | Nick | Navya | Bardia | Natalie Lattanzio | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-09-04 | 2 | Blocked - log it on Rework Log
RPT_02_Fixed Factor Printout | July | Ready for Release in Prod | Yes – Blocked in Prod | Nick | Shraddha | Preety | Natalie Lattanzio | 2026-08-11 | 2026-08-24 | 2026-08-24 | 2026-09-04 | 2 | Blocked - log it on Rework Log
RPT_02_Work Order Completion Printout | July | Ready for Release in Prod | Yes – Blocked in Prod | Rupa | Shraddha | Preety | Jeanne Waldron, Anthony Massimino | 2026-08-17 | 2026-08-21 | 2026-08-24 | 2026-09-08 | 1 | Blocked - log it on Rework Log
RPT_02_GRO Control | July | Ready for Release in Prod | Yes – Blocked in Prod | Siva | Navya | Preety | Jeanne Waldron, Anthony Massimino | 2026-08-14 | 2026-08-17 | 2026-08-24 | 2026-09-08 | 0 | Blocked - log it on Rework Log
RPT_02_GRO Monitor | July | Ready for Release in Prod | Yes – Blocked in Prod | Rupa | Sarath | Preety | Natalie Lattanzio | 2026-08-11 | 2026-08-14 | 2026-08-27 | 2026-09-04 | 0 | Blocked - log it on Rework Log
RPT_02_Public Buildings Inspection | August | Ready for Release in Prod | Yes – Blocked in Prod | Geetha | Navya | Preety | Jeanne Waldron, Anthony Massimino | 2026-08-18 | 2026-09-30 | 2026-10-01 | 2026-10-01 | 3 | Blocked - log it on Rework Log
RPT_02_Investigate Wall Check and Service Check | August | Ready for Release in Prod | Yes – needs DPO Approval to fix | Siva | Sarath | Preety | Shaunna Peters | 2026-08-21 | 2026-08-24 | 2026-09-08 | 2026-09-18 | 3 | Blocked - log it on Rework Log
RPT_02_Cut Out Orders | August | Ready for Release in Prod | Yes – Blocked in Prod | Fetwi | Shraddha | Preety | Shaunna Peters | 2026-08-10 | 2026-08-31 | 2026-08-31 | 2026-09-18 | 1 | Blocked - log it on Rework Log
RPT_02_Gas Trouble | August | Ready for Release in Prod | Yes – Blocked in Prod | Siddu | Navya | Preety | Jeanne Waldron, Anthony Massimino | 2026-08-10 | 2026-08-27 | 2026-09-01 | 2026-09-18 | 1 | Blocked - log it on Rework Log
RPT_02_Wall Check Control | August | Ready for Release in Prod | Yes – Blocked in Prod | Nick | Shraddha | Kushal | Jeanne Waldron, Anthony Massimino | 2026-08-12 | 2026-08-27 | 2026-08-31 | 2026-09-18 | 0 | Blocked - log it on Rework Log
RPT_02_High Pressure Steel Inside Inspection | August | Ready for Release in Prod | Yes – Blocked in Prod | Geetha | Sarath | Bardia | Shaunna Peters | 2026-08-19 | 2026-08-21 | 2026-09-04 | 2026-09-18 | 0 | Blocked - log it on Rework Log
RPT_02_Large Gas Outage | August | Ready for Release in Prod | Yes – Blocked in Prod | Nick | Sarath | Kushal | Brooke Allen | 2026-08-31 | 2026-09-01 | 2026-09-21 | 2026-10-07 | 5 | Blocked - log it on Rework Log
RPT_02_Fitting Work | August | Ready for Release in Prod | Yes – Blocked in Prod | Fetwi | Navya | Bardia | Shaunna Peters | 2026-08-11 | 2026-08-18 | 2026-09-08 | 2026-09-18 | 1 | Blocked - log it on Rework Log
RPT_02_Field Collector Report | August | Ready for Release in Prod | Yes – Blocked in Prod | Rupa | Shraddha | Bardia | Jeanne Timmons, Shaunna Peters | 2026-08-14 | 2026-08-26 | 2026-09-11 | 2026-09-18 | 0 | Blocked - log it on Rework Log
RPT_02_Turn On for Non-Payment | August | DPO Approval | No | Sree | Sarath | Kushal | Bryan Patterson, Reginald Durham, Shaunna Peters, Simone Brooks, Bill Contreras | 2026-08-18 | 2026-09-02 | 2026-09-25 |  | 2 | Open rework row - mark Blocked or close it
RPT_02_Collector Payment Recap | August | Ready for Release in Prod | Yes – Blocked in Prod | Rupa | Shraddha | Bardia | Oneil Lashley | 2026-08-17 | 2026-08-28 | 2026-09-16 | 2026-09-21 | 1 | Blocked - log it on Rework Log
RPT_02_Incentive Management | August | Ready for Release in Prod | Yes – Blocked in Prod | Siddu | Navya | Preety | Reginald Durham | 2026-08-19 | 2026-08-28 | 2026-09-04 | 2026-09-17 | 0 | Blocked - log it on Rework Log
RPT_02_UTC Report | September | DPO Approval | No | Rupa | Shraddha | Preety | Simone Brooks | 2026-08-19 | 2026-09-30 |  |  | 1
RPT_02_Adjacent Property Checks | September | DPO Approval | Yes – needs DPO Approval to fix | Rupa | Navya | Olu | Anthony Massimino | 2026-08-19 | 2026-09-01 | 2026-09-23 |  | 0 | Blocked - log it on Rework Log
RPT_02_High Bill Investigations | September | Ready for Release in Prod | Yes – Blocked in Prod | Sree | Sarath | Preety | Oneil Lashley |  | 2026-09-03 | 2026-09-17 | 2026-09-21 | 1 | Blocked - log it on Rework Log
RPT_02_Emergency Order Type | September | QA | No | Sree | Shraddha | Kushal | Jeanne Waldron, Anthony Massimino | 2026-10-03 | 2026-10-06 |  |  | 1 | Move status back to PBI Dev
RPT_02_Cut Out Curb Box | September | RELEASED IN PROD | Yes – Blocked in Prod | Fetwi | Navya | Preety | Oneil Lashley | 2026-08-19 | 2026-09-01 | 2026-09-25 | 2026-10-06 | 1 | Blocked - log it on Rework Log
RPT_02_New York Incident | September | RELEASED IN PROD | No | Nick | Sarath | Preety | Bryan Patterson, Reginald Durham, Bill Contreras | 2026-08-21 | 2026-09-08 | 2026-09-21 | 2026-09-30 | 1
RPT_02_Outside Repeat Leaks | September | DPO Approval | No | Fetwi | Navya | Preety | Reginald Durham, Simone Brooks, Bill Contreras | 2026-08-21 | 2026-09-03 | 2026-09-30 |  | 1
RPT_02_Meter Change | September | DPO Approval | Yes – needs DPO Approval to fix | Siddu | Shraddha | Olu | Michelle Fitten | 2026-08-25 | 2026-09-17 | 2026-09-24 |  | 0 | Blocked - log it on Rework Log
RPT_02_Field Order Value | September | DPO Approval | No | Siddu | Navya | Preety | Alex Giangolini | 2026-09-01 | 2026-09-29 | 2026-10-05 |  | 1
RPT_02_Same Day Reconnect | September | QA | No | Geetha | Navya | Preety | Bryan Patterson | 2026-09-01 | 2026-09-04 |  |  | 0
RPT_02_Site Specific Analysis | September | DPO Approval | No | Nick | Shraddha | Olu | Jeanne Waldron, Anthony Massimino | 2026-08-31 | 2026-09-08 | 2026-09-23 |  | 0
RPT_02_PSC Wire Down Response Time | September | PBI Dev | No | Fetwi | Sarath |  | Bryan Patterson | 2026-09-17 |  |  |  | 0
RPT_02_Hazardous Above Ground Leak | September | DPO Approval | No | Fetwi | Navya | Kushal | Reginald Durham, Simone Brooks, Shaunna Peters, Bill Contreras | 2026-08-20 | 2026-08-20 |  |  | 1 | This is in QA
RPT_02_AMI Contractor Completion Report | September | PBI Dev | No | Michael | Shraddha |  | Meredith Dube | 2026-08-24 |  |  |  | 0
RPT_02_Collection Statistic | September | NOT STARTED | No | Siva | Sarath |  | Brett Palmeri |  |  |  |  | 0
RPT_02_First and Last Job | September | QA | No | Sree | Shraddha |  | Oneil Lashley | 2026-09-11 | 2026-10-08 |  |  | 0
RPT_02_Rate Class | September | Ready for Release in Prod | Yes – Blocked in Prod | Fetwi | Navya | Preety | Zishan Momin | 2026-08-25 | 2026-09-16 | 2026-09-28 | 2026-10-02 | 0 | Blocked - log it on Rework Log
RPT_04_Leak Recheck Times | September | DPO Approval | No | Rupa | Shraddha | Preety | Shaunna Peters | 2026-08-24 | 2026-09-11 | 2026-10-06 |  | 0
RPT_02_Service Resource Activity | October | DPO Approval |  | Rupa | Shraddha | Preety | Simone Brooks | 2026-08-25 | 2026-09-24 | 2026-10-03 |  | 0
RPT_02_Incomplete Service Appointments | October | QA |  | Michael | Shraddha | Preety | Shaunna Peters | 2026-09-04 | 2026-10-08 |  |  | 0
RPT_02_Emergency Response Time Review Report | October | NOT STARTED |  | Siva |  |  | Christina Illingworth |  |  |  |  | 0
RPT_02_Personal Injury and Shock Investigation | October | NOT STARTED |  | Siva |  |  | Christina Illingworth |  |  |  |  | 0
RPT_02_Emergency Response Statistics | October | NOT STARTED |  | Nick |  |  | Christina Illingworth |  |  |  |  | 0
RPT_02_Emergency Time Adjustments Log | October | PBI Dev | Yes – needs DB Dev to fix | Fetwi | Navya |  | Bryan Patterson, Reginald Durham, Shaunna Peters, Simone Brooks, Bill Contreras | 2026-09-01 |  |  |  | 0 | Blocked - log it on Rework Log
RPT_02_PSC Soft Off Report | October | PBI Dev |  | Rupa | Navya |  | Angela Keegan | 2026-09-01 |  |  |  | 0
RPT_02_Service Interruptions | October | QA | No | Geetha | Navya | Preety | Bryan Patterson, Reginald Durham, Bill Contreras | 2026-09-15 |  |  |  | 0
RPT_02_Duty to Inspect | October | QA |  | Geetha | Navya | Preety | Bryan Patterson | 2026-09-22 | 2026-09-29 |  |  | 0
RPT_02_Service Appointment Life Cycle | October | DB Dev |  | Nick | Shraddha | Preety | Megan Piccarreto | 2026-09-18 |  |  |  | 0 | Move status to PBI Dev
RPT_02_PSC Inactive Account | October | QA |  | Rupa | Shraddha | Preety | Reginald Durham, Simone Brooks | 2026-09-03 | 2026-09-29 |  |  | 0
RPT_02_Service Resource Performance | October | PBI Dev |  | Rupa | Navya |  | Oneil Lashley | 2026-09-21 |  |  |  | 0
RPT_02_Emergency Leak Response Metric (6 sub reports) | October | QA |  | Fetwi | Navya |  | Bryan Patterson, Reginald Durham, Shaunna Peters, Simone Brooks, Bill Contreras | 2026-09-21 |  |  |  | 0
RPT_02_Fixed Factor Mismatch | November | NOT STARTED |  | Siddu | Navya |  | Matthew Menicucci | 2026-09-25 |  |  |  | 0 | Move status to PBI Dev
RPT_02_Light Up Orders | November | NOT STARTED |  | Siva | Navya |  | Shaunna Peters |  |  |  |  | 0
RPT_02_Meter To Billing Report | November | NOT STARTED |  | Siva | Shraddha |  | Shaunna Peters |  |  |  |  | 0
RPT_02_Install Meter Orders | November | NOT STARTED |  | Michael | Shraddha |  | Shaunna Peters | 2026-09-17 |  |  |  | 0 | Move status to PBI Dev
RPT_02_Non Emergency Orders | November | NOT STARTED |  | Michael | Navya |  | Shaunna Peters | 2026-10-08 |  |  |  | 0 | Move status to PBI Dev
RPT_02_Carbon Monoxide | November | NOT STARTED |  | Sree | Navya |  | Bryan Patterson, Reginald Durham, Simone Brooks, Bill Contreras | 2026-09-08 |  |  |  | 0 | Move status to PBI Dev
RPT_02_All Jobs | November | NOT STARTED |  | Siddu | Shraddha |  | Shaunna Peters | 2026-09-10 |  |  |  | 0 | Move status to PBI Dev
RPT_02_BCP Service Appointment WOs | November | PBI Dev |  | Nick | Navya |  | Reginald Durham, Bill Contreras | 2026-10-13 |  |  |  | 0
RPT_02_Meter Order Tracking | November | PBI Dev |  | Nick | Shraddha |  | Oneil Lashley | 2026-10-06 |  |  |  | 0
RPT_02_Tech Availability, Utilization & Absence | November | DB Dev |  | Rupa | Shraddha |  | Reginald Durham, Bill Contreras, Bill Contreras |  |  |  |  | 0
RPT_02_Job Productivity | November | PBI Dev |  | Rupa | Navya |  | Laura Capasso, Michelle Fitten, Anthony Jenson |  |  |  |  | 0
RPT_02_Post Capacity Service Appointments | November | DB Dev |  | Greeta | Shraddha |  | Ryan Flaherty |  |  |  |  | 0
RPT_02_Check Estimate | November | PBI Dev |  | Greeta | Navya |  | Shaunna Peters | 2026-10-01 |  |  |  | 0
RPT_02_Service Appointments (5 sub reports) | November | DB Dev |  | Sree | Navya |  | Reginald Durham, Bill Contreras, Megan Piccarreto, Bryan Patterson, Bill Contreras |  |  |  |  | 0
RPT_02_Job Unit Count | November | NOT STARTED |  | Siddu | Shraddha |  | Laura Capasso, Michelle Fitten | 2026-10-02 |  |  |  | 0 | Move status to PBI Dev
Formulas:
Milestone = XLOOKUP([Month]&" Reports",DimRebaseline[Delivery Wave],DimRebaseline[Revised Committed Milestone],"")

## Data (hidden)
Report Name | Wave | Tracker Status | Blocked? | Bucket
RPT_02_CO Flue Warning Tag Control | July | Ready for Release in Prod | Yes – Blocked in Prod | Blocked in Prod
RPT_02_Warning Tag HEFPA | July | Ready for Release in Prod | Yes – Blocked in Prod | Blocked in Prod
RPT_02_Warning tag Printout | July | Ready for Release in Prod | Yes – Blocked in Prod | Blocked in Prod
RPT_02_Corrosion | July | Ready for Release in Prod | Yes – Blocked in Prod | Blocked in Prod
RPT_02_House Pipe Test Comment Control | July | Ready for Release in Prod | Yes – Blocked in Prod | Blocked in Prod
RPT_02_Required Regulator Inspection Performed Control | July | Ready for Release in Prod | Yes – Blocked in Prod | Blocked in Prod
RPT_02_Service Regulator Inspections | July | Ready for Release in Prod | Yes – Blocked in Prod | Blocked in Prod
RPT_02_Service Regulator Inspection Printout | July | Ready for Release in Prod | Yes – Blocked in Prod | Blocked in Prod
RPT_02_20 Year Regulator Inspection | July | Ready for Release in Prod | Yes – Blocked in Prod | Blocked in Prod
RPT_02_Fixed Factor | July | Ready for Release in Prod | Yes – Blocked in Prod | Blocked in Prod
RPT_02_Fixed Factor Printout | July | Ready for Release in Prod | Yes – Blocked in Prod | Blocked in Prod
RPT_02_Work Order Completion Printout | July | Ready for Release in Prod | Yes – Blocked in Prod | Blocked in Prod
RPT_02_GRO Control | July | Ready for Release in Prod | Yes – Blocked in Prod | Blocked in Prod
RPT_02_GRO Monitor | July | Ready for Release in Prod | Yes – Blocked in Prod | Blocked in Prod
RPT_02_Public Buildings Inspection | August | PBI Dev | Yes – needs PBI Dev to fix | Blocked - Build/QA
RPT_02_Investigate Wall Check and Service Check | August | Ready for Release in Prod | Yes – Blocked in Prod | Blocked in Prod
RPT_02_Cut Out Orders | August | Ready for Release in Prod | Yes – Blocked in Prod | Blocked in Prod
RPT_02_Gas Trouble | August | Ready for Release in Prod | Yes – Blocked in Prod | Blocked in Prod
RPT_02_Wall Check Control | August | Ready for Release in Prod | Yes – Blocked in Prod | Blocked in Prod
RPT_02_High Pressure Steel Inside Inspection | August | Ready for Release in Prod | Yes – Blocked in Prod | Blocked in Prod
RPT_02_Large Gas Outage | August | DPO Approval | No | DPO Approval
RPT_02_Fitting Work | August | Ready for Release in Prod | Yes – Blocked in Prod | Blocked in Prod
RPT_02_Field Collector Report | August | Ready for Release in Prod | Yes – Blocked in Prod | Blocked in Prod
RPT_02_Turn On for Non-Payment | August | DPO Approval | No | DPO Approval
RPT_02_Collector Payment Recap | August | Ready for Release in Prod | Yes – Blocked in Prod | Blocked in Prod
RPT_02_Incentive Management | August | Ready for Release in Prod | Yes – Blocked in Prod | Blocked in Prod
RPT_02_UTC Report | September | DPO Approval | No | DPO Approval
RPT_02_Adjacent Property Checks | September | DPO Approval | No | DPO Approval
RPT_02_High Bill Investigations | September | Ready for Release in Prod | Yes – Blocked in Prod | Blocked in Prod
RPT_02_Emergency Order Type | September | PBI Dev | Yes – other | Blocked - Build/QA
RPT_02_Cut Out Curb Box | September | DPO Approval | No | DPO Approval
RPT_02_New York Incident | September | Ready for Release in Prod | Yes – Blocked in Prod | Blocked in Prod
RPT_02_Outside Repeat Leaks | September | DPO Approval | Yes – needs DB Dev to fix | Blocked - Build/QA
RPT_02_Meter Change | September | DPO Approval | No | DPO Approval
RPT_02_Field Order Value | September | QA | No | QA
RPT_02_Same Day Reconnect | September | QA | No | QA
RPT_02_Site Specific Analysis | September | DPO Approval | No | DPO Approval
RPT_02_PSC Wire Down Response Time | September | PBI Dev | No | PBI Dev
RPT_02_Hazardous Above Ground Leak | September | DB Dev | No | DB Dev
RPT_02_AMI Contractor Completion Report | September | PBI Dev | No | PBI Dev
RPT_02_Collection Statistic | September | NOT STARTED | No | Not Started
RPT_02_First and Last Job | September | PBI Dev | Yes – other | Blocked - Build/QA
RPT_02_Rate Class | September | DPO Approval | No | DPO Approval
RPT_04_Leak Recheck Times | September | PBI Dev | No | PBI Dev
RPT_02_Service Resource Activity | October | QA |  | QA
RPT_02_Incomplete Service Appointments | October | PBI Dev |  | PBI Dev
RPT_02_Emergency Response Time Review Report | October | NOT STARTED |  | Not Started
RPT_02_Personal Injury and Shock Investigation | October | NOT STARTED |  | Not Started
RPT_02_Emergency Response Statistics | October | NOT STARTED |  | Not Started
RPT_02_Emergency Time Adjustments Log | October | PBI Dev | Yes – needs DB Dev to fix | Blocked - Build/QA
RPT_02_PSC Soft Off Report | October | PBI Dev |  | PBI Dev
RPT_02_Service Interruptions | October | NOT STARTED |  | Not Started
RPT_02_Duty to Inspect | October | NOT STARTED |  | Not Started
RPT_02_Service Appointment Life Cycle | October | DB Dev |  | DB Dev
RPT_02_PSC Inactive Account | October | PBI Dev |  | PBI Dev
RPT_02_Service Resource Performance | October | PBI Dev |  | PBI Dev
RPT_02_Emergency Leak Response Metric (6 sub reports) | October | NOT STARTED |  | Not Started
RPT_02_Fixed Factor Mismatch | November | NOT STARTED |  | Not Started
RPT_02_Light Up Orders | November | NOT STARTED |  | Not Started
RPT_02_Meter To Billing Report | November | NOT STARTED |  | Not Started
RPT_02_Install Meter Orders | November | NOT STARTED |  | Not Started
RPT_02_Non Emergency Orders | November | NOT STARTED |  | Not Started
RPT_02_Carbon Monoxide | November | NOT STARTED |  | Not Started
RPT_02_All Jobs | November | NOT STARTED |  | Not Started
RPT_02_BCP Service Appointment WOs | November | NOT STARTED |  | Not Started
RPT_02_Meter Order Tracking | November | NOT STARTED |  | Not Started
RPT_02_Tech Availability, Utilization & Absence | November | NOT STARTED |  | Not Started
RPT_02_Job Productivity | November | NOT STARTED |  | Not Started
RPT_02_Post Capacity Service Appointments | November | NOT STARTED |  | Not Started
RPT_02_Check Estimate | November | NOT STARTED |  | Not Started
RPT_02_Service Appointments (5 sub reports) | November | NOT STARTED |  | Not Started
RPT_02_Job Unit Count | November | NOT STARTED |  | Not Started

## Dashboard Lists (hidden)
Months | Statuses | People
All | All | All
July | Waiting for release | Bardia
August | Blocked in build/QA | Fetwi
September | DPO Approval | Geetha
October | QA | Greeta
November | PBI Dev | Kushal
| DB Dev | Michael
| Not started | Navya
| Released | Nick
Olu
Preety
Rupa
Sarath
Shraddha
Siddu
Siva
Sree