## README - Instructions (hidden)
GDM Tracker
One tracker, built so a Manager, Director, PM, QA tester, or PBI/DB developer can each get what they need without hunting for it.
QUICK GUIDE BY ROLE
Manager / Director - look at: Status Flag (col D, color-coded), Business Value Rank (col E) to see what matters most, Blocked At (col AG) for an instant 'blocked at [stage]' read - plus that stage's own date columns turn red too, so it's visible without even reading the text. Auto Rework Alert (col AM, red = something bounced backward), Confirmed Deployed? (col AB) for real proof of what's actually live. UAT/Prod URLs (cols AD-AE) are clickable.
The pipeline
NOT STARTED -> DB Dev -> PBI Dev -> QA -> DPO Approval -> RELEASED IN PROD. Current Status (col C) is a manual dropdown - set it to wherever the report actually is. Each stage (except Not Started and Released) has its own Status Assigned / Expected / Estimated / Actual date columns, except DPO Approval, which just has Status Assigned, Expected, and a Reviewer name (col AA) - there's no separate Actual for DPO Approval; use Confirmed Deployed? (col AB) instead once it's truly live.
Expected vs. Estimated - the one habit that matters most
Expected Completion Date is the original target - set it once, when a report enters that stage, and don't change it again. Estimated Completion Date is the one that moves - update it whenever a timeline shifts or a rework changes the plan. This way you always know both what was originally promised and what's realistically true now, without losing either. This is guidance, not an enforced rule - nothing is locked, it's on the honor system.
Status Flag (col D) - automatic
Reads Current Status plus that stage's own dates: 'No target set', 'Overdue', 'Review - planned start passed', 'On track', or 'Delivered'. Color-coded. Once a report is Released, Status Flag always just says 'Delivered' - a missing date never downgrades or flags a released report; Confirmed Deployed? is extra evidence on top, never a condition for the status itself.
Rework tracking - three layers now
Layer 1, fully automatic (cols AM-AN): 'Furthest Stage Reached' figures out from the dates already filled in how far a report has actually gotten. 'Auto Rework Alert' flags it in red if Current Status has been moved backward from that point - e.g. QA already has a date, but Current Status now says DB Dev. No logging required for this to work, ever. Layer 2, optional manual detail (Rework Log tab + cols AH-AK here): log who sent it back, why, the Defect/Jira Ticket if there is one, and the new expected fix date. Combined Delivery Data automatically pulls the most recent entry into 'Last Sent Back From', 'Last Defect/Jira Ticket', and 'Rework Est. Fix Date' - maintain history in one place, it shows up here without re-typing it. Rework Count tallies how many times each report appears on the log. Any stage can go back to any previous stage - it's not QA-specific. Layer 3 - Blocked with a known cause (cols AF-AH): Blocked? stays a simple Yes/No. If the block is just something stuck in its current stage (waiting on a normal review, etc.), leave 'Blocked - Needs Return To' blank - Blocked At will say 'Blocked at [stage]'. If a PREVIOUS stage actually needs to fix something (e.g. QA found a bug only DB Dev can resolve), set 'Blocked - Needs Return To' to that stage - Blocked At will instead say 'Blocked - needs DB Dev to fix', and that stage's own date columns light up red too, so whoever owns that stage sees it without reading anything. Rework Log also now has a live summary table (columns J-N) mirroring the same counts per report, so you can see them without switching tabs.
Date columns reject text - on purpose
Every date column only accepts real dates. Typing a status word or note into one gets rejected with a message pointing to Comments instead - this was added because the original source data had status words like 'Completed' sitting in date cells throughout, which made real reconciliation nearly impossible.
Chronology Check (col AO)
Automatic - flags a report if a later stage's target date is earlier than an earlier stage's, since that's usually a typo or wrong year. Does not compare DB Dev against PBI Dev to each other, since those run in parallel.
Reading the sheet at a glance
Each stage has its own header color and a matching colored left-border running down the sheet, so scrolling across reads as distinct sections rather than a wall of identical columns. When a report is blocked, the specific stage it's blocked at gets its own date columns highlighted red too - not just the Blocked At text column - so whoever owns that stage sees it immediately without reading anything. UAT Report URL and Production URL are real clickable links, not text to copy-paste.
Dropdowns and data entry
Domain, DB Developer, PBI Developer, PO, QA Tester, and Current Status are dropdowns sourced from the Data Validation tab - add a name or value there and it shows up automatically. Most are soft suggestions (you can type a new value directly), except Blocked? and Confirmed Deployed?, which are strict Yes/No only.
Migrated from the old source - what changed
This tracker replaces the old monthly Report Migration Timeline file. During migration: 8 QA target dates were corrected to match the true source values; Business Value Rank, UAT/Production URLs, DPO Approval Reviewer, QA Tester, and a real Confirmed Deployed signal (with actual dates recovered for 4 reports) were added since they existed in the old source but were never captured before; 5 specific historical blocker notes were preserved in Comments, tagged [Historical]. Everything else in the old source (generic 'ready for X' handoff notes, one-off 'Raw changes'/'Curated Change' notes, and uncertain '?' date markers) was reviewed and intentionally left behind as not worth carrying forward.
Duplicate Name Check (col AP)
Automatic - flags a report if its exact name appears more than once in the sheet, since that usually means a typo or an accidental duplicate entry rather than two genuinely different reports.
Find a Report tab
Pick any report name from the dropdown at the top and every key fact about it - status, dates, blockers, rework history, comments - appears below automatically. Useful for a quick check on one report without scrolling the full sheet.
It's now a real Excel Table
Combined Delivery Data is a genuine Excel Table now, not just a formatted range. Type a new report into the row right below the current last row, and every formula, dropdown, and conditional format on that row fills in automatically - no manual copying down required.
How Fact Table is generated
Fact Table is a computed snapshot built from Combined Delivery Data - NOT a live formula, and NOT recalculated by Excel. The dashboard app rebuilds it itself, in the browser, every time this file is uploaded there; the Fact Table tab in this workbook is a reference copy only, regenerated by whatever process last refreshed this file, and has no effect on the app. One row per stage a report has actually reached - not one row per report. Row count comes from Current Status (the manual dropdown), mapped to its position in the pipeline: NOT STARTED = 0 rows (a report still Not Started gets none - no placeholder), DB Dev = 1 row, PBI Dev = 2, QA = 3, DPO Approval = 4, RELEASED IN PROD = 5. This is the one place the app trusts Current Status as the source of truth, since that's how this tracker's own reference Fact Table has always been built. Each row's fields: - Domain, Report Name, DB Developers, PBI Developers, Schema, PO - copied straight from that report's row on Combined Delivery Data, same for every stage-row of that report. - Status - the stage name itself (DB Dev / PBI Dev / QA / DPO Approval / RELEASED IN PROD). - Expected Release Date - that stage's own Expected Completion Date if filled in (the real target once someone sets it), falling back to that SAME stage's own Actual Completion Date only when no Expected date exists yet (the common case for historical/migrated data, which usually only ever got an Actual recorded). Never a date carried over from a different stage. DPO Approval has no Actual column at all; RELEASED IN PROD uses Confirmed Deployed Date for both its Expected and Actual Release Date, so it's often blank until someone fills that in. - Actual Release Date - that stage's own Actual Completion Date, exactly as recorded, genuinely blank if not yet confirmed. Never guessed or backfilled, even when Expected Release Date has a value. - Status Start Date - chains from the previous stage-row's own Expected Release Date (so it inherits that same Expected-first fallback). The very first stage-row a report has has no Status Start Date, since there's no earlier stage to chain from. Why DPO Approval and RELEASED IN PROD rows often show blank dates: those two stages don't carry the same kind of confirmed date the earlier stages do. Rather than inventing a plausible-looking date, the app leaves these blank until a real one exists - Fact Table (and the live dashboard) is meant to be honest about what's actually known, not fully populated for its own sake.
One dashboard customization: the "PO" field actually shows QA Tester
By specific request, the live dashboard's Fact Table populates its "PO" field from this sheet's QA Tester column, not the real PO column - so the PO name shown in the app's drill-down table, Coming Your Way table, and Stage Progression Gaps table is actually the QA Tester's name. This is a deliberate app-side choice, not a data error: the real PO column here is untouched and still populated normally for everyone's own reference, and any other tool reading this file directly will see the real PO value. Only the dashboard app's own display substitutes QA Tester in that spot.

## Combined Delivery Data
Domain | Report Name | Current Status | Status Flag | Business Value Rank | PO | DB Developer | PBI Developer | QA Tester | Schema | Plan Delivery Date | Plan Delivery Month | DB Dev Status Assigned Date | DB Dev Expected Completion Date | DB Dev Estimated Completion Date | DB Dev Actual Completion Date | PBI Dev Status Assigned Date | PBI Dev Expected Completion Date | PBI Dev Estimated Completion Date | PBI Dev Actual Completion Date | QA Status Assigned Date | QA Expected Completion Date | QA Estimated Completion Date | QA Actual Completion Date | DPO Approval Status Assigned Date | DPO Approval Expected Completion Date | DPO Approval Reviewer | Confirmed Deployed? | Confirmed Deployed Date | UAT Report URL | Production URL | Blocked? | Blocked - Needs Return To | Blocked At | Rework Count | Last Sent Back From | Rework Est. Fix Date | Last Defect/Jira Ticket | Furthest Stage Reached | Auto Rework Alert | Chronology Check | Duplicate Name Check | Comments | _Last Rework Row
Leaks | RPT_04_Active Leaks | RELEASED IN PROD | Delivered | 1 |  | Fetwi | Sarath | Preety |  | 2026-04-30 | April |  |  |  | 2026-04-03 |  |  |  | 2026-04-02 |  |  |  | 2026-04-10 |  |  | Kelvin Hu | Yes |  | https://app.powerbi.com/groups/me/apps/eedba83d-be9a-45f9-9504-7bfa41e6051a/reports/62307ec4-3158-4457-8dcc-4acc2150cdc3/ccfe9e7f0a40d49acb85?experience=power-bi | https://app.powerbi.com/groups/me/apps/2c7180b1-0d3d-45be-979e-f7dc86b3557d/reports/8cd4a21d-3abe-4e55-a99e-3af846ab1c67/ccfe9e7f0a40d49acb85?ctid=f98a6a53-25f3-4212-901c-c7787fcd3495&experience=power-bi | No |  |  | 0 |  |  |  | NOT STARTED | No |  |  | [Historical, April 2026]: QA found an issue - date calendar dimension broken. Fetwi assigned to fix. | 0
Leaks | RPT_04_Count of Active Leaks On Hand | RELEASED IN PROD | Delivered | 2 |  | Fetwi | Sarath | Preety |  | 2026-04-30 | April |  |  |  | 2026-04-03 |  |  |  | 2026-04-02 |  |  |  | 2026-04-10 |  |  | Kelvin Hu | Yes |  | https://app.powerbi.com/groups/me/apps/eedba83d-be9a-45f9-9504-7bfa41e6051a/reports/c0b3f0ae-dedd-485b-8bbc-aa0e5f3fd077/24a66431d0637282f4b7?experience=power-bi | https://app.powerbi.com/groups/me/apps/2c7180b1-0d3d-45be-979e-f7dc86b3557d/reports/5ffd546f-ad77-4a7f-8e6d-94dc08bef796/24a66431d0637282f4b7?ctid=f98a6a53-25f3-4212-901c-c7787fcd3495&experience=power-bi | No |  |  | 0 |  |  |  | NOT STARTED | No |  |  | [Historical, April 2026]: QA found an issue - date calendar dimension broken. Fetwi assigned to fix. | 0
Leaks | RPT_04_Leak Scheduling | RELEASED IN PROD | Delivered | 4 |  | Sreevarsha | Sarath | Preety |  | 2026-04-30 | April |  |  |  | 2026-04-03 |  |  |  | 2026-04-08 |  |  |  | 2026-04-10 |  |  | Kelvin Hu |  |  |  |  | No |  |  | 0 |  |  |  | NOT STARTED | No |  |  |  | 0
Leaks | RPT_04_Leak Days Remaining | RELEASED IN PROD | Delivered | 5 |  | Siva | Navya | Preety |  | 2026-04-30 | April |  |  |  | 2026-04-03 |  |  |  | 2026-04-14 |  |  |  | 2026-04-10 |  |  | Kelvin Hu | Yes |  | https://app.powerbi.com/groups/me/apps/eedba83d-be9a-45f9-9504-7bfa41e6051a/reports/8b9ae445-3a30-4ae6-a3fa-7a6d8e7ef349/d97da6159d0c87677529?experience=power-bi | https://app.powerbi.com/groups/me/apps/2c7180b1-0d3d-45be-979e-f7dc86b3557d/reports/848ce65a-4e47-422b-aae5-7ea9e7d68a5f/d97da6159d0c87677529?ctid=f98a6a53-25f3-4212-901c-c7787fcd3495&experience=power-bi | No |  |  | 0 |  |  |  | NOT STARTED | No |  |  | 16/04 - Testing completed in QA and created defect https://jira.prod.nationalgrid.com/browse/GDMP-2186; ETA -04/24 | 0
Leaks | RPT_04_Cleared Leaks | RELEASED IN PROD | Delivered | 3 |  | Sreevarsha | Sarath | Preety |  | 2026-04-30 | April |  |  |  | 2026-04-03 |  |  |  | 2026-04-08 |  |  |  | 2026-04-10 |  |  | Kelvin Hu | Yes |  | https://app.powerbi.com/groups/me/apps/eedba83d-be9a-45f9-9504-7bfa41e6051a/reports/938a9ba1-8138-440e-842a-d9a679933d8c/44bb4fce98fafb2cace2?experience=power-bi | https://app.powerbi.com/groups/me/apps/2c7180b1-0d3d-45be-979e-f7dc86b3557d/reports/677c6418-6db8-4ebf-9323-65be4cb2c960/ea184ec020032ecbdd43?ctid=f98a6a53-25f3-4212-901c-c7787fcd3495&experience=power-bi | No |  |  | 0 |  |  |  | NOT STARTED | No |  |  | [Historical, April 2026]: L_GRO_NUMBER columns had an issue in QA - DB team assigned to fix. | 0
Leaks | RPT_04_Leaks Repaired Detail | RELEASED IN PROD | Delivered | 6 |  | Rupa | Navya | Preety |  | 2026-04-30 | April |  |  |  | 2026-04-03 |  |  |  | 2026-04-14 |  |  |  | 2026-04-10 |  |  | Kelvin Hu | Yes |  | https://app.powerbi.com/groups/me/apps/eedba83d-be9a-45f9-9504-7bfa41e6051a/reports/cbaf2155-2cf3-4377-8af2-7e07a896e887/ea184ec020032ecbdd43?experience=power-bi | https://app.powerbi.com/groups/me/apps/2c7180b1-0d3d-45be-979e-f7dc86b3557d/reports/9c6d5e21-4e57-4a64-9973-61ff3717468e/ea184ec020032ecbdd43?ctid=f98a6a53-25f3-4212-901c-c7787fcd3495&experience=power-bi | No |  |  | 0 |  |  |  | NOT STARTED | No |  |  | 21/4 Testing completed in QA and defect raised https://jira.prod.nationalgrid.com/browse/GDMP-2190; Report ready for testing 04/23/2026 | 0
Leaks | RPT_04_Leaks Aging | RELEASED IN PROD | Delivered | 7 |  | Sreevarsha | Navya | Preety |  | 2026-04-30 | April |  |  |  | 2026-04-10 |  |  |  | 2026-04-14 |  |  |  | 2026-04-10 |  |  | Kelvin Hu | Yes |  | https://app.powerbi.com/groups/me/apps/eedba83d-be9a-45f9-9504-7bfa41e6051a/reports/383c1502-9c3c-4fa0-a321-321cfed3b4a1/ReportSection1e63b8fbeb9ea54074e1?experience=power-bi | https://app.powerbi.com/groups/me/apps/2c7180b1-0d3d-45be-979e-f7dc86b3557d/reports/b7f15195-22d6-4ac4-8982-a8cadb215cbf/ReportSection1e63b8fbeb9ea54074e1?ctid=f98a6a53-25f3-4212-901c-c7787fcd3495&experience=power-bi | No |  |  | 0 |  |  |  | NOT STARTED | No |  |  |  | 0
Leaks | RPT_04_Prior Leak Readings | RELEASED IN PROD | Delivered | 9 |  | Siddu | Navya | Preety |  | 2026-04-30 | April |  |  |  | 2026-04-10 |  |  |  | 2026-04-14 |  |  |  | 2026-04-10 |  |  | Kelvin Hu | Yes |  | https://app.powerbi.com/groups/me/apps/7767030c-f4c8-4488-b3cb-36a860cb6ff2/reports/acc74ccc-08b7-420d-b64e-5e4d786ac711/ReportSection6d915001f68ea4805272?experience=power-bi | https://app.powerbi.com/groups/me/apps/5b29b0dd-a398-4801-84ce-f3a7d8435827/reports/5a06a5bd-88fb-4024-8841-570da23785ad/ReportSection6d915001f68ea4805272?ctid=f98a6a53-25f3-4212-901c-c7787fcd3495&experience=power-bi | No |  |  | 0 |  |  |  | NOT STARTED | No |  |  |  | 0
Leaks | RSS_04_Leak Grade Change History | RELEASED IN PROD | Delivered | 8 |  | Siva | Navya | Preety |  | 2026-04-30 | April |  |  |  | 2026-04-15 |  |  |  | 2026-04-14 |  |  |  | 2026-04-10 |  |  | Kelvin Hu | Yes |  | https://app.powerbi.com/groups/me/apps/7767030c-f4c8-4488-b3cb-36a860cb6ff2/reports/6fe40f7b-3dfe-45ee-9f81-cb977321242d/9d7e292e8fb40cfee194?experience=power-bi | https://app.powerbi.com/groups/me/apps/5b29b0dd-a398-4801-84ce-f3a7d8435827/reports/4268caf5-dcbd-4b00-8518-baf8239fff69/9d7e292e8fb40cfee194?experience=power-bi | No |  |  | 0 |  |  |  | NOT STARTED | No |  |  | 23/4 - Testing completed in QA and defect created https://jira.prod.nationalgrid.com/browse/GDMP-2227; Report is ready for testing 04/23/2026 | 0
Leaks | RPT_04_Surveillances With Zero Readings | RELEASED IN PROD | Delivered | 10 |  | Sreevarsha | Navya | Kelvin |  | 2026-05-31 | May | [7 empty] | 2026-04-27 |  |  |  | 2026-04-27 |  |  | Kelvin Hu | Yes |  | https://app.powerbi.com/groups/me/apps/eedba83d-be9a-45f9-9504-7bfa41e6051a/reports/743b79eb-5470-4cd4-ad54-81eb3b409ae8/ea184ec020032ecbdd43?ctid=f98a6a53-25f3-4212-901c-c7787fcd3495&experience=power-bi | https://app.powerbi.com/groups/me/apps/2c7180b1-0d3d-45be-979e-f7dc86b3557d/reports/c887cd5e-9172-4de3-921e-2c0edd2533bc/ea184ec020032ecbdd43?experience=power-bi | No |  |  | 0 |  |  |  | NOT STARTED | No |  |  |  | 0
Leaks | RPT_04 High Emitter leaks | RELEASED IN PROD | Delivered | 11 |  | Sreevarsha | Navya | Preety |  | 2026-05-31 | May | [7 empty] | 2026-04-29 |  |  |  | 2026-04-29 |  |  | Kelvin Hu | Yes |  | https://app.powerbi.com/groups/me/apps/61b18507-2848-49b9-aacc-32c49ffe1e0b/reports/a44e7124-b1d0-4a09-a5d1-157e2043ba8e/ea184ec020032ecbdd43?ctid=f98a6a53-25f3-4212-901c-c7787fcd3495&experience=power-bi | https://app.powerbi.com/groups/me/apps/93d01997-58e0-48d8-bcca-ad8377094e64/reports/6d6fe558-e5d6-4a4b-b6fb-8a5f8735d1df/ea184ec020032ecbdd43?experience=power-bi | No |  |  | 0 |  |  |  | NOT STARTED | No |  |  | 05/05- defect raised https://jira.prod.nationalgrid.com/browse/GDMP-2230 | 0
Leaks | RPT_04_School Zone Leaks Without Repair | RELEASED IN PROD | Delivered | 12 |  | Sreevarsha | Sarath | Preety |  | 2026-05-31 | May | [7 empty] | 2026-05-19 |  |  |  | 2026-05-19 |  |  | Kelvin Hu | Yes |  | https://app.powerbi.com/groups/me/apps/eedba83d-be9a-45f9-9504-7bfa41e6051a/reports/0f3b2c1d-09ad-45db-9786-31e8c9401bc4/ReportSectionda782bb6769340acca9d?experience=power-bi | https://app.powerbi.com/groups/me/apps/2c7180b1-0d3d-45be-979e-f7dc86b3557d/reports/5e101b4d-8b08-431a-8b3a-04aafc85f314/ReportSection1e63b8fbeb9ea54074e1?experience=power-bi | No |  |  | 0 |  |  |  | NOT STARTED | No |  |  |  | 0
Leaks | RPT_04_PSC Quarterly Leak | RELEASED IN PROD | Delivered | 13 |  | Geetha | Sarath | Kelvin |  | 2026-05-31 | May | [7 empty] | 2026-06-02 |  |  |  | 2026-06-02 |  |  | Kelvin Hu | Yes | 2026-06-11 |  | https://app.powerbi.com/groups/me/apps/93d01997-58e0-48d8-bcca-ad8377094e64/reports/bda83ba5-3e9d-4f8d-9496-bf14e91f7b20/ccfe9e7f0a40d49acb85?ctid=f98a6a53-25f3-4212-901c-c7787fcd3495&experience=power-bi | No |  |  | 0 |  |  |  | NOT STARTED | No |  |  |  | 0
Leaks | RPT_04_Rechecks Completed less than 14 days | RELEASED IN PROD | Delivered | 14 |  | Rupa | Shraddha | Preety |  | 2026-05-31 | May | [7 empty] | 2026-04-22 |  |  |  | 2026-04-22 |  |  | Kelvin Hu | Yes |  | https://app.powerbi.com/groups/me/apps/7767030c-f4c8-4488-b3cb-36a860cb6ff2/reports/de1ad11f-021b-4cc1-b465-67efd542031c/3122b8024291693794eb?ctid=f98a6a53-25f3-4212-901c-c7787fcd3495&experience=power-bi | https://app.powerbi.com/groups/me/apps/5b29b0dd-a398-4801-84ce-f3a7d8435827/reports/0e063b20-0b38-4000-b436-fcbec11daa46/3122b8024291693794eb?experience=power-bi | No |  |  | 0 |  |  |  | NOT STARTED | No |  |  |  | 0
Leaks | RPT_04_SEI Leak Activity | RELEASED IN PROD | Delivered | 15 |  | Siva | Shraddha | Preety |  | 2026-05-31 | May | [7 empty] | 2026-04-27 |  |  |  | 2026-04-27 |  |  | Kelvin Hu | Yes |  | https://app.powerbi.com/groups/me/apps/7767030c-f4c8-4488-b3cb-36a860cb6ff2/reports/c76693f4-bab2-46a1-ab2a-16752d7664fd/ea184ec020032ecbdd43?experience=power-bi | https://app.powerbi.com/groups/me/apps/5b29b0dd-a398-4801-84ce-f3a7d8435827/reports/9d9f5721-feb1-4ed3-91fd-18bc33ef38f1/ea184ec020032ecbdd43?experience=power-bi | No |  |  | 0 |  |  |  | NOT STARTED | No |  |  |  | 0
Leaks | RPT_04_CMS Leak Productivity | RELEASED IN PROD | Delivered | 16 |  | Siddu | Navya | Preety |  | 2026-05-31 | May | [7 empty] | 2026-05-05 |  |  |  | 2026-05-05 |  |  | Kelvin Hu | Yes |  | https://app.powerbi.com/groups/me/apps/eedba83d-be9a-45f9-9504-7bfa41e6051a/reports/3440832e-c72e-45f2-b154-f6b1d66314fc/51a6cefeab19522827a6?experience=power-bi | https://app.powerbi.com/groups/me/apps/2c7180b1-0d3d-45be-979e-f7dc86b3557d/reports/18e31a06-f1af-4965-ad46-5a507f24ed56/51a6cefeab19522827a6?experience=power-bi | No |  |  | 0 |  |  |  | NOT STARTED | No |  |  |  | 0
Leaks | RPT_04_Main Break Corrosion and Leak Cluster | RELEASED IN PROD | Delivered | 17 |  | Siddu | Sarath | Kelvin |  | 2026-05-31 | May | [7 empty] | 2026-06-02 |  |  |  | 2026-06-06 |  |  | Kelvin Hu |  |  | https://app.powerbi.com/groups/me/apps/eedba83d-be9a-45f9-9504-7bfa41e6051a/reports/efc0a204-1a7b-4be6-8334-c7582c9093b8/ReportSection81bc1123208781ca563a?experience=power-bi |  | No |  |  | 0 |  |  |  | NOT STARTED | No |  |  |  | 0
Leaks | RPT_04_Leak Summary Status | RELEASED IN PROD | Delivered | 18 |  | Fetwi | Navya | Kelvin |  | 2026-05-31 | May | [7 empty] | 2026-05-01 |  |  |  | 2026-06-02 |  |  | Kelvin Hu | Yes | 2026-06-11 | https://app.powerbi.com/groups/me/apps/7767030c-f4c8-4488-b3cb-36a860cb6ff2/reports/184a9cdc-83f5-40b0-940d-d901ad9fb404/ReportSection6d915001f68ea4805272?ctid=f98a6a53-25f3-4212-901c-c7787fcd3495&experience=power-bi | https://app.powerbi.com/groups/me/apps/5b29b0dd-a398-4801-84ce-f3a7d8435827/reports/f7af2903-2d63-497e-b262-100f5a3b500b/ReportSection6d915001f68ea4805272?ctid=f98a6a53-25f3-4212-901c-c7787fcd3495&experience=power-bi | No |  |  | 0 |  |  |  | NOT STARTED | No |  |  |  | 0
Leaks | RPT_04_PSC Leak Printout | RELEASED IN PROD | Delivered | 19 |  | Fetwi | Shraddha | Preety |  | 2026-05-31 | May |  |  |  | 2026-06-02 |  |  |  | 2026-06-05 |  |  |  | 2026-06-02 |  |  | Kelvin Hu | Yes | 2026-06-19 | https://app.powerbi.com/groups/me/apps/61b18507-2848-49b9-aacc-32c49ffe1e0b/rdlreports/84ee7713-075e-496c-8610-43022c6a55ab?ctid=f98a6a53-25f3-4212-901c-c7787fcd3495&experience=power-bi |  | No |  |  | 0 |  |  |  | NOT STARTED | No |  |  | [Historical, May/June 2026]: Fetwi was investigating a slowness issue in this report. | 0
Leaks | RPT_04_Leak Control Report | RELEASED IN PROD | Delivered | 20 |  | Geetha | Navya | Preety |  | 2026-06-30 | June |  |  |  | 2026-05-06 |  |  |  | 2026-06-10 |  |  |  | 2026-06-22 | [7 empty] | No |  |  | 0 |  |  |  | NOT STARTED | No |  |  |  | 0
Leaks | RPT_04_Leak Life Cycle | RELEASED IN PROD | Delivered | 21 |  | Geetha | Shraddha | Preety |  | 2026-06-30 | June |  |  |  | 2026-05-20 |  |  |  | 2026-06-09 |  |  |  | 2026-06-25 | [7 empty] | No |  |  | 0 |  |  |  | NOT STARTED | No |  |  | [Historical, June 2026]: Waiting on Kelvin's approval to deploy to UAT. | 0
Leaks | RPT_04_Leak Life Cycle Legacy LMS LI | RELEASED IN PROD | Delivered | 22 |  | Fetwi | Navya | Preety |  | 2026-06-30 | June |  |  |  | 2026-05-26 |  |  |  | 2026-06-10 |  |  |  | 2026-06-25 | [7 empty] | No |  |  | 0 |  |  |  | NOT STARTED | No |  |  |  | 0
Leaks | RPT_04_Leak Increase Reads | RELEASED IN PROD | Delivered | 23 |  | Fetwi | Navya | Preety |  | 2026-06-30 | June |  |  |  | 2026-05-23 |  |  |  | 2026-05-11 |  |  |  | 2026-05-12 |  |  |  | Yes | 2026-06-11 | https://app.powerbi.com/groups/me/apps/eedba83d-be9a-45f9-9504-7bfa41e6051a/reports/a410b442-fd2f-43d1-a053-40f2e4966d4d/ea184ec020032ecbdd43?ctid=f98a6a53-25f3-4212-901c-c7787fcd3495&experience=power-bi | https://app.powerbi.com/groups/me/apps/2c7180b1-0d3d-45be-979e-f7dc86b3557d/reports/1cec238a-ce10-4ed5-8e56-50efa21bb327/ea184ec020032ecbdd43?ctid=f98a6a53-25f3-4212-901c-c7787fcd3495&experience=power-bi | No |  |  | 0 |  |  |  | NOT STARTED | No |  |  |  | 0
Leaks | Leak 360 Dashboard | QA | No target set | 24 |  | Siva | Sarath | Kelvin |  | 2026-06-30 | June |  |  |  | 2026-05-20 |  | 2026-07-24 |  | 2026-06-13 |  |  |  | 2026-06-15 | [7 empty] | No |  |  | 0 |  |  |  | PBI Dev | No |  |  | [Source confirms QA complete but gives no exact date - using QA Expected date as the closest evidence-backed proxy] | 0
Leaks | RPT_04_Leak Recheck Control | RELEASED IN PROD | Delivered | 25 |  | Siva | Shraddha | Preety |  | 2026-06-30 | June |  |  |  | 2026-05-20 |  |  |  | 2026-05-22 |  |  |  | 2026-07-01 | [7 empty] | No |  |  | 0 |  |  |  | NOT STARTED | No |  |  | [Source confirms QA complete but gives no exact date - using QA Expected date as the closest evidence-backed proxy] | 0
Leaks | RPT_04_Main_Replacement Report | RELEASED IN PROD | Delivered | 26 |  | Sree | Navya | Kelvin |  | 2026-06-30 | June |  |  |  | 2026-05-27 |  |  |  | 2026-06-18 |  |  |  | 2026-06-23 | [5 empty] | https://app.powerbi.com/Redirect?action=OpenApp&appId=eedba83d-be9a-45f9-9504-7bfa41e6051a&ctid=f98a6a53-25f3-4212-901c-c7787fcd3495&experience=power-bi | https://app.powerbi.com/groups/me/apps/2c7180b1-0d3d-45be-979e-f7dc86b3557d/reports/3a63d51e-dbb3-4d03-8e38-924376751299/3122b8024291693794eb?ctid=f98a6a53-25f3-4212-901c-c7787fcd3495&experience=power-bi | No |  |  | 0 |  |  |  | NOT STARTED | No |  |  |  | 0
Leaks | New Report: Leak Repair Exception | RELEASED IN PROD | Delivered | 27 |  | Geetha | Shraddha | Kelvin |  | 2026-06-30 | June |  |  |  | 2026-05-26 |  |  |  | 2026-06-16 |  |  |  | 2026-06-16 |  |  |  | Yes | 2026-06-19 | https://app.powerbi.com/groups/me/apps/eedba83d-be9a-45f9-9504-7bfa41e6051a/reports/f32957e8-b826-44b0-8c00-67ff417ed57e/e94cbcb8509576e1c578?ctid=f98a6a53-25f3-4212-901c-c7787fcd3495&experience=power-bi |  | No |  |  | 0 |  |  |  | NOT STARTED | No |  |  |  | 0
Leaks | New Report: (Leak reading sample point mismatch ) Creating a new report that... | RELEASED IN PROD | Delivered |  |  | Siddu | Shraddha |  |  | 2026-06-30 | June |  |  |  | 2026-05-27 |  |  |  | 2026-06-22 |  |  |  | 2026-06-24 | [7 empty] | No |  |  | 0 |  |  |  | NOT STARTED | No |  |  | [QA Actual date recovered from source text: "6/24/2026; QA Completed. Waiting for the view to be deployed to UAT"] | 0
CMS | RPT_02_CO Flue Warning Tag Control | QA | No target set | 1 | Kushal | Rupa | Navya | Kushal |  | 2026-07-31 | July | [7 empty] | 2026-07-10 |  |  |  | 2026-07-20 | [7 empty] | Yes |  | Blocked at QA | 0 |  |  |  | NOT STARTED | No |  |  | Blocked with https://jira.prod.nationalgrid.com/browse/GDMP-2875 | 0
CMS | RPT_02_Warning Tag HEFPA | QA | No target set | 2 | Kushal | Sree | Shraddha | Kushal |  | 2026-07-31 | July | [7 empty] | 2026-07-15 |  |  |  | 2026-07-20 | [7 empty] | No |  |  | 0 |  |  |  | NOT STARTED | No |  |  | Count Msimatches Found between ODS and GDM [QA note, 07/2026]: Observing count mismatch, Sree looking into it (07/22/2026). | 0
CMS | RPT_02_Warning tag Printout | QA | No target set | 3 | Kushal | Sree | Shraddha | Kushal |  | 2026-07-31 | July | [7 empty] | 2026-07-22 |  |  |  | 2026-07-20 | [7 empty] | No |  |  | 0 |  |  |  | NOT STARTED | No |  |  | Note: this report's stage dates are not in chronological order in the source tracker (e.g. a later stage dated before an earlier one) - please verify with the assigned developer. [QA note, 07/2026]: Development is completed, waiting for the view to be deployed to QA. | 0
CMS | RPT_02_Corrosion | QA | No target set | 4 | Kushal | Siva | Sarath | Kushal |  | 2026-07-31 | July | [7 empty] | 2026-07-24 |  |  |  | 2026-07-20 | [7 empty] | No |  |  | 0 |  |  |  | NOT STARTED | No |  |  | Note: this report's stage dates are not in chronological order in the source tracker (e.g. a later stage dated before an earlier one) - please verify with the assigned developer. | 0
CMS | RPT_02_House Pipe Test Comment Control | QA | No target set | 5 | Kushal | Geetha | Shraddha | Preety |  | 2026-07-31 | July | [7 empty] | 2026-07-13 |  |  |  | 2026-07-22 | [7 empty] | Yes |  | Blocked at QA | 0 |  |  |  | NOT STARTED | No |  |  | Blocked with https://jira.prod.nationalgrid.com/browse/GDMP-2876 , 17/7 - view don't have data in QA [QA note, 07/2026]: Ready for UAT review. [QA Actual date recovered from source text: "22/7 -Completed"] | 0
CMS | RPT_02_Required Regulator Inspection Performed Control | DB Dev | No target set | 6 | Bardia | Siddu | Navya | Bardia |  | 2026-07-31 | July | [7 empty] | 2026-07-14 |  |  |  | 2026-07-20 | [7 empty] | No |  |  | 1 | QA | 0 | 0 | NOT STARTED | No |  |  | GDM_RPT.VW_REQUIRED_REGULATOR_INSPECTIONS_PERFORMED_CONTROL [QA note, 07/2026]: Defects found and sent back for development. | 3
CMS | RPT_02_Service Regulator Inspections | DB Dev | No target set | 7 | Bardia | Sree | Sarath | Bardia |  | 2026-07-31 | July | [7 empty] | 2026-07-18 |  |  |  | 2026-07-20 | [7 empty] | No |  |  | 1 | QA | 0 | 0 | NOT STARTED | No |  |  | select * from DEV_GDM_DEV_DB.GDM_RPT.VW_SERVICE_REGULATOR_INSPECTIONS [QA note, 07/2026]: Defects found and sent back for development. | 4
CMS | RPT_02_Service Regulator Inspection Printout | QA | No target set | 8 | Bardia | Sree | Sarath | Bardia |  | 2026-07-31 | July | [7 empty] | 2026-07-18 |  |  |  | 2026-07-20 | [7 empty] | No |  |  | 0 |  |  |  | NOT STARTED | No |  |  | this has a dependency on dt_wospecattributes , 15 attributes need to be addted eg NG_REGINVLVREM | 0
CMS | RPT_02_20 Year Regulator Inspection | QA | No target set | 9 | Bardia | Siddu | Navya | Bardia |  | 2026-07-31 | July | [7 empty] | 2026-07-17 |  |  |  | 2026-07-20 | [7 empty] | No |  |  | 0 |  |  |  | NOT STARTED | No |  |  | GDM_RPT.VW_20_YEAR_REGULATOR_INSPECTION_COMPLETED, GDM_RPT.VW_20_YEAR_REGULATOR_INSPECTION_MANDATED | 0
CMS | RPT_02_Fixed Factor | QA | No target set | 10,12 | Bardia | Nick | Navya | Bardia |  | 2026-07-31 | July | [7 empty] | 2026-07-21 |  |  |  | 2026-07-20 | [7 empty] | No |  |  | 0 |  |  |  | NOT STARTED | No |  |  |  | 0
CMS | RPT_02_Fixed Factor Printout | QA | No target set | 11 | Bardia | Nick | Shraddha | Preety |  | 2026-07-31 | July | [7 empty] | 2026-07-22 |  |  |  | 2026-07-20 | [7 empty] | No |  |  | 0 |  |  |  | NOT STARTED | No |  |  | [QA note, 07/2026]: Development is completed, QA validation in progress. | 0
CMS | RPT_02_Work Order Completion Printout | QA | No target set | 13 | Kushal | Rupa | Sarath | Preety |  | 2026-07-31 | July | [7 empty] | 2026-07-23 |  |  |  | 2026-07-20 | [7 empty] | No |  |  | 0 |  |  |  | NOT STARTED | No |  |  |  | 0
CMS | RPT_02_GRO Control | QA | No target set | 14 | Kushal | Siva | Navya | Preety |  | 2026-07-31 | July | [7 empty] | 2026-07-22 |  |  |  | 2026-07-20 | [7 empty] | No |  |  | 0 |  |  |  | NOT STARTED | No |  |  |  | 0
CMS | RPT_02_GRO Monitor | QA | No target set | 15 | Bardia | Rupa | Shraddha | Preety |  | 2026-07-31 | July | [7 empty] | 2026-07-22 |  |  |  | 2026-07-27 | [7 empty] | No |  |  | 0 |  |  |  | NOT STARTED | No |  |  |  | 0
CMS | RPT_02_Public Buildings Inspection | QA | No target set | 16,17,24, 28 |  | Geetha |  |  |  | 2026-08-31 | August | [19 empty] | No |  |  | 0 |  |  |  | NOT STARTED | No |  |  |  | 0
CMS | RPT_02_Investigate Wall Check and Service Check | NOT STARTED | On track | 18 |  | Siva |  |  |  | 2026-08-31 | August | [19 empty] | No |  |  | 0 |  |  |  | NOT STARTED | No |  |  |  | 0
CMS | RPT_02_Cut Out Orders | NOT STARTED | On track | 19 |  | Fetwi |  |  |  | 2026-08-31 | August | [19 empty] | No |  |  | 0 |  |  |  | NOT STARTED | No |  |  |  | 0
CMS | RPT_02_Gas Trouble | QA | No target set | 20 |  | Siddu |  |  |  | 2026-08-31 | August | [19 empty] | No |  |  | 0 |  |  |  | NOT STARTED | No |  |  |  | 0
CMS | RPT_02_Wall Check Control | NOT STARTED | On track | 21 |  | Nick |  |  |  | 2026-08-31 | August | [19 empty] | No |  |  | 0 |  |  |  | NOT STARTED | No |  |  |  | 0
CMS | RPT_02_High Pressure Steel Inside Inspection | NOT STARTED | On track | 22 |  | Siva |  |  |  | 2026-08-31 | August | [19 empty] | No |  |  | 0 |  |  |  | NOT STARTED | No |  |  |  | 0
CMS | RPT_02_Large Gas Outage | NOT STARTED | On track | 23 |  | Nick |  |  |  | 2026-08-31 | August | [19 empty] | No |  |  | 0 |  |  |  | NOT STARTED | No |  |  |  | 0
CMS | RPT_02_Fitting Work | NOT STARTED | On track | 25 |  | Fetwi |  |  |  | 2026-08-31 | August | [19 empty] | No |  |  | 0 |  |  |  | NOT STARTED | No |  |  |  | 0
CMS | RPT_02_Field Collector Report | NOT STARTED | On track | 26 |  | Siddu |  |  |  | 2026-08-31 | August | [19 empty] | No |  |  | 0 |  |  |  | NOT STARTED | No |  |  |  | 0
CMS | RPT_02_Turn On for Non-Payment | NOT STARTED | On track | 27 |  | Sree |  |  |  | 2026-08-31 | August | [19 empty] | No |  |  | 0 |  |  |  | NOT STARTED | No |  |  |  | 0
CMS | RPT_02_Collector Payment Recap | NOT STARTED | On track | 29 |  | Rupa |  |  |  | 2026-08-31 | August | [19 empty] | No |  |  | 0 |  |  |  | NOT STARTED | No |  |  |  | 0
CMS | RPT_02_Incentive Management | NOT STARTED | On track | 30 | [5 empty] | 2026-08-31 | August | [19 empty] | No |  |  | 0 |  |  |  | NOT STARTED | No |  |  |  | 0
CMS | RPT_02_UTC Report | NOT STARTED | On track | 31 | [5 empty] | 2026-09-30 | September | [19 empty] | No |  |  | 0 |  |  |  | NOT STARTED | No |  |  |  | 0
CMS | RPT_02_Adjacent Property Checks | NOT STARTED | On track | 32 | [5 empty] | 2026-09-30 | September | [19 empty] | No |  |  | 0 |  |  |  | NOT STARTED | No |  |  |  | 0
CMS | RPT_02_High Bill Investigations | NOT STARTED | On track | 33 | [5 empty] | 2026-09-30 | September | [19 empty] | No |  |  | 0 |  |  |  | NOT STARTED | No |  |  |  | 0
CMS | RPT_02_Emergency Order Type | NOT STARTED | On track | 34 | [5 empty] | 2026-09-30 | September | [19 empty] | No |  |  | 0 |  |  |  | NOT STARTED | No |  |  |  | 0
CMS | RPT_02_Cut Out Curb Box | NOT STARTED | On track | 35 | [5 empty] | 2026-09-30 | September | [19 empty] | No |  |  | 0 |  |  |  | NOT STARTED | No |  |  |  | 0
CMS | RPT_02_New York Incident | NOT STARTED | On track | 36 | [5 empty] | 2026-09-30 | September | [19 empty] | No |  |  | 0 |  |  |  | NOT STARTED | No |  |  |  | 0
CMS | RPT_02_Outside Repeat Leaks | NOT STARTED | On track | 37 | [5 empty] | 2026-09-30 | September | [19 empty] | No |  |  | 0 |  |  |  | NOT STARTED | No |  |  |  | 0
CMS | RPT_02_Meter Change | NOT STARTED | On track | 38 | [5 empty] | 2026-09-30 | September | [19 empty] | No |  |  | 0 |  |  |  | NOT STARTED | No |  |  |  | 0
CMS | RPT_02_Field Order Value | NOT STARTED | On track | 39 | [5 empty] | 2026-09-30 | September | [19 empty] | No |  |  | 0 |  |  |  | NOT STARTED | No |  |  |  | 0
CMS | RPT_02_Same Day Reconnect | NOT STARTED | On track | 40 | [5 empty] | 2026-09-30 | September | [19 empty] | No |  |  | 0 |  |  |  | NOT STARTED | No |  |  |  | 0
CMS | RPT_02_Site Specific Analysis | NOT STARTED | On track | 41 | [5 empty] | 2026-09-30 | September | [19 empty] | No |  |  | 0 |  |  |  | NOT STARTED | No |  |  |  | 0
CMS | RPT_02_PSC Wire Down Response Time | NOT STARTED | On track | 42 | [5 empty] | 2026-09-30 | September | [19 empty] | No |  |  | 0 |  |  |  | NOT STARTED | No |  |  |  | 0
CMS | RPT_02_Hazardous Above Ground Leak | NOT STARTED | On track | 43 | [5 empty] | 2026-09-30 | September | [19 empty] | No |  |  | 0 |  |  |  | NOT STARTED | No |  |  |  | 0
CMS | RPT_02_AMI Contractor Completion Report | NOT STARTED | On track | 44 | [5 empty] | 2026-09-30 | September | [19 empty] | No |  |  | 0 |  |  |  | NOT STARTED | No |  |  |  | 0
CMS | RPT_02_Collection Statistic | NOT STARTED | On track | 45 | [5 empty] | 2026-09-30 | September | [19 empty] | No |  |  | 0 |  |  |  | NOT STARTED | No |  |  |  | 0
CMS | RPT_02_First and Last Job | NOT STARTED | On track | 46 | [5 empty] | 2026-09-30 | September | [19 empty] | No |  |  | 0 |  |  |  | NOT STARTED | No |  |  |  | 0
CMS | RPT_02_Rate Class | NOT STARTED | On track | 47 | [5 empty] | 2026-09-30 | September | [19 empty] | No |  |  | 0 |  |  |  | NOT STARTED | No |  |  |  | 0
Leaks | RPT_04_Leak Recheck Times | NOT STARTED | On track | 48 | [5 empty] | 2026-09-30 | September | [19 empty] | No |  |  | 0 |  |  |  | NOT STARTED | No |  |  |  | 0
Formulas:
Rework Est. Fix Date = IF(OR([Report Name]="",AR35=0),"",INDEX('Rework Log'!$H:$H,AR35))

## Find a Report
Find a Report
Pick a report below - everything updates automatically.
Report Name:
Domain
Current Status
Status Flag
Business Value Rank
PO
DB Developer
PBI Developer
QA Tester
DB Dev Expected
DB Dev Actual
PBI Dev Expected
PBI Dev Actual
QA Expected
QA Actual
DPO Approval Expected
DPO Approval Reviewer
Confirmed Deployed?
Confirmed Deployed Date
Blocked?
Blocked At
Rework Count
Last Sent Back From
Last Defect/Jira Ticket
Auto Rework Alert
Chronology Check
Comments

## Fact Table
Reference snapshot only - the app rebuilds this automatically from Combined Delivery Data on every upload. Editing this tab directly has no effect.
Domain | Status | Report Name | DB Developers | PBI Developers | Schema | PO | Status Start Date | Expected Release Date | Actual Release Date
Leaks | DB Dev | RPT_04_Active Leaks | Fetwi | Sarath |  |  |  | 2026-04-03 | 2026-04-03
Leaks | PBI Dev | RPT_04_Active Leaks | Fetwi | Sarath |  |  | 2026-04-03 | 2026-04-02 | 2026-04-02
Leaks | QA | RPT_04_Active Leaks | Fetwi | Sarath |  |  | 2026-04-02 | 2026-04-10 | 2026-04-10
Leaks | DPO Approval | RPT_04_Active Leaks | Fetwi | Sarath |  |  | 2026-04-10
Leaks | RELEASED IN PROD | RPT_04_Active Leaks | Fetwi | Sarath
Leaks | DB Dev | RPT_04_Count of Active Leaks On Hand | Fetwi | Sarath |  |  |  | 2026-04-03 | 2026-04-03
Leaks | PBI Dev | RPT_04_Count of Active Leaks On Hand | Fetwi | Sarath |  |  | 2026-04-03 | 2026-04-02 | 2026-04-02
Leaks | QA | RPT_04_Count of Active Leaks On Hand | Fetwi | Sarath |  |  | 2026-04-02 | 2026-04-10 | 2026-04-10
Leaks | DPO Approval | RPT_04_Count of Active Leaks On Hand | Fetwi | Sarath |  |  | 2026-04-10
Leaks | RELEASED IN PROD | RPT_04_Count of Active Leaks On Hand | Fetwi | Sarath
Leaks | DB Dev | RPT_04_Leak Scheduling | Sreevarsha | Sarath |  |  |  | 2026-04-03 | 2026-04-03
Leaks | PBI Dev | RPT_04_Leak Scheduling | Sreevarsha | Sarath |  |  | 2026-04-03 | 2026-04-08 | 2026-04-08
Leaks | QA | RPT_04_Leak Scheduling | Sreevarsha | Sarath |  |  | 2026-04-08 | 2026-04-10 | 2026-04-10
Leaks | DPO Approval | RPT_04_Leak Scheduling | Sreevarsha | Sarath |  |  | 2026-04-10
Leaks | RELEASED IN PROD | RPT_04_Leak Scheduling | Sreevarsha | Sarath
Leaks | DB Dev | RPT_04_Leak Days Remaining | Siva | Navya |  |  |  | 2026-04-03 | 2026-04-03
Leaks | PBI Dev | RPT_04_Leak Days Remaining | Siva | Navya |  |  | 2026-04-03 | 2026-04-14 | 2026-04-14
Leaks | QA | RPT_04_Leak Days Remaining | Siva | Navya |  |  | 2026-04-14 | 2026-04-10 | 2026-04-10
Leaks | DPO Approval | RPT_04_Leak Days Remaining | Siva | Navya |  |  | 2026-04-10
Leaks | RELEASED IN PROD | RPT_04_Leak Days Remaining | Siva | Navya
Leaks | DB Dev | RPT_04_Cleared Leaks | Sreevarsha | Sarath |  |  |  | 2026-04-03 | 2026-04-03
Leaks | PBI Dev | RPT_04_Cleared Leaks | Sreevarsha | Sarath |  |  | 2026-04-03 | 2026-04-08 | 2026-04-08
Leaks | QA | RPT_04_Cleared Leaks | Sreevarsha | Sarath |  |  | 2026-04-08 | 2026-04-10 | 2026-04-10
Leaks | DPO Approval | RPT_04_Cleared Leaks | Sreevarsha | Sarath |  |  | 2026-04-10
Leaks | RELEASED IN PROD | RPT_04_Cleared Leaks | Sreevarsha | Sarath
Leaks | DB Dev | RPT_04_Leaks Repaired Detail | Rupa | Navya |  |  |  | 2026-04-03 | 2026-04-03
Leaks | PBI Dev | RPT_04_Leaks Repaired Detail | Rupa | Navya |  |  | 2026-04-03 | 2026-04-14 | 2026-04-14
Leaks | QA | RPT_04_Leaks Repaired Detail | Rupa | Navya |  |  | 2026-04-14 | 2026-04-10 | 2026-04-10
Leaks | DPO Approval | RPT_04_Leaks Repaired Detail | Rupa | Navya |  |  | 2026-04-10
Leaks | RELEASED IN PROD | RPT_04_Leaks Repaired Detail | Rupa | Navya
Leaks | DB Dev | RPT_04_Leaks Aging | Sreevarsha | Navya |  |  |  | 2026-04-10 | 2026-04-10
Leaks | PBI Dev | RPT_04_Leaks Aging | Sreevarsha | Navya |  |  | 2026-04-10 | 2026-04-14 | 2026-04-14
Leaks | QA | RPT_04_Leaks Aging | Sreevarsha | Navya |  |  | 2026-04-14 | 2026-04-10 | 2026-04-10
Leaks | DPO Approval | RPT_04_Leaks Aging | Sreevarsha | Navya |  |  | 2026-04-10
Leaks | RELEASED IN PROD | RPT_04_Leaks Aging | Sreevarsha | Navya
Leaks | DB Dev | RPT_04_Prior Leak Readings | Siddu | Navya |  |  |  | 2026-04-10 | 2026-04-10
Leaks | PBI Dev | RPT_04_Prior Leak Readings | Siddu | Navya |  |  | 2026-04-10 | 2026-04-14 | 2026-04-14
Leaks | QA | RPT_04_Prior Leak Readings | Siddu | Navya |  |  | 2026-04-14 | 2026-04-10 | 2026-04-10
Leaks | DPO Approval | RPT_04_Prior Leak Readings | Siddu | Navya |  |  | 2026-04-10
Leaks | RELEASED IN PROD | RPT_04_Prior Leak Readings | Siddu | Navya
Leaks | DB Dev | RSS_04_Leak Grade Change History | Siva | Navya |  |  |  | 2026-04-15 | 2026-04-15
Leaks | PBI Dev | RSS_04_Leak Grade Change History | Siva | Navya |  |  | 2026-04-15 | 2026-04-14 | 2026-04-14
Leaks | QA | RSS_04_Leak Grade Change History | Siva | Navya |  |  | 2026-04-14 | 2026-04-10 | 2026-04-10
Leaks | DPO Approval | RSS_04_Leak Grade Change History | Siva | Navya |  |  | 2026-04-10
Leaks | RELEASED IN PROD | RSS_04_Leak Grade Change History | Siva | Navya
Leaks | DB Dev | RPT_04_Surveillances With Zero Readings | Sreevarsha | Navya
Leaks | PBI Dev | RPT_04_Surveillances With Zero Readings | Sreevarsha | Navya |  |  |  | 2026-04-27 | 2026-04-27
Leaks | QA | RPT_04_Surveillances With Zero Readings | Sreevarsha | Navya |  |  | 2026-04-27 | 2026-04-27 | 2026-04-27
Leaks | DPO Approval | RPT_04_Surveillances With Zero Readings | Sreevarsha | Navya |  |  | 2026-04-27
Leaks | RELEASED IN PROD | RPT_04_Surveillances With Zero Readings | Sreevarsha | Navya
Leaks | DB Dev | RPT_04 High Emitter leaks | Sreevarsha | Navya
Leaks | PBI Dev | RPT_04 High Emitter leaks | Sreevarsha | Navya |  |  |  | 2026-04-29 | 2026-04-29
Leaks | QA | RPT_04 High Emitter leaks | Sreevarsha | Navya |  |  | 2026-04-29 | 2026-04-29 | 2026-04-29
Leaks | DPO Approval | RPT_04 High Emitter leaks | Sreevarsha | Navya |  |  | 2026-04-29
Leaks | RELEASED IN PROD | RPT_04 High Emitter leaks | Sreevarsha | Navya
Leaks | DB Dev | RPT_04_School Zone Leaks Without Repair | Sreevarsha | Sarath
Leaks | PBI Dev | RPT_04_School Zone Leaks Without Repair | Sreevarsha | Sarath |  |  |  | 2026-05-19 | 2026-05-19
Leaks | QA | RPT_04_School Zone Leaks Without Repair | Sreevarsha | Sarath |  |  | 2026-05-19 | 2026-05-19 | 2026-05-19
Leaks | DPO Approval | RPT_04_School Zone Leaks Without Repair | Sreevarsha | Sarath |  |  | 2026-05-19
Leaks | RELEASED IN PROD | RPT_04_School Zone Leaks Without Repair | Sreevarsha | Sarath
Leaks | DB Dev | RPT_04_PSC Quarterly Leak | Geetha | Sarath
Leaks | PBI Dev | RPT_04_PSC Quarterly Leak | Geetha | Sarath |  |  |  | 2026-06-02 | 2026-06-02
Leaks | QA | RPT_04_PSC Quarterly Leak | Geetha | Sarath |  |  | 2026-06-02 | 2026-06-02 | 2026-06-02
Leaks | DPO Approval | RPT_04_PSC Quarterly Leak | Geetha | Sarath |  |  | 2026-06-02
Leaks | RELEASED IN PROD | RPT_04_PSC Quarterly Leak | Geetha | Sarath |  |  |  | 2026-06-11 | 2026-06-11
Leaks | DB Dev | RPT_04_Rechecks Completed less than 14 days | Rupa | Shraddha
Leaks | PBI Dev | RPT_04_Rechecks Completed less than 14 days | Rupa | Shraddha |  |  |  | 2026-04-22 | 2026-04-22
Leaks | QA | RPT_04_Rechecks Completed less than 14 days | Rupa | Shraddha |  |  | 2026-04-22 | 2026-04-22 | 2026-04-22
Leaks | DPO Approval | RPT_04_Rechecks Completed less than 14 days | Rupa | Shraddha |  |  | 2026-04-22
Leaks | RELEASED IN PROD | RPT_04_Rechecks Completed less than 14 days | Rupa | Shraddha
Leaks | DB Dev | RPT_04_SEI Leak Activity | Siva | Shraddha
Leaks | PBI Dev | RPT_04_SEI Leak Activity | Siva | Shraddha |  |  |  | 2026-04-27 | 2026-04-27
Leaks | QA | RPT_04_SEI Leak Activity | Siva | Shraddha |  |  | 2026-04-27 | 2026-04-27 | 2026-04-27
Leaks | DPO Approval | RPT_04_SEI Leak Activity | Siva | Shraddha |  |  | 2026-04-27
Leaks | RELEASED IN PROD | RPT_04_SEI Leak Activity | Siva | Shraddha
Leaks | DB Dev | RPT_04_CMS Leak Productivity | Siddu | Navya
Leaks | PBI Dev | RPT_04_CMS Leak Productivity | Siddu | Navya |  |  |  | 2026-05-05 | 2026-05-05
Leaks | QA | RPT_04_CMS Leak Productivity | Siddu | Navya |  |  | 2026-05-05 | 2026-05-05 | 2026-05-05
Leaks | DPO Approval | RPT_04_CMS Leak Productivity | Siddu | Navya |  |  | 2026-05-05
Leaks | RELEASED IN PROD | RPT_04_CMS Leak Productivity | Siddu | Navya
Leaks | DB Dev | RPT_04_Main Break Corrosion and Leak Cluster | Siddu | Sarath
Leaks | PBI Dev | RPT_04_Main Break Corrosion and Leak Cluster | Siddu | Sarath |  |  |  | 2026-06-02 | 2026-06-02
Leaks | QA | RPT_04_Main Break Corrosion and Leak Cluster | Siddu | Sarath |  |  | 2026-06-02 | 2026-06-06 | 2026-06-06
Leaks | DPO Approval | RPT_04_Main Break Corrosion and Leak Cluster | Siddu | Sarath |  |  | 2026-06-06
Leaks | RELEASED IN PROD | RPT_04_Main Break Corrosion and Leak Cluster | Siddu | Sarath
Leaks | DB Dev | RPT_04_Leak Summary Status | Fetwi | Navya
Leaks | PBI Dev | RPT_04_Leak Summary Status | Fetwi | Navya |  |  |  | 2026-05-01 | 2026-05-01
Leaks | QA | RPT_04_Leak Summary Status | Fetwi | Navya |  |  | 2026-05-01 | 2026-06-02 | 2026-06-02
Leaks | DPO Approval | RPT_04_Leak Summary Status | Fetwi | Navya |  |  | 2026-06-02
Leaks | RELEASED IN PROD | RPT_04_Leak Summary Status | Fetwi | Navya |  |  |  | 2026-06-11 | 2026-06-11
Leaks | DB Dev | RPT_04_PSC Leak Printout | Fetwi | Shraddha |  |  |  | 2026-06-02 | 2026-06-02
Leaks | PBI Dev | RPT_04_PSC Leak Printout | Fetwi | Shraddha |  |  | 2026-06-02 | 2026-06-05 | 2026-06-05
Leaks | QA | RPT_04_PSC Leak Printout | Fetwi | Shraddha |  |  | 2026-06-05 | 2026-06-02 | 2026-06-02
Leaks | DPO Approval | RPT_04_PSC Leak Printout | Fetwi | Shraddha |  |  | 2026-06-02
Leaks | RELEASED IN PROD | RPT_04_PSC Leak Printout | Fetwi | Shraddha |  |  |  | 2026-06-19 | 2026-06-19
Leaks | DB Dev | RPT_04_Leak Control Report | Geetha | Navya |  |  |  | 2026-05-06 | 2026-05-06
Leaks | PBI Dev | RPT_04_Leak Control Report | Geetha | Navya |  |  | 2026-05-06 | 2026-06-10 | 2026-06-10
Leaks | QA | RPT_04_Leak Control Report | Geetha | Navya |  |  | 2026-06-10 | 2026-06-22 | 2026-06-22
Leaks | DPO Approval | RPT_04_Leak Control Report | Geetha | Navya |  |  | 2026-06-22
Leaks | RELEASED IN PROD | RPT_04_Leak Control Report | Geetha | Navya
Leaks | DB Dev | RPT_04_Leak Life Cycle | Geetha | Shraddha |  |  |  | 2026-05-20 | 2026-05-20
Leaks | PBI Dev | RPT_04_Leak Life Cycle | Geetha | Shraddha |  |  | 2026-05-20 | 2026-06-09 | 2026-06-09
Leaks | QA | RPT_04_Leak Life Cycle | Geetha | Shraddha |  |  | 2026-06-09 | 2026-06-25 | 2026-06-25
Leaks | DPO Approval | RPT_04_Leak Life Cycle | Geetha | Shraddha |  |  | 2026-06-25
Leaks | RELEASED IN PROD | RPT_04_Leak Life Cycle | Geetha | Shraddha
Leaks | DB Dev | RPT_04_Leak Life Cycle Legacy LMS LI | Fetwi | Navya |  |  |  | 2026-05-26 | 2026-05-26
Leaks | PBI Dev | RPT_04_Leak Life Cycle Legacy LMS LI | Fetwi | Navya |  |  | 2026-05-26 | 2026-06-10 | 2026-06-10
Leaks | QA | RPT_04_Leak Life Cycle Legacy LMS LI | Fetwi | Navya |  |  | 2026-06-10 | 2026-06-25 | 2026-06-25
Leaks | DPO Approval | RPT_04_Leak Life Cycle Legacy LMS LI | Fetwi | Navya |  |  | 2026-06-25
Leaks | RELEASED IN PROD | RPT_04_Leak Life Cycle Legacy LMS LI | Fetwi | Navya
Leaks | DB Dev | RPT_04_Leak Increase Reads | Fetwi | Navya |  |  |  | 2026-05-23 | 2026-05-23
Leaks | PBI Dev | RPT_04_Leak Increase Reads | Fetwi | Navya |  |  | 2026-05-23 | 2026-05-11 | 2026-05-11
Leaks | QA | RPT_04_Leak Increase Reads | Fetwi | Navya |  |  | 2026-05-11 | 2026-05-12 | 2026-05-12
Leaks | DPO Approval | RPT_04_Leak Increase Reads | Fetwi | Navya |  |  | 2026-05-12
Leaks | RELEASED IN PROD | RPT_04_Leak Increase Reads | Fetwi | Navya |  |  |  | 2026-06-11 | 2026-06-11
Leaks | DB Dev | Leak 360 Dashboard | Siva | Sarath |  |  |  | 2026-05-20 | 2026-05-20
Leaks | PBI Dev | Leak 360 Dashboard | Siva | Sarath |  |  | 2026-05-20 | 2026-06-13 | 2026-06-13
Leaks | QA | Leak 360 Dashboard | Siva | Sarath |  |  | 2026-06-13 | 2026-06-15 | 2026-06-15
Leaks | DB Dev | RPT_04_Leak Recheck Control | Siva | Shraddha |  |  |  | 2026-05-20 | 2026-05-20
Leaks | PBI Dev | RPT_04_Leak Recheck Control | Siva | Shraddha |  |  | 2026-05-20 | 2026-05-22 | 2026-05-22
Leaks | QA | RPT_04_Leak Recheck Control | Siva | Shraddha |  |  | 2026-05-22 | 2026-07-01 | 2026-07-01
Leaks | DPO Approval | RPT_04_Leak Recheck Control | Siva | Shraddha |  |  | 2026-07-01
Leaks | RELEASED IN PROD | RPT_04_Leak Recheck Control | Siva | Shraddha
Leaks | DB Dev | RPT_04_Main_Replacement Report | Sree | Navya |  |  |  | 2026-05-27 | 2026-05-27
Leaks | PBI Dev | RPT_04_Main_Replacement Report | Sree | Navya |  |  | 2026-05-27 | 2026-06-18 | 2026-06-18
Leaks | QA | RPT_04_Main_Replacement Report | Sree | Navya |  |  | 2026-06-18 | 2026-06-23 | 2026-06-23
Leaks | DPO Approval | RPT_04_Main_Replacement Report | Sree | Navya |  |  | 2026-06-23
Leaks | RELEASED IN PROD | RPT_04_Main_Replacement Report | Sree | Navya
Leaks | DB Dev | New Report: Leak Repair Exception | Geetha | Shraddha |  |  |  | 2026-05-26 | 2026-05-26
Leaks | PBI Dev | New Report: Leak Repair Exception | Geetha | Shraddha |  |  | 2026-05-26 | 2026-06-16 | 2026-06-16
Leaks | QA | New Report: Leak Repair Exception | Geetha | Shraddha |  |  | 2026-06-16 | 2026-06-16 | 2026-06-16
Leaks | DPO Approval | New Report: Leak Repair Exception | Geetha | Shraddha |  |  | 2026-06-16
Leaks | RELEASED IN PROD | New Report: Leak Repair Exception | Geetha | Shraddha |  |  |  | 2026-06-19 | 2026-06-19
Leaks | DB Dev | New Report: (Leak reading sample point mismatch ) Creating a new report that... | Siddu | Shraddha |  |  |  | 2026-05-27 | 2026-05-27
Leaks | PBI Dev | New Report: (Leak reading sample point mismatch ) Creating a new report that... | Siddu | Shraddha |  |  | 2026-05-27 | 2026-06-22 | 2026-06-22
Leaks | QA | New Report: (Leak reading sample point mismatch ) Creating a new report that... | Siddu | Shraddha |  |  | 2026-06-22 | 2026-06-24 | 2026-06-24
Leaks | DPO Approval | New Report: (Leak reading sample point mismatch ) Creating a new report that... | Siddu | Shraddha |  |  | 2026-06-24
Leaks | RELEASED IN PROD | New Report: (Leak reading sample point mismatch ) Creating a new report that... | Siddu | Shraddha
CMS | DB Dev | RPT_02_CO Flue Warning Tag Control | Rupa | Navya |  | Kushal
CMS | PBI Dev | RPT_02_CO Flue Warning Tag Control | Rupa | Navya |  | Kushal |  | 2026-07-10 | 2026-07-10
CMS | QA | RPT_02_CO Flue Warning Tag Control | Rupa | Navya |  | Kushal | 2026-07-10 | 2026-07-20 | 2026-07-20
CMS | DB Dev | RPT_02_Warning Tag HEFPA | Sree | Shraddha |  | Kushal
CMS | PBI Dev | RPT_02_Warning Tag HEFPA | Sree | Shraddha |  | Kushal |  | 2026-07-15 | 2026-07-15
CMS | QA | RPT_02_Warning Tag HEFPA | Sree | Shraddha |  | Kushal | 2026-07-15 | 2026-07-20 | 2026-07-20
CMS | DB Dev | RPT_02_Warning tag Printout | Sree | Shraddha |  | Kushal
CMS | PBI Dev | RPT_02_Warning tag Printout | Sree | Shraddha |  | Kushal |  | 2026-07-22 | 2026-07-22
CMS | QA | RPT_02_Warning tag Printout | Sree | Shraddha |  | Kushal | 2026-07-22 | 2026-07-20 | 2026-07-20
CMS | DB Dev | RPT_02_Corrosion | Siva | Sarath |  | Kushal
CMS | PBI Dev | RPT_02_Corrosion | Siva | Sarath |  | Kushal |  | 2026-07-24 | 2026-07-24
CMS | QA | RPT_02_Corrosion | Siva | Sarath |  | Kushal | 2026-07-24 | 2026-07-20 | 2026-07-20
CMS | DB Dev | RPT_02_House Pipe Test Comment Control | Geetha | Shraddha |  | Kushal
CMS | PBI Dev | RPT_02_House Pipe Test Comment Control | Geetha | Shraddha |  | Kushal |  | 2026-07-13 | 2026-07-13
CMS | QA | RPT_02_House Pipe Test Comment Control | Geetha | Shraddha |  | Kushal | 2026-07-13 | 2026-07-22 | 2026-07-22
CMS | DB Dev | RPT_02_Required Regulator Inspection Performed Control | Siddu | Navya |  | Bardia
CMS | DB Dev | RPT_02_Service Regulator Inspections | Sree | Sarath |  | Bardia
CMS | DB Dev | RPT_02_Service Regulator Inspection Printout | Sree | Sarath |  | Bardia
CMS | PBI Dev | RPT_02_Service Regulator Inspection Printout | Sree | Sarath |  | Bardia |  | 2026-07-18 | 2026-07-18
CMS | QA | RPT_02_Service Regulator Inspection Printout | Sree | Sarath |  | Bardia | 2026-07-18 | 2026-07-20 | 2026-07-20
CMS | DB Dev | RPT_02_20 Year Regulator Inspection | Siddu | Navya |  | Bardia
CMS | PBI Dev | RPT_02_20 Year Regulator Inspection | Siddu | Navya |  | Bardia |  | 2026-07-17 | 2026-07-17
CMS | QA | RPT_02_20 Year Regulator Inspection | Siddu | Navya |  | Bardia | 2026-07-17 | 2026-07-20 | 2026-07-20
CMS | DB Dev | RPT_02_Fixed Factor | Nick | Navya |  | Bardia
CMS | PBI Dev | RPT_02_Fixed Factor | Nick | Navya |  | Bardia |  | 2026-07-21 | 2026-07-21
CMS | QA | RPT_02_Fixed Factor | Nick | Navya |  | Bardia | 2026-07-21 | 2026-07-20 | 2026-07-20
CMS | DB Dev | RPT_02_Fixed Factor Printout | Nick | Shraddha |  | Bardia
CMS | PBI Dev | RPT_02_Fixed Factor Printout | Nick | Shraddha |  | Bardia |  | 2026-07-22 | 2026-07-22
CMS | QA | RPT_02_Fixed Factor Printout | Nick | Shraddha |  | Bardia | 2026-07-22 | 2026-07-20 | 2026-07-20
CMS | DB Dev | RPT_02_Work Order Completion Printout | Rupa | Sarath |  | Kushal
CMS | PBI Dev | RPT_02_Work Order Completion Printout | Rupa | Sarath |  | Kushal |  | 2026-07-23 | 2026-07-23
CMS | QA | RPT_02_Work Order Completion Printout | Rupa | Sarath |  | Kushal | 2026-07-23 | 2026-07-20 | 2026-07-20
CMS | DB Dev | RPT_02_GRO Control | Siva | Navya |  | Kushal
CMS | PBI Dev | RPT_02_GRO Control | Siva | Navya |  | Kushal |  | 2026-07-22 | 2026-07-22
CMS | QA | RPT_02_GRO Control | Siva | Navya |  | Kushal | 2026-07-22 | 2026-07-20 | 2026-07-20
CMS | DB Dev | RPT_02_GRO Monitor | Rupa | Shraddha |  | Bardia
CMS | PBI Dev | RPT_02_GRO Monitor | Rupa | Shraddha |  | Bardia |  | 2026-07-22 | 2026-07-22
CMS | QA | RPT_02_GRO Monitor | Rupa | Shraddha |  | Bardia | 2026-07-22 | 2026-07-27 | 2026-07-27
CMS | DB Dev | RPT_02_Public Buildings Inspection | Geetha
CMS | PBI Dev | RPT_02_Public Buildings Inspection | Geetha
CMS | QA | RPT_02_Public Buildings Inspection | Geetha
CMS | DB Dev | RPT_02_Gas Trouble | Siddu
CMS | PBI Dev | RPT_02_Gas Trouble | Siddu
CMS | QA | RPT_02_Gas Trouble | Siddu

## Dim Table
This tab is manually maintained - edit Expected Report Count / Expected Release Date directly, or add new domain/month rows, as delivery plans change. Unlike Fact Table, the app always reads this sheet as-is.
Domain | Expected Report Count | Expected Release Date
Leaks | 8 | 2026-04-30
Leaks | 10 | 2026-05-30
Leaks | 9 | 2026-06-30
CMS | 15 | 2026-07-30
CMS | 15 | 2026-08-30
CMS | 17 | 2026-09-30
CMS | 20 | 2026-10-30
CMS | 20 | 2026-11-30
Maintenance and Construction | 18 | 2026-12-30
Maintenance and Construction | 18 | 2027-01-30
Maintenance and Construction | 19 | 2027-02-28
Meter Management | 9 | 2027-03-30
Assets and Engineering | 8 | 2027-03-30

## Data Validation
Domain | DB Developer | PBI Developer | PO | Blocked? | Current Status | All Developers | QA Tester
-> feeds column A on Combined Delivery Data | -> feeds column F on Combined Delivery Data | -> feeds column G on Combined Delivery Data | -> feeds column E on Combined Delivery Data | -> feeds column AF on Combined Delivery Data | -> feeds column C on Combined Delivery Data | -> feeds column G on Rework Log (Assigned To) | -> feeds column I on Combined Delivery Data
Leaks | Fetwi | Navya | Kushal | Yes | NOT STARTED | Fetwi | Preety
CMS | Siva | Sarath | Bardia | No | DB Dev | Siva | Kelvin
Maintenance and Construction | Sreevarsha | Shraddha |  |  | PBI Dev | Sreevarsha | Kushal
Meter Management | Siddu |  |  |  | QA | Siddu | Bardia
Assets and Engineering | Sree |  |  |  | DPO Approval | Sree
| Rupa |  |  |  | RELEASED IN PROD | Rupa
| Geetha |  |  |  |  | Geetha
| Nick |  |  |  |  | Nick
Navya
Sarath
Shraddha
Note on A1: This list feeds the dropdown on Combined Delivery Data, column A (Domain). Add, remove, or rename values here and the dropdown updates automatically.
Note on B1: This list feeds the dropdown on Combined Delivery Data, column F (DB Developer). Add, remove, or rename values here and the dropdown updates automatically.
Note on C1: This list feeds the dropdown on Combined Delivery Data, column G (PBI Developer). Add, remove, or rename values here and the dropdown updates automatically.
Note on D1: This list feeds the dropdown on Combined Delivery Data, column E (PO). Add, remove, or rename values here and the dropdown updates automatically.
Note on E1: This list feeds the dropdown on Combined Delivery Data, column Z (Blocked?). Add, remove, or rename values here and the dropdown updates automatically.
Note on F1: This list feeds the dropdown on Combined Delivery Data, column C (Current Status). Add, remove, or rename values here and the dropdown updates automatically.

## Rework Log
One row per bounce-back, optional detail. You do not need to log here for the tracker to know a rework happened - Combined Delivery Data (column AL, Auto Rework Alert) detects that automatically the moment a later stage already has a date but Current Status gets moved back. Use this tab to capture WHY it happened, the defect/Jira ticket if there is one, and when it is now expected fixed. | [6 empty] | Live summary - one row per report, computed from the log entries to the left. Nothing here is typed manually.
Report Name | Date Sent Back | From Stage | To Stage | Reason / Note | Defect/Jira Ticket | Est. Fix Date | Report Name | Times Sent Back | Last Sent Back Date | Last From Stage | Last To Stage
RPT_02_Required Regulator Inspection Performed Control | 2026-07-23 | QA | DB Dev | Defects found in QA testing. |  |  | RPT_04_Active Leaks | 0
RPT_02_Service Regulator Inspections | 2026-07-23 | QA | DB Dev | Defects found in QA testing. |  |  | RPT_04_Count of Active Leaks On Hand | 0
[7 empty] | RPT_04_Leak Scheduling | 0
[7 empty] | RPT_04_Leak Days Remaining | 0
[7 empty] | RPT_04_Cleared Leaks | 0
[7 empty] | RPT_04_Leaks Repaired Detail | 0
[7 empty] | RPT_04_Leaks Aging | 0
[7 empty] | RPT_04_Prior Leak Readings | 0
[7 empty] | RSS_04_Leak Grade Change History | 0
[7 empty] | RPT_04_Surveillances With Zero Readings | 0
[7 empty] | RPT_04 High Emitter leaks | 0
[7 empty] | RPT_04_School Zone Leaks Without Repair | 0
[7 empty] | RPT_04_PSC Quarterly Leak | 0
[7 empty] | RPT_04_Rechecks Completed less than 14 days | 0
[7 empty] | RPT_04_SEI Leak Activity | 0
[7 empty] | RPT_04_CMS Leak Productivity | 0
[7 empty] | RPT_04_Main Break Corrosion and Leak Cluster | 0
[7 empty] | RPT_04_Leak Summary Status | 0
[7 empty] | RPT_04_PSC Leak Printout | 0
[7 empty] | RPT_04_Leak Control Report | 0
[7 empty] | RPT_04_Leak Life Cycle | 0
[7 empty] | RPT_04_Leak Life Cycle Legacy LMS LI | 0
[7 empty] | RPT_04_Leak Increase Reads | 0
[7 empty] | Leak 360 Dashboard | 0
[7 empty] | RPT_04_Leak Recheck Control | 0
[7 empty] | RPT_04_Main_Replacement Report | 0
[7 empty] | New Report: Leak Repair Exception | 0
[7 empty] | New Report: (Leak reading sample point mismatch ) Creating a new report that... | 0
[7 empty] | RPT_02_CO Flue Warning Tag Control | 0
[7 empty] | RPT_02_Warning Tag HEFPA | 0
[7 empty] | RPT_02_Warning tag Printout | 0
[7 empty] | RPT_02_Corrosion | 0
[7 empty] | RPT_02_House Pipe Test Comment Control | 0
[7 empty] | RPT_02_Required Regulator Inspection Performed Control | 1 | 2026-07-23 | QA | DB Dev
[7 empty] | RPT_02_Service Regulator Inspections | 1 | 2026-07-23 | QA | DB Dev
[7 empty] | RPT_02_Service Regulator Inspection Printout | 0
[7 empty] | RPT_02_20 Year Regulator Inspection | 0
[7 empty] | RPT_02_Fixed Factor | 0
[7 empty] | RPT_02_Fixed Factor Printout | 0
[7 empty] | RPT_02_Work Order Completion Printout | 0
[7 empty] | RPT_02_GRO Control | 0
[7 empty] | RPT_02_GRO Monitor | 0
[7 empty] | RPT_02_Public Buildings Inspection | 0
[7 empty] | RPT_02_Investigate Wall Check and Service Check | 0
[7 empty] | RPT_02_Cut Out Orders | 0
[7 empty] | RPT_02_Gas Trouble | 0
[7 empty] | RPT_02_Wall Check Control | 0
[7 empty] | RPT_02_High Pressure Steel Inside Inspection | 0
[7 empty] | RPT_02_Large Gas Outage | 0
[7 empty] | RPT_02_Fitting Work | 0
[7 empty] | RPT_02_Field Collector Report | 0
[7 empty] | RPT_02_Turn On for Non-Payment | 0
[7 empty] | RPT_02_Collector Payment Recap | 0
[7 empty] | RPT_02_Incentive Management | 0
[7 empty] | RPT_02_UTC Report | 0
[7 empty] | RPT_02_Adjacent Property Checks | 0
[7 empty] | RPT_02_High Bill Investigations | 0
[7 empty] | RPT_02_Emergency Order Type | 0
[7 empty] | RPT_02_Cut Out Curb Box | 0
[7 empty] | RPT_02_New York Incident | 0
[7 empty] | RPT_02_Outside Repeat Leaks | 0
[7 empty] | RPT_02_Meter Change | 0
[7 empty] | RPT_02_Field Order Value | 0
[7 empty] | RPT_02_Same Day Reconnect | 0
[7 empty] | RPT_02_Site Specific Analysis | 0
[7 empty] | RPT_02_PSC Wire Down Response Time | 0
[7 empty] | RPT_02_Hazardous Above Ground Leak | 0
[7 empty] | RPT_02_AMI Contractor Completion Report | 0
[7 empty] | RPT_02_Collection Statistic | 0
[7 empty] | RPT_02_First and Last Job | 0
[7 empty] | RPT_02_Rate Class | 0
[7 empty] | RPT_04_Leak Recheck Times | 0