## READ ME FIRST (hidden)
GDM REPORT DELIVERY TRACKER
THE TWO TABS
Combined Delivery Data = what is true RIGHT NOW. One row per report, latest dates only - built for a 10-second executive read. Rework Log = everything that ever went wrong. One row per bounce-back, kept forever. AMBER columns belong to the sender, BLUE to the fixer, PURPLE is automatic.
COLORS
RED = needs action now (blocked, overdue, late, unclaimed, or a red instruction in Data Check). AMBER = open or waiting. GREEN = good. If nothing is red on your rows, you owe nothing. PURPLE headers and purple-tinted cells = the sheet computes these and they are locked - you never type in purple. Everything else is yours to fill.
NORMAL DAY - A STAGE FINISHES
Two cells on Combined Delivery Data: your stage's Actual Completion Date, and Current Status to the next stage. Done.
SOMETHING IS WRONG - SENDER (usually QA), about 30 seconds
1. Main tab: Blocked? -> "Yes - needs [stage] to fix", and Current Status -> back to that stage 2. Rework Log, the AMBER columns of one new row: report (dropdown), Ctrl+; for today, From/To stage, your name, what was wrong You never touch completion dates. The row now shows UNCLAIMED in red until the fixer commits.
THE FIXER - AT PICKUP (two cells, both yours)
1. Expected Fix Date: your promise. The main tab instantly shows everyone "Blocked - needs DB Dev to fix - promised 8/5", and your row starts counting "N d LATE" if you miss it 2. CUT your old completion date from the main tab, PASTE it into "First Completed On" - one motion. History saved forever; the main tab correctly shows no completion date while you redo the work. A red note in Data Check reminds you until it's done.
THE FIXER - WHEN DONE
1. Same row: Date Fixed (Ctrl+;), your name, what was fixed, Resolved? = Yes - the row turns green 2. Main tab: type the NEW completion date into the empty cell, set Blocked? -> No. Everything red clears itself.
WHAT NEVER GETS LOST
Original target dates: never overwritten, always on the main tab. First-time completion dates: "First Completed On" on the Rework Log, forever. Every redo completion: Date Fixed. Start dates: each stage starts when the previous one completes - and completions are moved (never deleted), so nothing disappears. The main tab always shows only the LATEST truth.
SPECIAL CASES - ONE LINE EACH
Bounces again -> repeat the moments; a NEW row each time. Several small defects, one bounce -> ONE row, list them in What Was Wrong. Separate rows only when fixes go to different stages (then point Blocked? at the earliest). Bug found AFTER release -> same moments; Confirmed Deployed stays Yes, update its date after redeploy. Fixer needs more time -> overwrite your Expected Fix Date. "Not a bug" -> close the row: What Was Fixed = "No change needed - working as designed". Logged by mistake -> delete the row, set Blocked? back to No. The sheet self-corrects. Cancelled mid-fix -> close the row with "Cancelled - descoped". Told verbally, nothing entered -> it did not happen. The Blocked? flip IS the send-back.
THE SHEET POLICES ITSELF
Blocked but not logged -> red "Blocked - log it on Rework Log". Picked up but old completion date still on main tab -> red "Move old [stage] completion date...". Row open but not marked blocked -> red instruction. Missing sent-back date -> red in Aging. Duplicates and impossible date orders -> flagged. Hover any dropdown for guidance.

## Combined Delivery Data
Domain | Report Name | Current Status | Status Flag (auto) | Business Value Rank | PO | DB Developer | PBI Developer | QA Tester | Schema | Plan Delivery Date | Plan Delivery Month | DB Dev Baseline Completion Date | DB Dev Reforecast Completion Date | DB Dev Actual Completion Date | PBI Dev Baseline Completion Date | PBI Dev Reforecast Completion Date | PBI Dev Actual Completion Date | QA Baseline Completion Date | QA Reforecast Completion Date | QA Actual Completion Date | DPO Approval Baseline Completion Date | DPO Approval Reforecast Completion Date | DPO Approval Reviewer | Confirmed Deployed? | Confirmed Deployed Date | UAT Report URL | Production URL | Blocked? | Data Check (auto) | Comments
Leaks | RPT_04_Active Leaks | RELEASED IN PROD | Delivered | 1 |  | Fetwi | Sarath | Preety |  | 2026-04-30 | April | 2026-04-03 |  | 2026-04-03 | 2026-04-02 |  | 2026-04-02 | 2026-04-10 |  | 2026-04-10 |  |  | Kelvin Hu | Yes | 2026-04-10 | https://app.powerbi.com/groups/me/apps/eedba83d-be9a-45f9-9504-7bfa41e6051a/reports/62307ec4-3158-4457-8dcc-4acc2150cdc3/ccfe9e7f0a40d49acb85?experience=power-bi | https://app.powerbi.com/groups/me/apps/2c7180b1-0d3d-45be-979e-f7dc86b3557d/reports/8cd4a21d-3abe-4e55-a99e-3af846ab1c67/ccfe9e7f0a40d49acb85?ctid=f98a6a53-25f3-4212-901c-c7787fcd3495&experience=power-bi | No | #VALUE! | [Historical, April 2026]: QA found an issue - date calendar dimension broken. Fetwi assigned to fix.
Leaks | RPT_04_Count of Active Leaks On Hand | RELEASED IN PROD | Delivered | 2 |  | Fetwi | Sarath | Preety |  | 2026-04-30 | April | 2026-04-03 |  | 2026-04-03 | 2026-04-02 |  | 2026-04-02 | 2026-04-10 |  | 2026-04-10 |  |  | Kelvin Hu | Yes | 2026-04-10 | https://app.powerbi.com/groups/me/apps/eedba83d-be9a-45f9-9504-7bfa41e6051a/reports/c0b3f0ae-dedd-485b-8bbc-aa0e5f3fd077/24a66431d0637282f4b7?experience=power-bi | https://app.powerbi.com/groups/me/apps/2c7180b1-0d3d-45be-979e-f7dc86b3557d/reports/5ffd546f-ad77-4a7f-8e6d-94dc08bef796/24a66431d0637282f4b7?ctid=f98a6a53-25f3-4212-901c-c7787fcd3495&experience=power-bi | No |  | [Historical, April 2026]: QA found an issue - date calendar dimension broken. Fetwi assigned to fix.
Leaks | RPT_04_Leak Scheduling | RELEASED IN PROD | Delivered | 4 |  | Sreevarsha | Sarath | Preety |  | 2026-04-30 | April | 2026-04-03 |  | 2026-04-03 | 2026-04-08 |  | 2026-04-08 | 2026-04-10 |  | 2026-04-10 |  |  | Kelvin Hu | Yes | 2026-04-10 |  |  | No
Leaks | RPT_04_Leak Days Remaining | RELEASED IN PROD | Delivered | 5 |  | Siva | Navya | Preety |  | 2026-04-30 | April | 2026-04-03 |  | 2026-04-03 | 2026-04-14 |  | 2026-04-14 | 2026-04-10 |  | 2026-04-10 |  |  | Kelvin Hu | Yes | 2026-04-10 | https://app.powerbi.com/groups/me/apps/eedba83d-be9a-45f9-9504-7bfa41e6051a/reports/8b9ae445-3a30-4ae6-a3fa-7a6d8e7ef349/d97da6159d0c87677529?experience=power-bi | https://app.powerbi.com/groups/me/apps/2c7180b1-0d3d-45be-979e-f7dc86b3557d/reports/848ce65a-4e47-422b-aae5-7ea9e7d68a5f/d97da6159d0c87677529?ctid=f98a6a53-25f3-4212-901c-c7787fcd3495&experience=power-bi | No | QA target is before PBI Dev target | 16/04 - Testing completed in QA and created defect https://jira.prod.nationalgrid.com/browse/GDMP-2186; ETA -04/24
Leaks | RPT_04_Cleared Leaks | RELEASED IN PROD | Delivered | 3 |  | Sreevarsha | Sarath | Preety |  | 2026-04-30 | April | 2026-04-03 |  | 2026-04-03 | 2026-04-08 |  | 2026-04-08 | 2026-04-10 |  | 2026-04-10 |  |  | Kelvin Hu | Yes | 2026-04-10 | https://app.powerbi.com/groups/me/apps/eedba83d-be9a-45f9-9504-7bfa41e6051a/reports/938a9ba1-8138-440e-842a-d9a679933d8c/44bb4fce98fafb2cace2?experience=power-bi | https://app.powerbi.com/groups/me/apps/2c7180b1-0d3d-45be-979e-f7dc86b3557d/reports/677c6418-6db8-4ebf-9323-65be4cb2c960/ea184ec020032ecbdd43?ctid=f98a6a53-25f3-4212-901c-c7787fcd3495&experience=power-bi | No |  | [Historical, April 2026]: L_GRO_NUMBER columns had an issue in QA - DB team assigned to fix.
Leaks | RPT_04_Leaks Repaired Detail | RELEASED IN PROD | Delivered | 6 |  | Rupa | Navya | Preety |  | 2026-04-30 | April | 2026-04-03 |  | 2026-04-03 | 2026-04-14 |  | 2026-04-14 | 2026-04-10 |  | 2026-04-10 |  |  | Kelvin Hu | Yes | 2026-04-10 | https://app.powerbi.com/groups/me/apps/eedba83d-be9a-45f9-9504-7bfa41e6051a/reports/cbaf2155-2cf3-4377-8af2-7e07a896e887/ea184ec020032ecbdd43?experience=power-bi | https://app.powerbi.com/groups/me/apps/2c7180b1-0d3d-45be-979e-f7dc86b3557d/reports/9c6d5e21-4e57-4a64-9973-61ff3717468e/ea184ec020032ecbdd43?ctid=f98a6a53-25f3-4212-901c-c7787fcd3495&experience=power-bi | No | QA target is before PBI Dev target | 21/4 Testing completed in QA and defect raised https://jira.prod.nationalgrid.com/browse/GDMP-2190; Report ready for testing 04/23/2026
Leaks | RPT_04_Leaks Aging | RELEASED IN PROD | Delivered | 7 |  | Sreevarsha | Navya | Preety |  | 2026-04-30 | April | 2026-04-10 |  | 2026-04-10 | 2026-04-14 |  | 2026-04-14 | 2026-04-10 |  | 2026-04-10 |  |  | Kelvin Hu | Yes | 2026-04-10 | https://app.powerbi.com/groups/me/apps/eedba83d-be9a-45f9-9504-7bfa41e6051a/reports/383c1502-9c3c-4fa0-a321-321cfed3b4a1/ReportSection1e63b8fbeb9ea54074e1?experience=power-bi | https://app.powerbi.com/groups/me/apps/2c7180b1-0d3d-45be-979e-f7dc86b3557d/reports/b7f15195-22d6-4ac4-8982-a8cadb215cbf/ReportSection1e63b8fbeb9ea54074e1?ctid=f98a6a53-25f3-4212-901c-c7787fcd3495&experience=power-bi | No | QA target is before PBI Dev target
Leaks | RPT_04_Prior Leak Readings | RELEASED IN PROD | Delivered | 9 |  | Siddu | Navya | Preety |  | 2026-04-30 | April | 2026-04-10 |  | 2026-04-10 | 2026-04-14 |  | 2026-04-14 | 2026-04-10 |  | 2026-04-10 |  |  | Kelvin Hu | Yes | 2026-04-10 | https://app.powerbi.com/groups/me/apps/7767030c-f4c8-4488-b3cb-36a860cb6ff2/reports/acc74ccc-08b7-420d-b64e-5e4d786ac711/ReportSection6d915001f68ea4805272?experience=power-bi | https://app.powerbi.com/groups/me/apps/5b29b0dd-a398-4801-84ce-f3a7d8435827/reports/5a06a5bd-88fb-4024-8841-570da23785ad/ReportSection6d915001f68ea4805272?ctid=f98a6a53-25f3-4212-901c-c7787fcd3495&experience=power-bi | No | QA target is before PBI Dev target
Leaks | RSS_04_Leak Grade Change History | RELEASED IN PROD | Delivered | 8 |  | Siva | Navya | Preety |  | 2026-04-30 | April | 2026-04-15 |  | 2026-04-15 | 2026-04-14 |  | 2026-04-14 | 2026-04-10 |  | 2026-04-10 |  |  | Kelvin Hu | Yes | 2026-04-10 | https://app.powerbi.com/groups/me/apps/7767030c-f4c8-4488-b3cb-36a860cb6ff2/reports/6fe40f7b-3dfe-45ee-9f81-cb977321242d/9d7e292e8fb40cfee194?experience=power-bi | https://app.powerbi.com/groups/me/apps/5b29b0dd-a398-4801-84ce-f3a7d8435827/reports/4268caf5-dcbd-4b00-8518-baf8239fff69/9d7e292e8fb40cfee194?experience=power-bi | No | QA target is before DB Dev target | 23/4 - Testing completed in QA and defect created https://jira.prod.nationalgrid.com/browse/GDMP-2227; Report is ready for testing 04/23/2026
Leaks | RPT_04_Surveillances With Zero Readings | RELEASED IN PROD | Delivered | 10 |  | Sreevarsha | Navya | Kelvin |  | 2026-05-31 | May |  |  |  | 2026-04-27 |  | 2026-04-27 | 2026-04-27 |  | 2026-04-27 |  |  | Kelvin Hu | Yes | 2026-04-27 | https://app.powerbi.com/groups/me/apps/eedba83d-be9a-45f9-9504-7bfa41e6051a/reports/743b79eb-5470-4cd4-ad54-81eb3b409ae8/ea184ec020032ecbdd43?ctid=f98a6a53-25f3-4212-901c-c7787fcd3495&experience=power-bi | https://app.powerbi.com/groups/me/apps/2c7180b1-0d3d-45be-979e-f7dc86b3557d/reports/c887cd5e-9172-4de3-921e-2c0edd2533bc/ea184ec020032ecbdd43?experience=power-bi | No
Leaks | RPT_04 High Emitter leaks | RELEASED IN PROD | Delivered | 11 |  | Sreevarsha | Navya | Preety |  | 2026-05-31 | May |  |  |  | 2026-04-29 |  | 2026-04-29 | 2026-04-29 |  | 2026-04-29 |  |  | Kelvin Hu | Yes | 2026-04-29 | https://app.powerbi.com/groups/me/apps/61b18507-2848-49b9-aacc-32c49ffe1e0b/reports/a44e7124-b1d0-4a09-a5d1-157e2043ba8e/ea184ec020032ecbdd43?ctid=f98a6a53-25f3-4212-901c-c7787fcd3495&experience=power-bi | https://app.powerbi.com/groups/me/apps/93d01997-58e0-48d8-bcca-ad8377094e64/reports/6d6fe558-e5d6-4a4b-b6fb-8a5f8735d1df/ea184ec020032ecbdd43?experience=power-bi | No |  | 05/05- defect raised https://jira.prod.nationalgrid.com/browse/GDMP-2230
Leaks | RPT_04_School Zone Leaks Without Repair | RELEASED IN PROD | Delivered | 12 |  | Sreevarsha | Sarath | Preety |  | 2026-05-31 | May |  |  |  | 2026-05-19 |  | 2026-05-19 | 2026-05-19 |  | 2026-05-19 |  |  | Kelvin Hu | Yes | 2026-05-19 | https://app.powerbi.com/groups/me/apps/eedba83d-be9a-45f9-9504-7bfa41e6051a/reports/0f3b2c1d-09ad-45db-9786-31e8c9401bc4/ReportSectionda782bb6769340acca9d?experience=power-bi | https://app.powerbi.com/groups/me/apps/2c7180b1-0d3d-45be-979e-f7dc86b3557d/reports/5e101b4d-8b08-431a-8b3a-04aafc85f314/ReportSection1e63b8fbeb9ea54074e1?experience=power-bi | No
Leaks | RPT_04_PSC Quarterly Leak | RELEASED IN PROD | Delivered | 13 |  | Geetha | Sarath | Kelvin |  | 2026-05-31 | May |  |  |  | 2026-06-02 |  | 2026-06-02 | 2026-06-02 |  | 2026-06-02 | 2026-06-11 |  | Kelvin Hu | Yes | 2026-06-11 |  | https://app.powerbi.com/groups/me/apps/93d01997-58e0-48d8-bcca-ad8377094e64/reports/bda83ba5-3e9d-4f8d-9496-bf14e91f7b20/ccfe9e7f0a40d49acb85?ctid=f98a6a53-25f3-4212-901c-c7787fcd3495&experience=power-bi | No
Leaks | RPT_04_Rechecks Completed less than 14 days | RELEASED IN PROD | Delivered | 14 |  | Rupa | Shraddha | Preety |  | 2026-05-31 | May |  |  |  | 2026-04-22 |  | 2026-04-22 | 2026-04-22 |  | 2026-04-22 |  |  | Kelvin Hu | Yes | 2026-04-22 | https://app.powerbi.com/groups/me/apps/7767030c-f4c8-4488-b3cb-36a860cb6ff2/reports/de1ad11f-021b-4cc1-b465-67efd542031c/3122b8024291693794eb?ctid=f98a6a53-25f3-4212-901c-c7787fcd3495&experience=power-bi | https://app.powerbi.com/groups/me/apps/5b29b0dd-a398-4801-84ce-f3a7d8435827/reports/0e063b20-0b38-4000-b436-fcbec11daa46/3122b8024291693794eb?experience=power-bi | No
Leaks | RPT_04_SEI Leak Activity | RELEASED IN PROD | Delivered | 15 |  | Siva | Shraddha | Preety |  | 2026-05-31 | May |  |  |  | 2026-04-27 |  | 2026-04-27 | 2026-04-27 |  | 2026-04-27 |  |  | Kelvin Hu | Yes | 2026-04-27 | https://app.powerbi.com/groups/me/apps/7767030c-f4c8-4488-b3cb-36a860cb6ff2/reports/c76693f4-bab2-46a1-ab2a-16752d7664fd/ea184ec020032ecbdd43?experience=power-bi | https://app.powerbi.com/groups/me/apps/5b29b0dd-a398-4801-84ce-f3a7d8435827/reports/9d9f5721-feb1-4ed3-91fd-18bc33ef38f1/ea184ec020032ecbdd43?experience=power-bi | No
Leaks | RPT_04_CMS Leak Productivity | RELEASED IN PROD | Delivered | 16 |  | Siddu | Navya | Preety |  | 2026-05-31 | May |  |  |  | 2026-05-05 |  | 2026-05-05 | 2026-05-05 |  | 2026-05-05 |  |  | Kelvin Hu | Yes | 2026-05-05 | https://app.powerbi.com/groups/me/apps/eedba83d-be9a-45f9-9504-7bfa41e6051a/reports/3440832e-c72e-45f2-b154-f6b1d66314fc/51a6cefeab19522827a6?experience=power-bi | https://app.powerbi.com/groups/me/apps/2c7180b1-0d3d-45be-979e-f7dc86b3557d/reports/18e31a06-f1af-4965-ad46-5a507f24ed56/51a6cefeab19522827a6?experience=power-bi | No
Leaks | RPT_04_Main Break Corrosion and Leak Cluster | RELEASED IN PROD | Delivered | 17 |  | Siddu | Sarath | Kelvin |  | 2026-05-31 | May |  |  |  | 2026-06-02 |  | 2026-06-02 | 2026-06-06 |  | 2026-06-06 |  |  | Kelvin Hu | Yes | 2026-06-06 | https://app.powerbi.com/groups/me/apps/eedba83d-be9a-45f9-9504-7bfa41e6051a/reports/efc0a204-1a7b-4be6-8334-c7582c9093b8/ReportSection81bc1123208781ca563a?experience=power-bi |  | No
Leaks | RPT_04_Leak Summary Status | RELEASED IN PROD | Delivered | 18 |  | Fetwi | Navya | Kelvin |  | 2026-05-31 | May |  |  |  | 2026-05-01 |  | 2026-05-01 | 2026-06-02 |  | 2026-06-02 | 2026-06-11 |  | Kelvin Hu | Yes | 2026-06-11 | https://app.powerbi.com/groups/me/apps/7767030c-f4c8-4488-b3cb-36a860cb6ff2/reports/184a9cdc-83f5-40b0-940d-d901ad9fb404/ReportSection6d915001f68ea4805272?ctid=f98a6a53-25f3-4212-901c-c7787fcd3495&experience=power-bi | https://app.powerbi.com/groups/me/apps/5b29b0dd-a398-4801-84ce-f3a7d8435827/reports/f7af2903-2d63-497e-b262-100f5a3b500b/ReportSection6d915001f68ea4805272?ctid=f98a6a53-25f3-4212-901c-c7787fcd3495&experience=power-bi | No
Leaks | RPT_04_PSC Leak Printout | RELEASED IN PROD | Delivered | 19 |  | Fetwi | Shraddha | Preety |  | 2026-05-31 | May | 2026-06-02 |  | 2026-06-02 | 2026-06-05 |  | 2026-06-05 | 2026-06-02 |  | 2026-06-02 | 2026-06-19 |  | Kelvin Hu | Yes | 2026-06-19 | https://app.powerbi.com/groups/me/apps/61b18507-2848-49b9-aacc-32c49ffe1e0b/rdlreports/84ee7713-075e-496c-8610-43022c6a55ab?ctid=f98a6a53-25f3-4212-901c-c7787fcd3495&experience=power-bi |  | No | QA target is before PBI Dev target | [Historical, May/June 2026]: Fetwi was investigating a slowness issue in this report.
Leaks | RPT_04_Leak Control Report | RELEASED IN PROD | Delivered | 20 |  | Geetha | Navya | Preety |  | 2026-06-30 | June | 2026-05-06 |  | 2026-05-06 | 2026-06-10 |  | 2026-06-10 | 2026-06-22 |  | 2026-06-22 |  |  |  | Yes | 2026-06-22 |  |  | No
Leaks | RPT_04_Leak Life Cycle | RELEASED IN PROD | Delivered | 21 |  | Geetha | Shraddha | Preety |  | 2026-06-30 | June | 2026-05-20 |  | 2026-05-20 | 2026-06-09 |  | 2026-06-09 | 2026-06-25 |  | 2026-06-25 |  |  |  | Yes | 2026-06-25 |  |  | No |  | [Historical, June 2026]: Waiting on Kelvin's approval to deploy to UAT.
Leaks | RPT_04_Leak Life Cycle Legacy LMS LI | RELEASED IN PROD | Delivered | 22 |  | Fetwi | Navya | Preety |  | 2026-06-30 | June | 2026-05-26 |  | 2026-05-26 | 2026-06-10 |  | 2026-06-10 | 2026-06-25 |  | 2026-06-25 |  |  |  | Yes | 2026-06-25 |  |  | No
Leaks | RPT_04_Leak Increase Reads | RELEASED IN PROD | Delivered | 23 |  | Fetwi | Navya | Preety |  | 2026-06-30 | June | 2026-05-23 |  | 2026-05-23 | 2026-05-11 |  | 2026-05-11 | 2026-05-12 |  | 2026-05-12 | 2026-06-11 |  |  | Yes | 2026-06-11 | https://app.powerbi.com/groups/me/apps/eedba83d-be9a-45f9-9504-7bfa41e6051a/reports/a410b442-fd2f-43d1-a053-40f2e4966d4d/ea184ec020032ecbdd43?ctid=f98a6a53-25f3-4212-901c-c7787fcd3495&experience=power-bi | https://app.powerbi.com/groups/me/apps/2c7180b1-0d3d-45be-979e-f7dc86b3557d/reports/1cec238a-ce10-4ed5-8e56-50efa21bb327/ea184ec020032ecbdd43?ctid=f98a6a53-25f3-4212-901c-c7787fcd3495&experience=power-bi | No | QA target is before DB Dev target
Leaks | Leak 360 Dashboard | RELEASED IN PROD | Delivered | 24 |  | Siva | Sarath | Kelvin |  | 2026-06-30 | June | 2026-05-20 |  | 2026-05-20 | 2026-06-13 |  | 2026-06-13 | 2026-07-24 | [5 empty] | Yes | 2026-07-24 |  |  | No |  | [Source confirms QA complete but gives no exact date - using QA Expected date as the closest evidence-backed proxy]
Leaks | RPT_04_Leak Recheck Control | RELEASED IN PROD | Delivered | 25 |  | Siva | Shraddha | Preety |  | 2026-06-30 | June | 2026-05-20 |  | 2026-05-20 | 2026-05-22 |  | 2026-05-22 | 2026-07-01 |  | 2026-07-01 |  |  |  | Yes | 2026-07-01 |  |  | No |  | [Source confirms QA complete but gives no exact date - using QA Expected date as the closest evidence-backed proxy]
Leaks | RPT_04_Main_Replacement Report | RELEASED IN PROD | Delivered | 26 |  | Sree | Navya | Kelvin |  | 2026-06-30 | June | 2026-05-27 |  | 2026-05-27 | 2026-06-18 |  | 2026-06-18 | 2026-06-23 |  | 2026-06-23 |  |  |  | Yes | 2026-06-23 | https://app.powerbi.com/Redirect?action=OpenApp&appId=eedba83d-be9a-45f9-9504-7bfa41e6051a&ctid=f98a6a53-25f3-4212-901c-c7787fcd3495&experience=power-bi | https://app.powerbi.com/groups/me/apps/2c7180b1-0d3d-45be-979e-f7dc86b3557d/reports/3a63d51e-dbb3-4d03-8e38-924376751299/3122b8024291693794eb?ctid=f98a6a53-25f3-4212-901c-c7787fcd3495&experience=power-bi | No
Leaks | New Report: Leak Repair Exception | RELEASED IN PROD | Delivered | 27 |  | Geetha | Shraddha | Kelvin |  | 2026-06-30 | June | 2026-05-26 |  | 2026-05-26 | 2026-06-16 |  | 2026-06-16 | 2026-06-16 |  | 2026-06-16 | 2026-06-19 |  |  | Yes | 2026-06-19 | https://app.powerbi.com/groups/me/apps/eedba83d-be9a-45f9-9504-7bfa41e6051a/reports/f32957e8-b826-44b0-8c00-67ff417ed57e/e94cbcb8509576e1c578?ctid=f98a6a53-25f3-4212-901c-c7787fcd3495&experience=power-bi |  | No
Leaks | New Report: (Leak reading sample point mismatch ) Creating a new report that... | RELEASED IN PROD | Delivered |  |  | Siddu | Shraddha |  |  | 2026-06-30 | June | 2026-05-27 |  | 2026-05-27 | 2026-06-22 |  | 2026-06-22 | 2026-06-24 |  | 2026-06-24 |  |  |  | Yes | 2026-06-24 |  |  | No |  | [QA Actual date recovered from source text: "6/24/2026; QA Completed. Waiting for the view to be deployed to UAT"]
CMS | RPT_02_CO Flue Warning Tag Control | QA | Blocked - needs PBI Dev to fix | 1 | Kushal | Rupa | Navya | Kushal |  | 2026-07-31 | July |  |  |  | 2026-07-20 |  | 2026-07-20 | 2026-07-24 |  | 2026-07-24 | [7 empty] | Yes – needs PBI Dev to fix | Blocked - log it on Rework Log | Blocked with https://jira.prod.nationalgrid.com/browse/GDMP-2875
CMS | RPT_02_Warning Tag HEFPA | QA | On track | 2 | Kushal | Sree | Shraddha | Kushal |  | 2026-07-31 | July |  |  |  | 2026-07-21 |  | 2026-07-21 | 2026-07-24 |  | 2026-07-24 | [7 empty] | No |  | Count Msimatches Found between ODS and GDM [QA note, 07/2026]: Observing count mismatch, Sree looking into it (07/22/2026).
CMS | RPT_02_Warning tag Printout | QA | No target set | 3 | Kushal | Sree | Shraddha | Kushal |  | 2026-07-31 | July |  |  |  | 2026-07-27 | [12 empty] | No |  | Note: this report's stage dates are not in chronological order in the source tracker (e.g. a later stage dated before an earlier one) - please verify with the assigned developer. [QA note, 07/2026]: Development is completed, waiting for the view to be deployed to QA.
CMS | RPT_02_Corrosion | QA | No target set | 4 | Kushal | Siva | Sarath | Kushal |  | 2026-07-31 | July |  |  |  | 2026-07-27 | [12 empty] | No |  | Note: this report's stage dates are not in chronological order in the source tracker (e.g. a later stage dated before an earlier one) - please verify with the assigned developer.
CMS | RPT_02_House Pipe Test Comment Control | QA | On track | 5 | Kushal | Geetha | Shraddha | Preety |  | 2026-07-31 | July |  |  |  | 2026-07-15 |  | 2026-07-23 | 2026-07-22 |  | 2026-07-22 | [7 empty] | No |  | Blocked with https://jira.prod.nationalgrid.com/browse/GDMP-2876 , 17/7 - view don't have data in QA [QA note, 07/2026]: Ready for UAT review. [QA Actual date recovered from source text: "22/7 -Completed"]
CMS | RPT_02_Required Regulator Inspection Performed Control | DB Dev | Blocked - needs DB Dev to fix | 6 | Bardia | Siddu | Navya | Bardia |  | 2026-07-31 | July |  |  |  | 2026-07-17 |  | 2026-07-17 | 2026-07-22 |  | 2026-07-22 | [7 empty] | Yes – needs DB Dev to fix | Blocked - log it on Rework Log | GDM_RPT.VW_REQUIRED_REGULATOR_INSPECTIONS_PERFORMED_CONTROL [QA note, 07/2026]: Defects found and sent back for development.
CMS | RPT_02_Service Regulator Inspections | DB Dev | No target set | 7 | Bardia | Sree | Sarath | Bardia |  | 2026-07-31 | July |  |  |  | 2026-07-20 |  | 2026-07-20 | 2026-07-22 |  | 2026-07-22 | [7 empty] | No |  | select * from DEV_GDM_DEV_DB.GDM_RPT.VW_SERVICE_REGULATOR_INSPECTIONS [QA note, 07/2026]: Defects found and sent back for development.
CMS | RPT_02_Service Regulator Inspection Printout | QA | No target set | 8 | Bardia | Sree | Sarath | Bardia |  | 2026-07-31 | July |  |  |  | 2026-07-21 | [12 empty] | No |  | this has a dependency on dt_wospecattributes , 15 attributes need to be addted eg NG_REGINVLVREM
CMS | RPT_02_20 Year Regulator Inspection | QA | No target set | 9 | Bardia | Siddu | Navya | Bardia |  | 2026-07-31 | July |  |  |  | 2026-07-27 | [12 empty] | No |  | GDM_RPT.VW_20_YEAR_REGULATOR_INSPECTION_COMPLETED, GDM_RPT.VW_20_YEAR_REGULATOR_INSPECTION_MANDATED
CMS | RPT_02_Fixed Factor | QA | No target set | 10,12 | Bardia | Nick | Navya | Bardia |  | 2026-07-31 | July |  |  |  | 2026-07-27 | [12 empty] | No
CMS | RPT_02_Fixed Factor Printout | QA | No target set | 11 | Bardia | Nick | Shraddha | Preety |  | 2026-07-31 | July | 2026-07-20 |  | 2026-07-20 | 2026-07-27 |  | 2026-07-23 | [10 empty] | No |  | [QA note, 07/2026]: Development is completed, QA validation in progress.
CMS | RPT_02_Work Order Completion Printout | QA | No target set | 13 | Kushal | Rupa | Sarath | Preety |  | 2026-07-31 | July |  |  |  | 2026-07-27 | [12 empty] | No
CMS | RPT_02_GRO Control | QA | No target set | 14 | Kushal | Siva | Navya | Preety |  | 2026-07-31 | July |  |  |  | 2026-07-27 | [12 empty] | No
CMS | RPT_02_GRO Monitor | QA | No target set | 15 | Bardia | Rupa | Shraddha | Preety |  | 2026-07-31 | July |  |  |  | 2026-07-27 | [12 empty] | No
CMS | RPT_02_Public Buildings Inspection | QA | No target set | 16,17,24, 28 |  | Geetha |  |  |  | 2026-08-31 | August | [16 empty] | No
CMS | RPT_02_Investigate Wall Check and Service Check | NOT STARTED | On track | 18 |  | Siva |  |  |  | 2026-08-31 | August | [16 empty] | No
CMS | RPT_02_Cut Out Orders | NOT STARTED | On track | 19 |  | Fetwi |  |  |  | 2026-08-31 | August | [16 empty] | No
CMS | RPT_02_Gas Trouble | QA | No target set | 20 |  | Siddu |  |  |  | 2026-08-31 | August | [16 empty] | No
CMS | RPT_02_Wall Check Control | NOT STARTED | On track | 21 |  | Nick |  |  |  | 2026-08-31 | August | [16 empty] | No
CMS | RPT_02_High Pressure Steel Inside Inspection | NOT STARTED | On track | 22 |  | Siva |  |  |  | 2026-08-31 | August | [16 empty] | No
CMS | RPT_02_Large Gas Outage | NOT STARTED | On track | 23 |  | Nick |  |  |  | 2026-08-31 | August | [16 empty] | No
CMS | RPT_02_Fitting Work | NOT STARTED | On track | 25 |  | Fetwi |  |  |  | 2026-08-31 | August | [16 empty] | No
CMS | RPT_02_Field Collector Report | NOT STARTED | On track | 26 |  | Siddu |  |  |  | 2026-08-31 | August | [16 empty] | No
CMS | RPT_02_Turn On for Non-Payment | NOT STARTED | On track | 27 |  | Sree |  |  |  | 2026-08-31 | August | [16 empty] | No
CMS | RPT_02_Collector Payment Recap | NOT STARTED | On track | 29 |  | Rupa |  |  |  | 2026-08-31 | August | [16 empty] | No
CMS | RPT_02_Incentive Management | NOT STARTED | On track | 30 | [5 empty] | 2026-08-31 | August | [16 empty] | No
CMS | RPT_02_UTC Report | NOT STARTED | On track | 31 | [5 empty] | 2026-09-30 | September | [16 empty] | No
CMS | RPT_02_Adjacent Property Checks | NOT STARTED | On track | 32 | [5 empty] | 2026-09-30 | September | [16 empty] | No
CMS | RPT_02_High Bill Investigations | NOT STARTED | On track | 33 | [5 empty] | 2026-09-30 | September | [16 empty] | No
CMS | RPT_02_Emergency Order Type | NOT STARTED | On track | 34 | [5 empty] | 2026-09-30 | September | [16 empty] | No
CMS | RPT_02_Cut Out Curb Box | NOT STARTED | On track | 35 | [5 empty] | 2026-09-30 | September | [16 empty] | No
CMS | RPT_02_New York Incident | NOT STARTED | On track | 36 | [5 empty] | 2026-09-30 | September | [16 empty] | No
CMS | RPT_02_Outside Repeat Leaks | NOT STARTED | On track | 37 | [5 empty] | 2026-09-30 | September | [16 empty] | No
CMS | RPT_02_Meter Change | NOT STARTED | On track | 38 | [5 empty] | 2026-09-30 | September | [16 empty] | No
CMS | RPT_02_Field Order Value | NOT STARTED | On track | 39 | [5 empty] | 2026-09-30 | September | [16 empty] | No
CMS | RPT_02_Same Day Reconnect | NOT STARTED | On track | 40 | [5 empty] | 2026-09-30 | September | [16 empty] | No
CMS | RPT_02_Site Specific Analysis | NOT STARTED | On track | 41 | [5 empty] | 2026-09-30 | September | [16 empty] | No
CMS | RPT_02_PSC Wire Down Response Time | NOT STARTED | On track | 42 | [5 empty] | 2026-09-30 | September | [16 empty] | No
CMS | RPT_02_Hazardous Above Ground Leak | NOT STARTED | On track | 43 | [5 empty] | 2026-09-30 | September | [16 empty] | No
CMS | RPT_02_AMI Contractor Completion Report | NOT STARTED | On track | 44 | [5 empty] | 2026-09-30 | September | [16 empty] | No
CMS | RPT_02_Collection Statistic | NOT STARTED | On track | 45 | [5 empty] | 2026-09-30 | September | [16 empty] | No
CMS | RPT_02_First and Last Job | NOT STARTED | On track | 46 | [5 empty] | 2026-09-30 | September | [16 empty] | No
CMS | RPT_02_Rate Class | NOT STARTED | On track | 47 | [5 empty] | 2026-09-30 | September | [16 empty] | No
Leaks | RPT_04_Leak Recheck Times | NOT STARTED | On track | 48 | [5 empty] | 2026-09-30 | September | [16 empty] | No

## Find a Report (hidden)
Find a Report
Pick a report below - everything updates automatically.
Report Name:
Domain
Current Status
Status Flag
Business Value Rank
PO
DB Developer
PBI Developer
QA Tester
DB Dev Expected
DB Dev Actual
PBI Dev Expected
PBI Dev Actual
QA Expected
QA Actual
DPO Approval Expected
DPO Approval Reviewer
Confirmed Deployed?
Confirmed Deployed Date
Blocked?
Data Check
Times Sent Back
Open Reworks
Last Sent Back Date
Last From -> To
Comments

## Rework Log
ONE ROW PER FIX ATTEMPT. AMBER = sender (usually QA): fill A-F when sending back; you also own Resolved? (G) - set Yes when you accept the fix back, or "Did not pass re-test" if still broken (then log a NEW row for the next attempt). BLUE = fixer: at pickup enter your Expected Fix Date and move your old completion date here (cut & paste); when done, enter Date Fixed - the clock stops and the row turns BLUE = waiting on the sender to re-test. Row colors answer "whose move is it?": AMBER = fixer's, BLUE = sender's, GREEN = accepted, GREY = attempt closed, new row carries it. PURPLE columns are computed by the sheet and locked - you never type in purple. | [12 empty] | LIVE SUMMARY (auto) - the sheet computes this. Purple = never type here.
Report Name | Date Sent Back | From Stage | To Stage | Sent Back By | What Was Wrong | Resolved? | First Completed On (cut & paste from main tab) | Expected Fix Date | Date Fixed | Fixed By | What Was Fixed | Aging (auto) | Report Name | Times Sent Back | Open Reworks | Last Sent Back Date | Last From -> To
RPT_02_Required Regulator Inspection Performed Control | 2026-07-25 | QA | DB Dev | Bardia | the count does not match(count of records between ods and gdm | Did not pass re-test |  | 2026-07-25 | 2026-07-28 | Sreevarsha |  | Sent back again | RPT_04_Active Leaks | 0 | 0
[13 empty] | RPT_04_Count of Active Leaks On Hand | 0 | 0
|  | QA |  |  |  | Did not pass re-test | [6 empty] | RPT_04_Leak Scheduling | 0 | 0
|  | QA |  |  |  | No | [6 empty] | RPT_04_Leak Days Remaining | 0 | 0
|  | QA |  |  |  | No | [6 empty] | RPT_04_Cleared Leaks | 0 | 0
|  | QA |  |  |  | No | [6 empty] | RPT_04_Leaks Repaired Detail | 0 | 0
|  | QA |  |  |  | No | [6 empty] | RPT_04_Leaks Aging | 0 | 0
|  | QA |  |  |  | No | [6 empty] | RPT_04_Prior Leak Readings | 0 | 0
|  | QA |  |  |  | No | [6 empty] | RSS_04_Leak Grade Change History | 0 | 0
|  | QA |  |  |  | No | [6 empty] | RPT_04_Surveillances With Zero Readings | 0 | 0
|  | QA |  |  |  | No | [6 empty] | RPT_04 High Emitter leaks | 0 | 0
|  | QA |  |  |  | No | [6 empty] | RPT_04_School Zone Leaks Without Repair | 0 | 0
|  | QA |  |  |  | No | [6 empty] | RPT_04_PSC Quarterly Leak | 0 | 0
|  | QA |  |  |  | No | [6 empty] | RPT_04_Rechecks Completed less than 14 days | 0 | 0
|  | QA |  |  |  | No | [6 empty] | RPT_04_SEI Leak Activity | 0 | 0
|  | QA |  |  |  | No | [6 empty] | RPT_04_CMS Leak Productivity | 0 | 0
|  | QA |  |  |  | No | [6 empty] | RPT_04_Main Break Corrosion and Leak Cluster | 0 | 0
|  | QA |  |  |  | No | [6 empty] | RPT_04_Leak Summary Status | 0 | 0
|  | QA |  |  |  | No | [6 empty] | RPT_04_PSC Leak Printout | 0 | 0
|  | QA |  |  |  | No | [6 empty] | RPT_04_Leak Control Report | 0 | 0
|  | QA |  |  |  | No | [6 empty] | RPT_04_Leak Life Cycle | 0 | 0
|  | QA |  |  |  | No | [6 empty] | RPT_04_Leak Life Cycle Legacy LMS LI | 0 | 0
|  | QA |  |  |  | No | [6 empty] | RPT_04_Leak Increase Reads | 0 | 0
|  | QA |  |  |  | No | [6 empty] | Leak 360 Dashboard | 0 | 0
|  | QA |  |  |  | No | [6 empty] | RPT_04_Leak Recheck Control | 0 | 0
|  | QA |  |  |  | No | [6 empty] | RPT_04_Main_Replacement Report | 0 | 0
|  | QA |  |  |  | No | [6 empty] | New Report: Leak Repair Exception | 0 | 0
|  | QA |  |  |  | No | [6 empty] | New Report: (Leak reading sample point mismatch ) Creating a new report that... | 0 | 0
|  | QA |  |  |  | No | [6 empty] | RPT_02_CO Flue Warning Tag Control | 0 | 0
|  | QA |  |  |  | No | [6 empty] | RPT_02_Warning Tag HEFPA | 0 | 0
|  | QA |  |  |  | No | [6 empty] | RPT_02_Warning tag Printout | 0 | 0
|  | QA |  |  |  | No | [6 empty] | RPT_02_Corrosion | 0 | 0
|  | QA |  |  |  | No | [6 empty] | RPT_02_House Pipe Test Comment Control | 0 | 0
|  | QA |  |  |  | No | [6 empty] | RPT_02_Required Regulator Inspection Performed Control | 1 | 0
|  | QA |  |  |  | No | [6 empty] | RPT_02_Service Regulator Inspections | 0 | 0
|  | QA |  |  |  | No | [6 empty] | RPT_02_Service Regulator Inspection Printout | 0 | 0
|  | QA |  |  |  | No | [6 empty] | RPT_02_20 Year Regulator Inspection | 0 | 0
|  | QA |  |  |  | No | [6 empty] | RPT_02_Fixed Factor | 0 | 0
|  | QA |  |  |  | No | [6 empty] | RPT_02_Fixed Factor Printout | 0 | 0
|  | QA |  |  |  | No | [6 empty] | RPT_02_Work Order Completion Printout | 0 | 0
|  | QA |  |  |  | No | [6 empty] | RPT_02_GRO Control | 0 | 0
|  | QA |  |  |  | No | [6 empty] | RPT_02_GRO Monitor | 0 | 0
|  | QA |  |  |  | No | [6 empty] | RPT_02_Public Buildings Inspection | 0 | 0
|  | QA |  |  |  | No | [6 empty] | RPT_02_Investigate Wall Check and Service Check | 0 | 0
|  | QA |  |  |  | No | [6 empty] | RPT_02_Cut Out Orders | 0 | 0
|  | QA |  |  |  | No | [6 empty] | RPT_02_Gas Trouble | 0 | 0
|  | QA |  |  |  | No | [6 empty] | RPT_02_Wall Check Control | 0 | 0
|  | QA |  |  |  | No | [6 empty] | RPT_02_High Pressure Steel Inside Inspection | 0 | 0
|  | QA |  |  |  | No | [6 empty] | RPT_02_Large Gas Outage | 0 | 0
|  | QA |  |  |  | No | [6 empty] | RPT_02_Fitting Work | 0 | 0
|  | QA |  |  |  | No | [6 empty] | RPT_02_Field Collector Report | 0 | 0
|  | QA |  |  |  | No | [6 empty] | RPT_02_Turn On for Non-Payment | 0 | 0
|  | QA |  |  |  | No | [6 empty] | RPT_02_Collector Payment Recap | 0 | 0
|  | QA |  |  |  | No | [6 empty] | RPT_02_Incentive Management | 0 | 0
|  | QA |  |  |  | No | [6 empty] | RPT_02_UTC Report | 0 | 0
|  | QA |  |  |  | No | [6 empty] | RPT_02_Adjacent Property Checks | 0 | 0
|  | QA |  |  |  | No | [6 empty] | RPT_02_High Bill Investigations | 0 | 0
|  | QA |  |  |  | No | [6 empty] | RPT_02_Emergency Order Type | 0 | 0
|  | QA |  |  |  | No | [6 empty] | RPT_02_Cut Out Curb Box | 0 | 0
|  | QA |  |  |  | No | [6 empty] | RPT_02_New York Incident | 0 | 0
|  | QA |  |  |  | No | [6 empty] | RPT_02_Outside Repeat Leaks | 0 | 0
|  | QA |  |  |  | No | [6 empty] | RPT_02_Meter Change | 0 | 0
|  | QA |  |  |  | No | [6 empty] | RPT_02_Field Order Value | 0 | 0
|  | QA |  |  |  | No | [6 empty] | RPT_02_Same Day Reconnect | 0 | 0
|  | QA |  |  |  | No | [6 empty] | RPT_02_Site Specific Analysis | 0 | 0
|  | QA |  |  |  | No | [6 empty] | RPT_02_PSC Wire Down Response Time | 0 | 0
|  | QA |  |  |  | No | [6 empty] | RPT_02_Hazardous Above Ground Leak | 0 | 0
|  | QA |  |  |  | No | [6 empty] | RPT_02_AMI Contractor Completion Report | 0 | 0
|  | QA |  |  |  | No | [6 empty] | RPT_02_Collection Statistic | 0 | 0
|  | QA |  |  |  | No | [6 empty] | RPT_02_First and Last Job | 0 | 0
|  | QA |  |  |  | No | [6 empty] | RPT_02_Rate Class | 0 | 0
|  | QA |  |  |  | No | [6 empty] | RPT_04_Leak Recheck Times | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
|  | QA |  |  |  | No | [6 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | 0

## Fact Table (hidden)
Reference snapshot only - the app rebuilds this automatically from Combined Delivery Data on every upload. Editing this tab directly has no effect.
Domain | Status | Report Name | DB Developers | PBI Developers | Schema | PO | Status Start Date | Expected Release Date | Actual Release Date
Leaks | DB Dev | RPT_04_Active Leaks | Fetwi | Sarath |  |  |  | 2026-04-03 | 2026-04-03
Leaks | PBI Dev | RPT_04_Active Leaks | Fetwi | Sarath |  |  | 2026-04-03 | 2026-04-02 | 2026-04-02
Leaks | QA | RPT_04_Active Leaks | Fetwi | Sarath |  |  | 2026-04-02 | 2026-04-10 | 2026-04-10
Leaks | DPO Approval | RPT_04_Active Leaks | Fetwi | Sarath |  |  | 2026-04-10
Leaks | RELEASED IN PROD | RPT_04_Active Leaks | Fetwi | Sarath
Leaks | DB Dev | RPT_04_Count of Active Leaks On Hand | Fetwi | Sarath |  |  |  | 2026-04-03 | 2026-04-03
Leaks | PBI Dev | RPT_04_Count of Active Leaks On Hand | Fetwi | Sarath |  |  | 2026-04-03 | 2026-04-02 | 2026-04-02
Leaks | QA | RPT_04_Count of Active Leaks On Hand | Fetwi | Sarath |  |  | 2026-04-02 | 2026-04-10 | 2026-04-10
Leaks | DPO Approval | RPT_04_Count of Active Leaks On Hand | Fetwi | Sarath |  |  | 2026-04-10
Leaks | RELEASED IN PROD | RPT_04_Count of Active Leaks On Hand | Fetwi | Sarath
Leaks | DB Dev | RPT_04_Leak Scheduling | Sreevarsha | Sarath |  |  |  | 2026-04-03 | 2026-04-03
Leaks | PBI Dev | RPT_04_Leak Scheduling | Sreevarsha | Sarath |  |  | 2026-04-03 | 2026-04-08 | 2026-04-08
Leaks | QA | RPT_04_Leak Scheduling | Sreevarsha | Sarath |  |  | 2026-04-08 | 2026-04-10 | 2026-04-10
Leaks | DPO Approval | RPT_04_Leak Scheduling | Sreevarsha | Sarath |  |  | 2026-04-10
Leaks | RELEASED IN PROD | RPT_04_Leak Scheduling | Sreevarsha | Sarath
Leaks | DB Dev | RPT_04_Leak Days Remaining | Siva | Navya |  |  |  | 2026-04-03 | 2026-04-03
Leaks | PBI Dev | RPT_04_Leak Days Remaining | Siva | Navya |  |  | 2026-04-03 | 2026-04-14 | 2026-04-14
Leaks | QA | RPT_04_Leak Days Remaining | Siva | Navya |  |  | 2026-04-14 | 2026-04-10 | 2026-04-10
Leaks | DPO Approval | RPT_04_Leak Days Remaining | Siva | Navya |  |  | 2026-04-10
Leaks | RELEASED IN PROD | RPT_04_Leak Days Remaining | Siva | Navya
Leaks | DB Dev | RPT_04_Cleared Leaks | Sreevarsha | Sarath |  |  |  | 2026-04-03 | 2026-04-03
Leaks | PBI Dev | RPT_04_Cleared Leaks | Sreevarsha | Sarath |  |  | 2026-04-03 | 2026-04-08 | 2026-04-08
Leaks | QA | RPT_04_Cleared Leaks | Sreevarsha | Sarath |  |  | 2026-04-08 | 2026-04-10 | 2026-04-10
Leaks | DPO Approval | RPT_04_Cleared Leaks | Sreevarsha | Sarath |  |  | 2026-04-10
Leaks | RELEASED IN PROD | RPT_04_Cleared Leaks | Sreevarsha | Sarath
Leaks | DB Dev | RPT_04_Leaks Repaired Detail | Rupa | Navya |  |  |  | 2026-04-03 | 2026-04-03
Leaks | PBI Dev | RPT_04_Leaks Repaired Detail | Rupa | Navya |  |  | 2026-04-03 | 2026-04-14 | 2026-04-14
Leaks | QA | RPT_04_Leaks Repaired Detail | Rupa | Navya |  |  | 2026-04-14 | 2026-04-10 | 2026-04-10
Leaks | DPO Approval | RPT_04_Leaks Repaired Detail | Rupa | Navya |  |  | 2026-04-10
Leaks | RELEASED IN PROD | RPT_04_Leaks Repaired Detail | Rupa | Navya
Leaks | DB Dev | RPT_04_Leaks Aging | Sreevarsha | Navya |  |  |  | 2026-04-10 | 2026-04-10
Leaks | PBI Dev | RPT_04_Leaks Aging | Sreevarsha | Navya |  |  | 2026-04-10 | 2026-04-14 | 2026-04-14
Leaks | QA | RPT_04_Leaks Aging | Sreevarsha | Navya |  |  | 2026-04-14 | 2026-04-10 | 2026-04-10
Leaks | DPO Approval | RPT_04_Leaks Aging | Sreevarsha | Navya |  |  | 2026-04-10
Leaks | RELEASED IN PROD | RPT_04_Leaks Aging | Sreevarsha | Navya
Leaks | DB Dev | RPT_04_Prior Leak Readings | Siddu | Navya |  |  |  | 2026-04-10 | 2026-04-10
Leaks | PBI Dev | RPT_04_Prior Leak Readings | Siddu | Navya |  |  | 2026-04-10 | 2026-04-14 | 2026-04-14
Leaks | QA | RPT_04_Prior Leak Readings | Siddu | Navya |  |  | 2026-04-14 | 2026-04-10 | 2026-04-10
Leaks | DPO Approval | RPT_04_Prior Leak Readings | Siddu | Navya |  |  | 2026-04-10
Leaks | RELEASED IN PROD | RPT_04_Prior Leak Readings | Siddu | Navya
Leaks | DB Dev | RSS_04_Leak Grade Change History | Siva | Navya |  |  |  | 2026-04-15 | 2026-04-15
Leaks | PBI Dev | RSS_04_Leak Grade Change History | Siva | Navya |  |  | 2026-04-15 | 2026-04-14 | 2026-04-14
Leaks | QA | RSS_04_Leak Grade Change History | Siva | Navya |  |  | 2026-04-14 | 2026-04-10 | 2026-04-10
Leaks | DPO Approval | RSS_04_Leak Grade Change History | Siva | Navya |  |  | 2026-04-10
Leaks | RELEASED IN PROD | RSS_04_Leak Grade Change History | Siva | Navya
Leaks | DB Dev | RPT_04_Surveillances With Zero Readings | Sreevarsha | Navya
Leaks | PBI Dev | RPT_04_Surveillances With Zero Readings | Sreevarsha | Navya |  |  |  | 2026-04-27 | 2026-04-27
Leaks | QA | RPT_04_Surveillances With Zero Readings | Sreevarsha | Navya |  |  | 2026-04-27 | 2026-04-27 | 2026-04-27
Leaks | DPO Approval | RPT_04_Surveillances With Zero Readings | Sreevarsha | Navya |  |  | 2026-04-27
Leaks | RELEASED IN PROD | RPT_04_Surveillances With Zero Readings | Sreevarsha | Navya
Leaks | DB Dev | RPT_04 High Emitter leaks | Sreevarsha | Navya
Leaks | PBI Dev | RPT_04 High Emitter leaks | Sreevarsha | Navya |  |  |  | 2026-04-29 | 2026-04-29
Leaks | QA | RPT_04 High Emitter leaks | Sreevarsha | Navya |  |  | 2026-04-29 | 2026-04-29 | 2026-04-29
Leaks | DPO Approval | RPT_04 High Emitter leaks | Sreevarsha | Navya |  |  | 2026-04-29
Leaks | RELEASED IN PROD | RPT_04 High Emitter leaks | Sreevarsha | Navya
Leaks | DB Dev | RPT_04_School Zone Leaks Without Repair | Sreevarsha | Sarath
Leaks | PBI Dev | RPT_04_School Zone Leaks Without Repair | Sreevarsha | Sarath |  |  |  | 2026-05-19 | 2026-05-19
Leaks | QA | RPT_04_School Zone Leaks Without Repair | Sreevarsha | Sarath |  |  | 2026-05-19 | 2026-05-19 | 2026-05-19
Leaks | DPO Approval | RPT_04_School Zone Leaks Without Repair | Sreevarsha | Sarath |  |  | 2026-05-19
Leaks | RELEASED IN PROD | RPT_04_School Zone Leaks Without Repair | Sreevarsha | Sarath
Leaks | DB Dev | RPT_04_PSC Quarterly Leak | Geetha | Sarath
Leaks | PBI Dev | RPT_04_PSC Quarterly Leak | Geetha | Sarath |  |  |  | 2026-06-02 | 2026-06-02
Leaks | QA | RPT_04_PSC Quarterly Leak | Geetha | Sarath |  |  | 2026-06-02 | 2026-06-02 | 2026-06-02
Leaks | DPO Approval | RPT_04_PSC Quarterly Leak | Geetha | Sarath |  |  | 2026-06-02
Leaks | RELEASED IN PROD | RPT_04_PSC Quarterly Leak | Geetha | Sarath |  |  |  | 2026-06-11 | 2026-06-11
Leaks | DB Dev | RPT_04_Rechecks Completed less than 14 days | Rupa | Shraddha
Leaks | PBI Dev | RPT_04_Rechecks Completed less than 14 days | Rupa | Shraddha |  |  |  | 2026-04-22 | 2026-04-22
Leaks | QA | RPT_04_Rechecks Completed less than 14 days | Rupa | Shraddha |  |  | 2026-04-22 | 2026-04-22 | 2026-04-22
Leaks | DPO Approval | RPT_04_Rechecks Completed less than 14 days | Rupa | Shraddha |  |  | 2026-04-22
Leaks | RELEASED IN PROD | RPT_04_Rechecks Completed less than 14 days | Rupa | Shraddha
Leaks | DB Dev | RPT_04_SEI Leak Activity | Siva | Shraddha
Leaks | PBI Dev | RPT_04_SEI Leak Activity | Siva | Shraddha |  |  |  | 2026-04-27 | 2026-04-27
Leaks | QA | RPT_04_SEI Leak Activity | Siva | Shraddha |  |  | 2026-04-27 | 2026-04-27 | 2026-04-27
Leaks | DPO Approval | RPT_04_SEI Leak Activity | Siva | Shraddha |  |  | 2026-04-27
Leaks | RELEASED IN PROD | RPT_04_SEI Leak Activity | Siva | Shraddha
Leaks | DB Dev | RPT_04_CMS Leak Productivity | Siddu | Navya
Leaks | PBI Dev | RPT_04_CMS Leak Productivity | Siddu | Navya |  |  |  | 2026-05-05 | 2026-05-05
Leaks | QA | RPT_04_CMS Leak Productivity | Siddu | Navya |  |  | 2026-05-05 | 2026-05-05 | 2026-05-05
Leaks | DPO Approval | RPT_04_CMS Leak Productivity | Siddu | Navya |  |  | 2026-05-05
Leaks | RELEASED IN PROD | RPT_04_CMS Leak Productivity | Siddu | Navya
Leaks | DB Dev | RPT_04_Main Break Corrosion and Leak Cluster | Siddu | Sarath
Leaks | PBI Dev | RPT_04_Main Break Corrosion and Leak Cluster | Siddu | Sarath |  |  |  | 2026-06-02 | 2026-06-02
Leaks | QA | RPT_04_Main Break Corrosion and Leak Cluster | Siddu | Sarath |  |  | 2026-06-02 | 2026-06-06 | 2026-06-06
Leaks | DPO Approval | RPT_04_Main Break Corrosion and Leak Cluster | Siddu | Sarath |  |  | 2026-06-06
Leaks | RELEASED IN PROD | RPT_04_Main Break Corrosion and Leak Cluster | Siddu | Sarath
Leaks | DB Dev | RPT_04_Leak Summary Status | Fetwi | Navya
Leaks | PBI Dev | RPT_04_Leak Summary Status | Fetwi | Navya |  |  |  | 2026-05-01 | 2026-05-01
Leaks | QA | RPT_04_Leak Summary Status | Fetwi | Navya |  |  | 2026-05-01 | 2026-06-02 | 2026-06-02
Leaks | DPO Approval | RPT_04_Leak Summary Status | Fetwi | Navya |  |  | 2026-06-02
Leaks | RELEASED IN PROD | RPT_04_Leak Summary Status | Fetwi | Navya |  |  |  | 2026-06-11 | 2026-06-11
Leaks | DB Dev | RPT_04_PSC Leak Printout | Fetwi | Shraddha |  |  |  | 2026-06-02 | 2026-06-02
Leaks | PBI Dev | RPT_04_PSC Leak Printout | Fetwi | Shraddha |  |  | 2026-06-02 | 2026-06-05 | 2026-06-05
Leaks | QA | RPT_04_PSC Leak Printout | Fetwi | Shraddha |  |  | 2026-06-05 | 2026-06-02 | 2026-06-02
Leaks | DPO Approval | RPT_04_PSC Leak Printout | Fetwi | Shraddha |  |  | 2026-06-02
Leaks | RELEASED IN PROD | RPT_04_PSC Leak Printout | Fetwi | Shraddha |  |  |  | 2026-06-19 | 2026-06-19
Leaks | DB Dev | RPT_04_Leak Control Report | Geetha | Navya |  |  |  | 2026-05-06 | 2026-05-06
Leaks | PBI Dev | RPT_04_Leak Control Report | Geetha | Navya |  |  | 2026-05-06 | 2026-06-10 | 2026-06-10
Leaks | QA | RPT_04_Leak Control Report | Geetha | Navya |  |  | 2026-06-10 | 2026-06-22 | 2026-06-22
Leaks | DPO Approval | RPT_04_Leak Control Report | Geetha | Navya |  |  | 2026-06-22
Leaks | RELEASED IN PROD | RPT_04_Leak Control Report | Geetha | Navya
Leaks | DB Dev | RPT_04_Leak Life Cycle | Geetha | Shraddha |  |  |  | 2026-05-20 | 2026-05-20
Leaks | PBI Dev | RPT_04_Leak Life Cycle | Geetha | Shraddha |  |  | 2026-05-20 | 2026-06-09 | 2026-06-09
Leaks | QA | RPT_04_Leak Life Cycle | Geetha | Shraddha |  |  | 2026-06-09 | 2026-06-25 | 2026-06-25
Leaks | DPO Approval | RPT_04_Leak Life Cycle | Geetha | Shraddha |  |  | 2026-06-25
Leaks | RELEASED IN PROD | RPT_04_Leak Life Cycle | Geetha | Shraddha
Leaks | DB Dev | RPT_04_Leak Life Cycle Legacy LMS LI | Fetwi | Navya |  |  |  | 2026-05-26 | 2026-05-26
Leaks | PBI Dev | RPT_04_Leak Life Cycle Legacy LMS LI | Fetwi | Navya |  |  | 2026-05-26 | 2026-06-10 | 2026-06-10
Leaks | QA | RPT_04_Leak Life Cycle Legacy LMS LI | Fetwi | Navya |  |  | 2026-06-10 | 2026-06-25 | 2026-06-25
Leaks | DPO Approval | RPT_04_Leak Life Cycle Legacy LMS LI | Fetwi | Navya |  |  | 2026-06-25
Leaks | RELEASED IN PROD | RPT_04_Leak Life Cycle Legacy LMS LI | Fetwi | Navya
Leaks | DB Dev | RPT_04_Leak Increase Reads | Fetwi | Navya |  |  |  | 2026-05-23 | 2026-05-23
Leaks | PBI Dev | RPT_04_Leak Increase Reads | Fetwi | Navya |  |  | 2026-05-23 | 2026-05-11 | 2026-05-11
Leaks | QA | RPT_04_Leak Increase Reads | Fetwi | Navya |  |  | 2026-05-11 | 2026-05-12 | 2026-05-12
Leaks | DPO Approval | RPT_04_Leak Increase Reads | Fetwi | Navya |  |  | 2026-05-12
Leaks | RELEASED IN PROD | RPT_04_Leak Increase Reads | Fetwi | Navya |  |  |  | 2026-06-11 | 2026-06-11
Leaks | DB Dev | Leak 360 Dashboard | Siva | Sarath |  |  |  | 2026-05-20 | 2026-05-20
Leaks | PBI Dev | Leak 360 Dashboard | Siva | Sarath |  |  | 2026-05-20 | 2026-06-13 | 2026-06-13
Leaks | QA | Leak 360 Dashboard | Siva | Sarath |  |  | 2026-06-13 | 2026-06-15 | 2026-06-15
Leaks | DB Dev | RPT_04_Leak Recheck Control | Siva | Shraddha |  |  |  | 2026-05-20 | 2026-05-20
Leaks | PBI Dev | RPT_04_Leak Recheck Control | Siva | Shraddha |  |  | 2026-05-20 | 2026-05-22 | 2026-05-22
Leaks | QA | RPT_04_Leak Recheck Control | Siva | Shraddha |  |  | 2026-05-22 | 2026-07-01 | 2026-07-01
Leaks | DPO Approval | RPT_04_Leak Recheck Control | Siva | Shraddha |  |  | 2026-07-01
Leaks | RELEASED IN PROD | RPT_04_Leak Recheck Control | Siva | Shraddha
Leaks | DB Dev | RPT_04_Main_Replacement Report | Sree | Navya |  |  |  | 2026-05-27 | 2026-05-27
Leaks | PBI Dev | RPT_04_Main_Replacement Report | Sree | Navya |  |  | 2026-05-27 | 2026-06-18 | 2026-06-18
Leaks | QA | RPT_04_Main_Replacement Report | Sree | Navya |  |  | 2026-06-18 | 2026-06-23 | 2026-06-23
Leaks | DPO Approval | RPT_04_Main_Replacement Report | Sree | Navya |  |  | 2026-06-23
Leaks | RELEASED IN PROD | RPT_04_Main_Replacement Report | Sree | Navya
Leaks | DB Dev | New Report: Leak Repair Exception | Geetha | Shraddha |  |  |  | 2026-05-26 | 2026-05-26
Leaks | PBI Dev | New Report: Leak Repair Exception | Geetha | Shraddha |  |  | 2026-05-26 | 2026-06-16 | 2026-06-16
Leaks | QA | New Report: Leak Repair Exception | Geetha | Shraddha |  |  | 2026-06-16 | 2026-06-16 | 2026-06-16
Leaks | DPO Approval | New Report: Leak Repair Exception | Geetha | Shraddha |  |  | 2026-06-16
Leaks | RELEASED IN PROD | New Report: Leak Repair Exception | Geetha | Shraddha |  |  |  | 2026-06-19 | 2026-06-19
Leaks | DB Dev | New Report: (Leak reading sample point mismatch ) Creating a new report that... | Siddu | Shraddha |  |  |  | 2026-05-27 | 2026-05-27
Leaks | PBI Dev | New Report: (Leak reading sample point mismatch ) Creating a new report that... | Siddu | Shraddha |  |  | 2026-05-27 | 2026-06-22 | 2026-06-22
Leaks | QA | New Report: (Leak reading sample point mismatch ) Creating a new report that... | Siddu | Shraddha |  |  | 2026-06-22 | 2026-06-24 | 2026-06-24
Leaks | DPO Approval | New Report: (Leak reading sample point mismatch ) Creating a new report that... | Siddu | Shraddha |  |  | 2026-06-24
Leaks | RELEASED IN PROD | New Report: (Leak reading sample point mismatch ) Creating a new report that... | Siddu | Shraddha
CMS | DB Dev | RPT_02_CO Flue Warning Tag Control | Rupa | Navya |  | Kushal
CMS | PBI Dev | RPT_02_CO Flue Warning Tag Control | Rupa | Navya |  | Kushal |  | 2026-07-10 | 2026-07-10
CMS | QA | RPT_02_CO Flue Warning Tag Control | Rupa | Navya |  | Kushal | 2026-07-10 | 2026-07-20 | 2026-07-20
CMS | DB Dev | RPT_02_Warning Tag HEFPA | Sree | Shraddha |  | Kushal
CMS | PBI Dev | RPT_02_Warning Tag HEFPA | Sree | Shraddha |  | Kushal |  | 2026-07-15 | 2026-07-15
CMS | QA | RPT_02_Warning Tag HEFPA | Sree | Shraddha |  | Kushal | 2026-07-15 | 2026-07-20 | 2026-07-20
CMS | DB Dev | RPT_02_Warning tag Printout | Sree | Shraddha |  | Kushal
CMS | PBI Dev | RPT_02_Warning tag Printout | Sree | Shraddha |  | Kushal |  | 2026-07-22 | 2026-07-22
CMS | QA | RPT_02_Warning tag Printout | Sree | Shraddha |  | Kushal | 2026-07-22 | 2026-07-20 | 2026-07-20
CMS | DB Dev | RPT_02_Corrosion | Siva | Sarath |  | Kushal
CMS | PBI Dev | RPT_02_Corrosion | Siva | Sarath |  | Kushal |  | 2026-07-24 | 2026-07-24
CMS | QA | RPT_02_Corrosion | Siva | Sarath |  | Kushal | 2026-07-24 | 2026-07-20 | 2026-07-20
CMS | DB Dev | RPT_02_House Pipe Test Comment Control | Geetha | Shraddha |  | Kushal
CMS | PBI Dev | RPT_02_House Pipe Test Comment Control | Geetha | Shraddha |  | Kushal |  | 2026-07-13 | 2026-07-13
CMS | QA | RPT_02_House Pipe Test Comment Control | Geetha | Shraddha |  | Kushal | 2026-07-13 | 2026-07-22 | 2026-07-22
CMS | DB Dev | RPT_02_Required Regulator Inspection Performed Control | Siddu | Navya |  | Bardia
CMS | DB Dev | RPT_02_Service Regulator Inspections | Sree | Sarath |  | Bardia
CMS | DB Dev | RPT_02_Service Regulator Inspection Printout | Sree | Sarath |  | Bardia
CMS | PBI Dev | RPT_02_Service Regulator Inspection Printout | Sree | Sarath |  | Bardia |  | 2026-07-18 | 2026-07-18
CMS | QA | RPT_02_Service Regulator Inspection Printout | Sree | Sarath |  | Bardia | 2026-07-18 | 2026-07-20 | 2026-07-20
CMS | DB Dev | RPT_02_20 Year Regulator Inspection | Siddu | Navya |  | Bardia
CMS | PBI Dev | RPT_02_20 Year Regulator Inspection | Siddu | Navya |  | Bardia |  | 2026-07-17 | 2026-07-17
CMS | QA | RPT_02_20 Year Regulator Inspection | Siddu | Navya |  | Bardia | 2026-07-17 | 2026-07-20 | 2026-07-20
CMS | DB Dev | RPT_02_Fixed Factor | Nick | Navya |  | Bardia
CMS | PBI Dev | RPT_02_Fixed Factor | Nick | Navya |  | Bardia |  | 2026-07-21 | 2026-07-21
CMS | QA | RPT_02_Fixed Factor | Nick | Navya |  | Bardia | 2026-07-21 | 2026-07-20 | 2026-07-20
CMS | DB Dev | RPT_02_Fixed Factor Printout | Nick | Shraddha |  | Bardia
CMS | PBI Dev | RPT_02_Fixed Factor Printout | Nick | Shraddha |  | Bardia |  | 2026-07-22 | 2026-07-22
CMS | QA | RPT_02_Fixed Factor Printout | Nick | Shraddha |  | Bardia | 2026-07-22 | 2026-07-20 | 2026-07-20
CMS | DB Dev | RPT_02_Work Order Completion Printout | Rupa | Sarath |  | Kushal
CMS | PBI Dev | RPT_02_Work Order Completion Printout | Rupa | Sarath |  | Kushal |  | 2026-07-23 | 2026-07-23
CMS | QA | RPT_02_Work Order Completion Printout | Rupa | Sarath |  | Kushal | 2026-07-23 | 2026-07-20 | 2026-07-20
CMS | DB Dev | RPT_02_GRO Control | Siva | Navya |  | Kushal
CMS | PBI Dev | RPT_02_GRO Control | Siva | Navya |  | Kushal |  | 2026-07-22 | 2026-07-22
CMS | QA | RPT_02_GRO Control | Siva | Navya |  | Kushal | 2026-07-22 | 2026-07-20 | 2026-07-20
CMS | DB Dev | RPT_02_GRO Monitor | Rupa | Shraddha |  | Bardia
CMS | PBI Dev | RPT_02_GRO Monitor | Rupa | Shraddha |  | Bardia |  | 2026-07-22 | 2026-07-22
CMS | QA | RPT_02_GRO Monitor | Rupa | Shraddha |  | Bardia | 2026-07-22 | 2026-07-27 | 2026-07-27
CMS | DB Dev | RPT_02_Public Buildings Inspection | Geetha
CMS | PBI Dev | RPT_02_Public Buildings Inspection | Geetha
CMS | QA | RPT_02_Public Buildings Inspection | Geetha
CMS | DB Dev | RPT_02_Gas Trouble | Siddu
CMS | PBI Dev | RPT_02_Gas Trouble | Siddu
CMS | QA | RPT_02_Gas Trouble | Siddu

## Dim Table
This tab is manually maintained - edit Expected Report Count / Expected Release Date directly, or add new domain/month rows, as delivery plans change. Unlike Fact Table, the app always reads this sheet as-is.
Domain | Expected Report Count | Expected Release Date
Leaks | 8 | 2026-04-30
Leaks | 10 | 2026-05-30
Leaks | 9 | 2026-06-30
CMS | 15 | 2026-07-30
CMS | 15 | 2026-08-30
CMS | 17 | 2026-09-30
CMS | 20 | 2026-10-30
CMS | 20 | 2026-11-30
Maintenance and Construction | 18 | 2026-12-30
Maintenance and Construction | 18 | 2027-01-30
Maintenance and Construction | 19 | 2027-02-28
Meter Management | 9 | 2027-03-30
Assets and Engineering | 8 | 2027-03-30

## Data Validation
Domain | DB Developer | PBI Developer | PO | Yes / No | Current Status | All Developers | QA Tester | Blocked? | Rework Stage | DPO Approval | Resolved?
-> feeds column A on Combined Delivery Data | -> feeds column G on Combined Delivery Data | -> feeds column H on Combined Delivery Data | -> feeds column F on Combined Delivery Data | -> feeds column U (Confirmed Deployed?) on Combined Delivery Data | -> feeds column C on Combined Delivery Data | -> legacy combined list (Rework Log now uses per-stage lists via B/C/H/K) | -> feeds column I on Combined Delivery Data | -> feeds column Y on Combined Delivery Data | -> feeds From/To Stage on Rework Log | -> feeds Sent Back By / Fixed By when stage is DPO Approval | -> feeds Resolved? on Rework Log (sender-owned)
Leaks | Fetwi | Navya | Kushal | Yes | NOT STARTED | Fetwi | Preety | No | DB Dev | Kelvin Hu | No
CMS | Siva | Sarath | Bardia | No | DB Dev | Siva | Kelvin | Yes – other | PBI Dev |  | Yes
Maintenance and Construction | Sreevarsha | Shraddha |  |  | PBI Dev | Sreevarsha | Kushal | Yes – needs DB Dev to fix | QA |  | Did not pass re-test
Meter Management | Siddu |  |  |  | QA | Siddu | Bardia | Yes – needs PBI Dev to fix | DPO Approval
Assets and Engineering | Sree |  |  |  | DPO Approval | Sree |  | Yes – needs QA to fix
| Rupa |  |  |  | RELEASED IN PROD | Rupa |  | Yes – needs DPO Approval to fix
| Geetha |  |  |  |  | Geetha
| Nick |  |  |  |  | Nick
Navya
Sarath
Shraddha
Note on A1: This list feeds the dropdown on Combined Delivery Data, column A (Domain). Add, remove, or rename values here and the dropdown updates automatically.
Note on B1: This list feeds the dropdown on Combined Delivery Data, column F (DB Developer). Add, remove, or rename values here and the dropdown updates automatically.
Note on C1: This list feeds the dropdown on Combined Delivery Data, column G (PBI Developer). Add, remove, or rename values here and the dropdown updates automatically.
Note on D1: This list feeds the dropdown on Combined Delivery Data, column E (PO). Add, remove, or rename values here and the dropdown updates automatically.
Note on E1: This list feeds the dropdown on Combined Delivery Data, column Z (Blocked?). Add, remove, or rename values here and the dropdown updates automatically.
Note on F1: This list feeds the dropdown on Combined Delivery Data, column C (Current Status). Add, remove, or rename values here and the dropdown updates automatically.